Community Based Approach to Local Development Project

FIRST QUARTERLY

PROGRESS REPORT

JANUARY - MARCH

2011

| Project is financed by European Union |  | Project is cofinanced and implemented by UNDP |
| --- | --- | --- |

TABLE OF CONTENTS

| Executive Summary | 1 |
| --- | --- |
| Statistical Abstract | 2 |
| Introduction | 3 |
| Developing Support Structures | 6 |
| Developing Capacity | 8 |
| Community Projects | 9 |
| Replication of Methodology | 12 |
| Communication and Visibility | 14 |
| Advisory and Management | 19 |
| Lessons and Future Outlook | 20 |
| Annexure | 21-33 |

LIST OF ABBREVIATIONS

| ARC | Autonomous Republic of Crimea |
| --- | --- |
| CBA | Community Based Approach to Local Development Project |
| CDO | Community Development Officer (CBA staff in the region) |
| CDP | Community Development Plan |
| CO | Community Organisation |
| EU | European Union |
| LDF | Local Development Forum |
| MDG | Millennium Development Goals |
| MPP | Micro Project Proposal |
| MP | Micro Project (Community Project) |
| OC | Oblast Council |
| OCC | Oblast Coordination Council |
| OCRC | Oblast Community Resource Centre (same as OIU) |
| OIU | Oblast Implementation Unit (same as OCRC) |
| OSA | Oblast State Administration |
| PA | Partnership Agreement |
| PMU | Project Management Unit (CBA head office in Kyiv) |
| RC | Rayon Council |
| RCRC | Rayon Community Resource Centre |
| RSA | Rayon State Administration |
| UMDG | Ukrainian Millennium Development Goal |
| UNDP | United Nations Development Programme |
| VC/CC | Village Council/City Council |

Acknowledgement to Our Partners

| Ministry of Regional Development and Construction |  | Secretariat of the Cabinet of Ministers of Ukraine |
| --- | --- | --- |

|  | Cabinet of Ministers and Supreme Council of ARC |  |  | Cherkaska Oblast State Administration and Council |  |  | Chernihivska Oblast State Administration and Council |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Chernivetska Oblast State Administration and Council |  |  | Dnipropetrovska Oblast Council |  |  | Donetska Oblast State Administration and Council |
|  | Ivano-Frankivska Oblast State Administration and Council |  |  | Kharkivska Oblast State Administration and Council |  |  | Khersonska Oblast State Administration and Council |
|  | Kirovohradska Oblast State Administration and Council |  |  | Khmelnytska Oblast State Administration and Council |  |  | Kyivska Oblast State Administration and Council |
|  | Lvivska Oblast State Administration and Council |  |  | Luhanska Oblast State Administration and Council |  |  | Mykolaivska Oblast State Administration and Council |
|  | Odeska Oblast State Administration |  |  | Poltavska Oblast State Administration and Council |  |  | Rivnenska Oblast State Administration and Council |
|  | Sumska Oblast State Administration and Council |  |  | Vinnytska Oblast State Administration and Council |  |  | Volynska Oblast State Administration and Council |
|  | Ternopilska Oblast Administration and Council |  |  | Zakarpatska Oblast State Administration and Council |  |  | Zaporizka Oblast State Administration and Council |
|  |  |  |  | Zhytomyrska Oblast State Administration |  |  |  |

We acknowledge the support and cooperation on the part of the Government of Ukraine (especially the Secretariat of Cabinet of Ministers and the Ministry of Regional Development and Construction) and our regional partners, namely Oblast State Administrations and Oblast Councils. We also acknowledge the support of all pilot rayon authorities (rayon state administrations and councils) and village/city councils that are the partners of CBA Project for their support in CBA implementation.

Similarly, CBA team would like to thank all the institutions/individuals involved in the implementation process for their cooperation during the year, namely EU Delegation and UNDP management, the community organisations, officials of oblast and rayon state administrations/councils, NGOs, media, other public and private agencies.

Executive Summary

CBA Project was launched in December 2007 with objectives to strengthen participatory governance and improve living quality of the Ukrainian population living in rural areas. Over a period of 3.5 years, it is expected to involve 25 regions, 200 rayons, 1000 village/city councils and 1000 communities into the process of sustainable local development under the framework of self-help, partnership and mutual cooperation.

Cumulative achievements indicate that CBA has achieved all its targets. First quarter of 2011 was dedicated mostly to works on completion of micro-projects (hadover, sustainability mechanism, public audit), and finalizing and dissemination of documentation of experience. Summary of CBA activities during first quarter of 2011 are given hereunder:

- Support structure development: 1 rayon community resource centre was established during the reporting period in Khersonska oblast (making it 176 in total since inception) in order to support function of LDFs, and coordinate community-driven initiatives with local authorities and potential donor.

With these achievements, CBA targets in the area of creation of support structures got accomplished.

- Human resource development: In a bid to enhance skill of human resources involved in CBA implementation, 2151 CO-executives, 477 officials of local government and district/regional/national level state bodies participated in trainings during the quarter. In total, 37,040 persons (including 29,402 CO-executives, 7527 local/regional authorities and 111 Project personnel) participated in trainings of the Project until first quarter of 2011. Necessary logistics were provided for effective functioning of community organisations, rayon community resource centres and oblast community resource centres. As a result of the training and logistic support, CBA could witness effective implementation of its activities in the regions.

- Micro-projects: In first quarter 2011, last 48 MPs were completed (works done), making it 1303 since inception. During the reported period, 121 O&M funds (total 928 since inception) were created; 144 objects were handed over (total 1299 since inception) to the balance of local authorities. Public audit was conducted for 97 micro-projects in first quarter 2011, making it 1302 since inception.

- Information and Communication: Following events/activities were recorded in the area of information and communication:

Media were found to be active in rendering transparency to Project activities. In first quarter 2011, 24 media events took place while 433 media coverage were traced during the same period. Also during the quarter, a total of 33 newsletters were issued and 113 website publications about CBA were recorded at local level.

    - Lessons learned: Micro-project implementation gets heavily influenced by the timeliness of cost-sharing from the local budget.

Outlook of CBA activities till end of May 2011: activity related to closing CBA-I and preparation for CBA-II

Statistical Abstract

| SN | Activity | Target | Achievement |
| --- | --- | --- | --- |
|  |  |  | 2008 | 2009 | 2010 | 2011 | Total |
|  |  | Unit | Qty. |  |  |  | I Q |  |
| 1 | Establishment of central office of CBA | Number | 1 | 1 | - | - | - | - |
| 2 | Establishment of regional implementation units | Number | 25 | 24 | 1 | - | - | - |
| 3 | Partnership Agreement signed with regions | Number | 25 | 22 | 3 | - | - | - |
| 4 | Rayons selected | Number | 200 | 193 | 14 | 2 | - | 2 |
| 5 | Partnership agreement signed with rayons | Number | 200 | 177 | 27 | 5 | - | 5 |
| 6 | VC/CC selected and partnership established | Number | 1000 | 961 | 117 | 45 | - | 1123 |
| 7 | Communities selected | Number | 1000 | 876 | 222 | 47 | - | 1145 |
| 8 | Community Organisation (CO) |  |  |  |  |  | - |  |
|  | Created | Number | 1000 | 709 | 380 | 60 | - | 1149 |
|  | Enrolled with VC/CC | Number | 1000 | 550 | 519 | 79 | - | 1148 |
|  | Legally registered | Number | 1000 | 400 | 645 | 98 | - | 1143 |
| 9 | Household participation/membership (pilot COs) |  |  |  |  |  |  |  |
|  | Target households (cumulative) | Number | - | 267876 | 365055 | 420357 | - | 420357 |
|  | Household participated (cumulative) | Number | - | 82122 | 262480 | 331442 | - | 331442 |
|  | Household participation level (cumulative) | % |  | 31% | 72% | 78,8% | - | 78,8% |
|  | CO-members – total (cumulative) | Number | - | 96698 | 318,797 | 418739 | - | 418739 |
|  | CO-members – female | % | - | 60.1 | 60.5 | 58 |  | 58 |
|  | CO-members – male | % | - | 39.9 | 39.5 | 42 | - | 42 |
| 10 | Local Development Forum (LDF) created | Number | 200 | 98 | 106 | 5 | - | 209 |
| 11 | LDF sittings held | Number | - | 107 | 654 | 726 | 70 | 1557 |
| 12 | Oblast Coordination Council (OCC) created | Number | 25 | 6 | 18 | 1 | - | 25 |
| 13 | OCC sittings held | Number | - | 8 | 59 | 62 | 2 | 131 |
| 14 | Rayon Community Resource Centers created | Number | 200 | 10 | 122 | 43 | 1 | 176 |
| 15 | Human resource development |  |  |  |  |  |  |  |
|  | Trainings conducted | Number | - | 304 | 507 | 845 | 103 | 1759 |
|  | Training participants | Number | - | 7442 | 11009 | 15961 | 2628 | 37040 |
|  | CO-members | Number | - | 5584 | 8640 | 13027 | 2151 | 29402 |
|  | Local authorities | Number | - | 1791 | 2325 | 2934 | 477 | 7527 |
|  | Project personnel | Number | - | 67 | 44 | - | - | 111 |
| 16 | Community planning and mainstreaming |  |  |  |  |  |  |  |
|  | CO with community dev. plan (CDP) | Number | 1000 | 389 | 662 | 88 | - | 1139 |
|  | CDP Approved at LDF | Number | 1000 | 232 | 786 | 120 | - | 1138 |
| 17 | Micro-project (MP) proposals | Number |  |  |  |  |  |  |
| 17a | Approved by LDF | Number | 1175 | 122 | 889 | 330 | - | 1341 |
| 17b | Submitted by COs to CBA | Number | 1175 | 62 | 899 | 367 | - | 1326 |
| 17c | Approved by CBA | Number | 1175 | 47 | 832 | 425 | - | 1304 |
| 17d | Related with: |  |  |  |  |  | - |  |
|  | Energy saving | % |  | 62 | 53 | 70 | - | 59 |
|  | Health | % |  | 19 | 23 | 18 | - | 21 |
|  | Water supply | % |  | 13 | 18 | 8 | - | 15 |
|  | School transportation | % |  | 6 | 5 | 3 | - | 4 |
|  | Environment | % |  | 0 | 1 | 1 | - | 1 |
| 17e | Total cost of approved MPPs | UAH ml |  | 6.3 | 122.2 | 67.8 | - | 196.3 |
|  | Shared by COs | % | 5.0 | 10.2 | 7.3 | 7.1 | - | 7.2 |
|  | Shared by VC/CC | % | 45 | 14.6 | 10.8 | 12.2 | - | 12.8 |
|  | Shared by rayon/oblast authorities | % |  | 36.2 | 33.4 | 32.6 | - | 32.2 |
|  | Shared by CBA | % | 50 | 38.5 | 46.8 | 46.5 | - | 46.5 |
|  | Shared by others (private sponsors) | % | - | 0.5 | 1.6 | 1.6 | - | 1.3 |
| 17f | Beneficiary characteristics of approved MPs |  |  |  |  |  |  |  |
|  | Beneficiary population | % |  |  | 702995 | 498218 | - | 1201638 |
|  | Institutional benefitiary |  |  |  |  |  | - |  |
|  | School/kindergarten (cum.) | % |  | - | 45.0 | 57.6 | - | 51 |
|  | Healthpost (cum.) | % |  | - | 23.0 | 16.2 | - | 21 |
|  | Local communities (cum.) | % |  | - | 32.0 | 25.6 | - | 28 |
|  | Number of MPs funded by CBA | Number | 1175 | 76 | 648 | 582 | - | 1303 |
|  | MPs Completed | Number | 1175 | 0 | 165 | 1090 | 48 | 1303* |
| 18 | Information campaign and media strategy |  |  |  |  |  |  |  |
|  | Media events | Number | - | 249 | 115 | 209 | 24 | 597 |
|  | Media coverage | Number | - | 753 | 1098 | 995 | 433 | 3279 |
|  | Publications (web sites) | Number | - | 203 | 363 | 223 | 113 | 902 |
|  | Newsletters | Number | - | 48 | 144 | 124 | 33 | 349 |

* Including 8 micro-projects where works were particially completed, excluding works to be done on local budget expence

Chapter One

1.1	Background

Community-Based Approach to Local Development (CBA) is a joint initiative of EC and UNDP launched in December 2007. It is founded on the experience worldwide and within Ukraine for solution to local development problems through active participation of citizens, elected bodies, state authorities, civil societies and private sector. It is meant for applying the principle of bottom-up, participatory approach country-wide and provide valuable inputs for reinforcing the MDGs.

1.2	Objectives

Main objective of the CBA Project is to create enabling environment for long-term self-sustaining social-economic and environmental development at local level throughout Ukraine.

Specific objectives of the Project are to imrove living conditions in rural and (semi-) urban communities; demonstrate participatory local governance for decentralised public service delivery; enhance skill of stakeholders at all level in the area of participatory local development; and contribute to policy recommendations needed for effective participation of local communities in the development process.

1.3	Implementation Methodology

The strategic goal of the CBA is to build capacity of the local communities and local authorities for participation into joint decision making process and use this capacity for multi-stakeholders cooperation and multi-sectoral interventions with ensured local ownership of the process. The process is bottom-up and involves stakeholders from grassroots, meso and macro level in the process as it moves upward.

Functional area of the Project (rayons, village/city councils and local communities) are selected through open competition based on the criteria of socio-economic hardship especially in the area of health, education, water supply, energy supply and environmental situation. Through the selection process, CBA reaches the most suffering areas/population of the region/rayon.

Local level activities of CBA is carried out under the framework of Partnership with the stakeholders. It is based on willingness and commitment of the local partners (communities, village/city councils, rayon authorities, regional authorities) for cost sharing and joint decision-making.

Social mobilistion tool is used to unleash the potentials of selected communities to help themselves and mobilise local authorities and other development partners in the locality to address common basic needs of the people on participatory basis. To this end, following support structures are created to facilitate smooth implementation:

- Most of the households in a selected community are organised into ‘community organisation (CO)’ which is founded on norms of good governance. CO serves as the vehicle for carrying out various activities of local development nature on their own or with support from other development agencies;

- Through networking of COs, village/city councils, rayon authorities, local/regional authorities, private sector and civil societies a ‘local development forum (LDF)’ is established at rayon level under the leadership of the head/deputy head of rayon authority. LDF facilitates in making participatory decisions, mainstreaming of community plans, resource mobilisation for implementation of plans and so on;

- Through networking of LDFs, oblast authorities and other stakeholders in the oblast, an ‘oblast coordination committee (OCC)’ for carrying out participatory monitoring, resource mobilisation and coordination at oblast level.

- Networking of stakeholders at the national level enables overall monitoring and advisory support.

Capacity of the COs is built in such a way that they are able to make joint decision with local authorities, mobilize resources, implement local priorities and sustain the result. Capacity of the partners (VC/CC, raiyon/oblast etc.) is strengthened in terms of human resources to implement participatory approach propagated by the Project. Training, exposure visits, dialogues and small grants (for community projects), appropriate institutional mechanisms etc. are used as tools for building capacity.

For timely and quality output, appropriate ‘quality supervision committee (QSC)’ and ‘management information systems (MIS)’ are established to make the stakeholders directly involved in the process of monitoring and assessment of the Project activities. Flow of information is bottom-up and participatory.

CBA Implementation process follows a 4-stage cycle of intervention – namely institution development, planning, implementation and utilisation. Each stage involves a series of activities and action points that ultimately yields results intended by the Project. In normal situation, the complete process is expected to take about 2 years.

1.4	Management Arrangement

The Project is managed by UNDP/Ukraine under overall guidance of deputy resident representative and under direct supervision of Senior Progra mme Manager. Execution of the Project is done by an implementation team with a central body in Kyiv and 25 regional implementation units, one in each region. Oblast Implementation Units (Community Resource Centres) are further supported by oblast authorities in terms of office premises and hалвuman resources. Similarly, each rayon partner has deputed one official for coordination and implementation purpose and has established modest form of district community resource centre. They all together implement local component of the CBA activities. LDF and OCC serve as a guiding body at local and regional level and steering committee of the Project serve as a guiding body at the national level.

1.5	Project Area

CBA Project works in all oblasts of Ukraine and Autonomous Republic of Crimea covering total of 207 rayons (eight/oblast in general) and 1100 village/city councils (5/rayon in general). Distribution of target areas is given in Map–I.

Map – I: Geographical Distribution of Project Area

Chapter One

Community organisation (CO) formed by the target communities, rayon level ‘local development forum (LDF)’, oblast level ‘oblast coordination council (OCC)’ and national level ‘steering committee (SC)’ are the key support structures that contribute significantly to participatory decision making, bottom-up planning process and resource mobilisation for implementation of micro-projects. CBA target is establishment of 1000 COs, 200 LDFs, 25 OCCs and one Steering Committee.

Target on creating support structures was achieved by the end of 2009, and was surpassed in 2010, with 1149 formed pilot COs, 209 LDFs, 25 O/RCCs and the national Steering Committee formed since inception of CBA. Thus, CBA has reached its targets on support structure creation. Details of support structures development are given hereunder:

1.1	Local Development Forum as Instrument of Cooperation with Communities

During first quarter 2011, LDFs held 70 sittings in 16 oblasts to debate and decide on the matters related, resource allocation, implementation of MPs and handover. In total, 1557 sittings of LDFs were held since inception.

In principle, LDFs were created to serve the purpose of CBA activities, but in practice, their role has expanded to cover non-CBA communities as well. In particular, they serve as a platform for knowledge, experience sharing, and information dissemination. In some oblasts specialists in innovative technologies, energy saving and other useful for communities spheres are invited to share their experience and advice communities.

Table – I: Function of LDFs and RCRC

|  | 2008 | 2009 | 2010 | 2011 | Cumulative |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | I-Q |  |
| Number of LDFs | 98 | 106 | 5 | - | 209 |
| Number of LDF meetings | 107 | 654 | 726 | 70 | 1557 |
| Rayons with RCRC created | 10 | 122 | 43 | 1 | 176 |

Oblastwise details are given in Annex – II

Box - I: Local Authorities about LDFs “To my mind, we would not manage joint work without LDFs. I was very much pleased that Head of RSA responded on our problems, helped us to handle numerous revisions of a newly constructed water supply line. Support of top officials of rayon administration, chief architect, head of RCRC create a feeling of confidence and comfort that you are not tete-a-tete with your problems” Pasichnyk. L. Head of Halchynska village council, Zhytomyrska oblast “At LDF sittings, we reveived approval for our two micro-projects. Upon discussions, rayon authorities provided us with letters of guarantee on co-financing. At LDF sittings, we always got necessary explanations about financial and legal issues related to our activity. Successful implementation of our micro-projects motivated representatives of neighbouring villages present at LDFs to use the methodology and form COs as well”. Panasenko V. Head of CO ‘Majbutnje Palijvky’, Palijvka village, Malovyskivskyj rayon, Kirovohgadska oblast

3.3  Rayon Community Resource Centre

In the process on CBA implementation, rayon community resource cetres (RCRC) emerged following the initiative of rayon authoties. In practice, all 209 partner RSAs/RCs were expected to establish a resource centre. Of them, 176 RCRC were established formally. The RCRCs are carrying out various functions (e.g. secretariat of LDFs, local plan mainstreaming, building capacity of local communities, coordination etc.) so as to ensure effective implementation of CBA. Experience shows that rayon resource centres extended their activities beyond CBA, serving other communities interested to get organized and implement self-help initiatives.

Coordinator of Lokhvytsky RCRC works with community

representative

RSA/RC staff coordinating activities of these resource centres have participated in trainigns organized  by CBA, and have developed their capacity of working with local communities through ‘learning by doing’.

The work of rayon community resource centres is highly appreciated by local communities and authorities, in future CBA Project envisages further support for development of the network of RCRCs.

Formal establishment of RCRCs was mostly finished till the end of 2010. In first quarter 2011, 1 rayon community resource centre (RCRC) was formally created in partner rayon in Khersonska oblast, making it 176 since inception.

Box - II: Vox Populi: Heads of COs About RCRC ‘Working on idea about RCRC, I prioritized its effectiveness. Therefore, I started with developing a statute and regulations related to its functioning. Besides, we introduced changes to the ToR of the specialist coordinating RCRC activities. Therefore, our work was organized so as to turn our RCRC into the centre of community development and attracting additional investment for socio-economic development of rural areas. We possess a database of donors working in Ukraine, recommendations for preparation of project prposals, samples of necessary documents etc. We are always happy to support community’s initiatives’. Strashna L.M. Head of RCRC, Head of Department of Economic, Zvenyhorodskyj RSA, Cherkaska oblast ‘Community refers to the village council, as the primary institution for help in project implementation. We try to assist, but for us this kind of activities is new as well. Therefore, RCRC became a great support for us, providing us with all necessary information and assistance, e.g. legal registration of CO, receiving all certificate, routine work on micro-project implementation’. Holonivets S. Head of Halychany village council, Horohivsky rayon, Volynska oblast

1.4	Oblast Coordination Council

During the quarter, 2 sittings of the oblast coordination councils was recorded in Luhanska and Lvivska oblasts. In total, 131 sittings of OCCs occurred since inception (Table – II).

Table - II: Formation and Sittings of OCCs

|  | 2008 | 2009 | 2010 | 2011 | Cumulative |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | I-Q |  |
| Number of OCC formed | 6 | 18 | 1 | - | 25 |
| Number of meetings | 8 | 59 | 62 | 2 | 131 |

Oblastwise details are given in Annex – II

These sittings were focused on the following issues:

- Reviewing of results of CBA-I

- Handover of completed MPs

- Presentation of documentation of experience and short films about the Project implementation in oblast.

Box - III: Local Authority Representative About OCC ‘Sitting to sitting of OCC, we observed changes in people’s attitude toward the Project. Approval of support program at oblast level significantly contributed to the increase in the level of trust towards authorities. No other kind of sitting ever evoked such interest. Usually, people tend to avoid such meetings. But in case of OCC, even before the invitations are sent out, I often receive calls with enquiries whether we have not forgotten to include them into the list of participants. This is why each of OCC meetings was an extended one.’ Kulyk M. CBA focal person in Cherkaska oblast ‘‘I believe that the strength of OCC is in its composition, including representatives of institutions/departments beyond OSA. OCC is the instrument allowing to coordinate the work of all relevant institutions. Often, OCC meetings resulted in compromises or innovative mechanisms, e.g. mechanism of parallel funding of school bus purchase.’ Gyzhko A. Head of Department of Economic, CBA focal person, Vinnytska OSA

Chapter Two

Capacity building is one of the crucial activities of CBA Project. It involves such activities as training, exposure visits, dialogues and various other forms of techniques utilized for skill enhancement/knowledge transfer. The purpose is to enable local communities, local authorities and other partners to adopt and practice the approach promoted by the Project.

During first quarter, 103 capacity building events took place in participation of 2628 persons representing oblast/rayon authorities, village/city councils (477) and community organisations (2151). In total since inception, 1759 capacity building events took place in participation of 37,040 persons. Details on these events are given hereunder:

A series of training were organized in 15 oblasts for CO-executives during the quarter. The courses covered such areas as micro-project handover (32); public audit (22); participatory assessment of COs (15), finance management (3); and other (31). Oblastwise details are given in Annex- III. Since CBA inception, 1759 trainings were organized in which 29,402 CO-executives and members participated. Of the total participants, 59% were females and 41% were males.

Table – III: Trainings Organised for COs

|  | 2008 | 2009 | 2010 | 2011 | Cumulative |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | I-Q |  |
| No of trainings | 304 | 507 | 845 | 103 | 1759 |
| Total participants | 7442 | 11009 | 15961 | 2628 | 37040 |
| Male – No. (%) | 2976 (38.4) | 4409 (40.0) | 6598 (41.3) | 1377 (52.4) | 15360 (41.4) |
| Female – No. (%) | 4466 (61.6) | 6600 (60.0) | 9363 (58.7) | 1251 (47.6) | 21680 (58.6) |
| Participants by beneficiary type |  |  |  |  |  |
| CO-members – No. (%) | 5584 (75.0) | 8640 (78.5) | 13027 (81.7) | 2151 (81.8) | 29402 (79.6) |
| Local Authorities – No. (%) | 1791 (24.1) | 2325 (21.1) | 2934 (18.3) | 477 (18.2) | 7527 (20.4) |
| Project Personnel – No. (%) | 67 (0.9) | 44 (0.4) | - | - | 111 |

Oblast wise details are given in Annex –III

.

Chapter Three

CBA aims to improve living condition of local communities and strengthen participatory governance. For this purpose, it supports implementation of local priorities reflected in term of ‘community projects’ or ‘micro-projects’ through small grants based on equity, do-ability, sustainability and cost sharing criteria. These priorities are developed by the COs and mainstreamed into local development plans through joint decision-making process.

All micro-project proposals were approved by the end of 2010. In total since inception, 1303 MPPs were approved and implemented. Details of micro-projects supported by CBA are give on CBA website: http://www.cba.org.ua/ua/activities/microprojects.

Of all implemented MPs, 59% are devoted to energy saving, followed by 21% on healthcare, and 14.5% on water supply, 4.5% on school transport, 1% on environment (see Chart - I ). Oblastwise details are given in Annex - IV.

Chart - I: Distribution of Implemented MPs by Typology

Total cost of micro-projects is 196.3 UAH. According to the cost-sharing arrangement, micro-projects were to be co-funded by local budge (45%), COs (5%), and CBA (50%). Actual cost-sharing arrangement is as follows: CO contributed 7.2% and CBA share constitutes 46.5%, while local authorities’ input is 45%, and 1.3 % was provided by private sector. Oblast wise details are given in Annex - V.

The implemented micro-projects are meant to bring improvement either in communal infrastructure or on community territory so that community members could ultimately benefit. About 1.201.638 persons benefited from implementation of 1303 micro-projects. Distribution of beneficiary population by sectors and institutions are given in Chart - II and Chart - III. Details by oblast are given in Annex - VI and VII.

| Chart - II: Beneficiary Population by Sector | Chart - III: Beneficiary by Institution |
| --- | --- |

3.1	Implementation of Micro-projects

In first quarter 2011, activity on implementation of MPs was concentrated mostly on their completion (receipt of third tranches, preparation of final reports, public audit conduction, handover of the objects, O&M funds establishing etc.). In reported period, 48 MPs were copleted (works done). Since inception, 1303 MPs were completed (works done). Oblastwise details about tranches released for MPs are given in Annex - VIII.

| Solar battery on the roof of kindergarten, Kaharlyk village, Odeska oblast | Renovated watersupply line, Chernopopillya village, Zaporiska oblast | School bus, Buymer village, Sumska oblast |
| --- | --- | --- |

  - Post-completion Actions

Once the micro-project is completed, the CO passes through a series of steps involving public audit, commissioning, handover, inauguration, media outreach, permanent donors’ visibility, operation and maintenance etc. All these ensure high degree of transparency and high probability of resource utilization and local ownership of the object created. The feeling of ownership of the completed micro-projects is necessary for its operation and maintenance with community participation.

Box - V: Vox Populi: Heads of COs About QSC Our QSC is composed on qualified RSA specialists. They controlled all technical and financial issues of our work on micro-project. It was a special arrangement in the framework of CBA implementation. Since we had quite difficult relations with the vendor, QSC rigidly controlled the quality of work, performed by him. Thanks to QSC, all works were completed accordingly though with a delay. Shvets N. Head of CO ‘Agency of Balahivka community development’, Balahivka village, Kirovogradska oblast ‘It was an eye-opening experience. Primarily, what is a tender, a vendor, and how can we get the work done with less possible cost and with best possible quality. Secondly, the issue of quality control was completely new. We do not have specialist of that kind in the village, which is why we were very happy to have support and help from qualified engeneers from RSA’. Vinnyk G. , Head of CO ‘Stohid’, Volynska oblast

3.2.1 Public audit

Upon completion of the project, CO organize a public audit of the sub-project. Public audititing is a process during which the CO members assess the performance of their executives and functional group. It involves general members, VC/CC officials, contractor, OIU team, media. During the meeting functional group presents final progress report to the CO. The CO members are invited to inspect the quality of physical output of the sub-project and financial transactions. They can receive clarification on quieries and make suggestions. Upon finding it satisfactory, the CO makes a public clearance of the tasks accomplished. The clearance is recorded in the minute and signed by all the beneficiaries. A brief summury of the report is supposed to be displayed to public on a signboard.

In the reporting quarter, 97 micro-projects were audited with participation of 6618 CO members and 189 local authority representatives (see Table - IV). Since inception, 1302  micro projects were audited.

Table – IV: Public Auditing of Completed Micro-projects

|  | 2008 | 2009 | 2010 | 2011 | Cumulative |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | I-Q |  |
| No of completed MPs | n/a | 165 | 1090 | 48 | 1303 |
| No of conducted public audits | n/a | 29 | 1145 | 97 | 1302 |

3.2.2	 Commissioning and Handover

Ensuring ownership of the results obtained by the COs in the framework of CBA is of utmost importance. Therefore, understanding must be reached with CO and VC/CC/RSA regarding at the ownership of the property created/rehabilitated and use/maintenance of the same.

As showed in Table - V, 48 completed objects were handed over to the balance of the owner (village council) with an increased market value. Since inception, the number of objets handed over amounts to 1300.

Table – V: Handover of the Completed Objects

|  | 2008 | 2009 | 2010 | 2011 | Cumulative |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | I-Q |  |
| No of completed MPs | n/a | 165 | 1090 | 48 | 1303 |
| No of objects handed over | n/a | 71 | 1085 | 143 | 1299 |

3.2.3 Operation and Maintaince of Objects

CBA Project promotes the idea of sustainable development at local level. This idea envisages creation of appropriate mechanism enabling enable the CBA communities to continuously receive the stream of benefit from the object created/repaired through active participation of the community members. In the first quarter, Guidelines on Operation and Maintenance of Micro-Projects were developed and distributed to OIUs so as to provide guidance on establishment of O&M mechanisms.

Table – VI: Sustainability of Completed Micro-projects

|  | 2008 | 2009 | 2010 | 2011 | Cumulative |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | I-Q |  |
| No of completed MPs | n/a | 165 | 1090 | 48 | 1303 |
| No. of objects with O & M in place | n/a | 82 | 705 | 141 | 928 |

In the reported quarter, 141 operation and maintainance funds were established by community organizations, making it 928 since inception (Table – VI); oblastwise details are given in Annex - VIII. This includes O&M funds established by the decision approved by the community meeting and recored in the minutes. Operation and maintenance of micro-projects by the community members is a relatively new idea, therefore, it lacks clarity, policy and procedures. Despite this, the COs try various options to actualize this idea.

Box - VI: Vox Populi: Heads of COs about O&M Funds ‘…implementing the micro projects in partnership with CBA, our community members understood that local problems could be solved only jointly. Therefore, after works were completed, we decided to create an operation and maintenance fund to maintain our water supply system. Each citizen pays a small fee per month. Besides, we refer for help to our local business’. Levchenko V. Head of ‘Dzherelo’ CO, Vilkhovets’ village, Zvenyhorodsky rayon, Cherkaska oblast ‘Creation of O&M fund is a sort of community’s insurance fund which could be used in case of budgetary shortage’ Markovych O. Head of Majdan village council, Zakarpatska oblast

Chapter Four

4.1	Methodology dissemination to non-pilot rayons

Successful results of the Project implementation in regions, and perspectives for its second phase motivated representatives of non-pilot communities as well as authorities of non-pilot rayons of several regions to search for more detailed information about CBA methodology. Taking into account the interest from non-pilot areas, community development officiers launched a series of special seminars for non-pilot rayons and communities.

During seminars for non-pilot rayons, community development officers presented experience of the Project implementation in pilot rayons. In some cases participants also visited pilot communities, where CO-activists presented their successful experience on self-organization and micro-project implementation.

  - Emergence of non-pilot community organizations

Following the example of CBA pilot COs, other communities started to get organized and form their community organizations to solve local problems collectively. In first quarter 2011, 72 non-pilot COs were formed using CBA methodology. Of them, 65 were registered in VC/CC and 52 got legally registered. In total since inception, 171 COs were formed using following the example of pilot CBA communities, 108 of them got legally registered. Oblast and rayon resource centers provided solid assistance to those communities willing to create a CO.

  - Communities’ initiatives beyond CBA

Successful implementation of micro-projects under CBA support, significantly increases the level of knowledge and the level of self-confidence of community members. Feeling of strong organization motivates community members to start other initiatives in parallel or after completion of MP. They apply for grants from other donors or/and participate in regional competitions.

During first quarter 2011, 48 pilot CBA COs applied for various programs and competitions for financing/co-financing of their initiatives. Of them, 24 received grants. The most active COs during first quarter were from ARC (21 COs applied for grants beyond CBA) and Mykolaivska oblast (15 COs applied for grants).

Table - VII: Number of Programs and Competitions Pilot COs Apply for

| Activity | 1st Quater 2011 | Since Inception |
| --- | --- | --- |
| No. Pilot COs applied for grants from other donors | 48 | 235 |
| No. Pilot COs received grants | 24 | 159 |

Rate of successfully won applications is quite high - 50 % of those of applied for grants and received them. It is due to the fact that CBA/COs prepare better proposal with sound cost sharing arrangement and they are confident in convinving donors that they can accomplish the task in time and with high quality.

Box – VII: Examples of Community Initiatives, in Parallel to MPP Implementation CO ‘Agency of Stuzhytja village development’, Zakarpatska oblast CO ‘Agency of Stuzhytsja village development’, was created within frameworks of cooperation with CBA Project in 2008. Before launching cooperation with CBA Stuzhytsja community planned to develop and realize a trouristic rout in the village and neighbourhood, however, absence of street lighting did not allow starting the project. Therefore, community applied for participation in CBA Project and successfully implemented evergy saving micro-project on street light renovation. In parallel CO implemented ‘Stuzhytsja is a perl of Ukrainian Carpatian Mountains’ project. Within this project a touristic route was developed which includes unique environmental and other interesting objects. This project was financed by community members, scientific organizations and other sponsors. Total project cost was 45,000 UAH. At the same time in 2010 the CO started to realize micro-project on construction of kindergarten in cooperation with ‘Vysochyna’ Foundation (Czech Republic). Therefore, participation in CBA Project allowed a distant and depressed village to become self-sufficient’. CO ‘Agency of Holovetska village council development’, Starosambirsky rayon, Lvivska oblast Successful implementation of micro-project on energy saving in village school motivated community members to solve other problems of local development in their villge. In parallel with cooperation with CBA, Holovetska village council applied for partnership with American corporation UPS in the realm of social problems within frameworks of privat-public partnership. Among the results of this successful cooperation are establishment of computer class with internet access in village secondary school, study visit of pupils to Polish partners etc. In Septermber 2010 within public-private partnrship with UPS, Holovetska village council received a new school bus. Nowadays, community continue to work on those problems defined in community development plan developed within cooperation with CBA Project. Community members applied for grant to Renessance foundation to establish centre for community development. Cooperation with CBA Project allowed community to feel is power and believe in own ability to change life in the villege to the better.

Chapter Five

Communication, visibility and public relation (PR) activities are designed as a part of Project implementation strategy with a purpose to maximize transparency about the Project activities and to lobby for the cause it aims to promote. Specific activities include media events, media coverage, web portal, communication dissemination, visibility tools etc.

During the reported quarter, 24 media events were held (597 since inception) at regional level, 433 media coverage took place (3279 since inception), 33 issues of regional newsletter were made public (349 since inception). Besides, CBA-web portal was maintained for wide public access to CBA-information and various tools were used for donor’s visibility.

Details of the activities are described below:

5.1	Media Events

Media events include seminars and press conferences. During the reporting period, 24 press conferences and other media events (including official inaugurations of micro-project) were held (597 since inception) in participation of senior management of OSAs and OCs, RSAs and RCs, village/city councils, representatives of local NGOs and mass media (Table –IX). Underlying was the idea of assuring maximum transparency of the CBA activities in the area.

Each media event was announced through media advisory distributed to local media. During the event, press releases and information packs were distributed containing more detailed information on the CBA Project with appropriate donors’ visibility.

5.2	Media Coverage

During first quarter, 433 media coverage were registered across Ukraine. It included printed and electronic editions, radio and TV reportages. Not all media coverage could be registered by the Project due to restricted capacity to collect reports on all media coverage taking place throughout the country. Data in progress since 2008 is given in Table – VIII hereunder.

Table - VIII: Media Coverage of CBA Activity

|  | 2008 | 2009 | 2010 | 2011 | Cumulative |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | I-Q |  |
| Press Conference and media events | 249 | 115 | 209 | 24 | 597 |
| Media coverage | 753 | 1098 | 995 | 433 | 3279 |
| Publications on websites | 203 | 363 | 223 | 113 | 902 |

Oblastwise details in Annex –IX.

Printed editions dominated among channels of dissemination of information on CBA with 33.7% of the total coverage. Distribution of media coverage among electronic media, television, and radio was quite uniform in the reported period. Electronic media occupied 23.3% of media coverage, and radio took 21.7%. Television occupied 20.8% of the coverage. Comparing with general overall distribution for the whole period of the Project activity in first quarter 2011 the distribution of media coverage became more uniform (see Chart - IV).

Chart - IV: Distributions of Media Coverage in 1st Quarter 2011 and Since Inception

During the quarter, the highest media coverage was found to be in Ivano-Frankivska, Kirovohradska, Poltavska and Zhytomyrska oblasts (see Chart – V). Relatively high number of media coverage cases in these oblasts is connected to quite high level of public activity. Ivano-Frankivska oblast hosted an interregional conference in February, Poltavska and Zhytomyrska oblasts organized 12 and 14 sittings of LDFs (respectively) in participation of mass media. OIU in Kirovohradska oblast actively involved media from pilot rayons. Their representatives were invited to visit pilot communities, and to participate in official inauguration of micro projects. This activity resulted in 55 cases of media coverage during first quarter 2011.

The lowest media coverage in first quarter 2011 recorded in Kharkivska, Zaporizka, Chernivetska oblasts and ARC.

Focus of oblast/rayon authorities on media involvement played significant role in development of  journalists network, interested in CBA activities and community development topic.

Chart - V: Media Coverage of CBA Activities During I Quarter 2011

5.3	Dissemination of Information About CBA

In order to disseminate information about the Project among stakeholders, potential participants and wider public audience, following actions were undertaken:

Newsletters: In order to duly and timely inform local partners/stakeholders as well as participants about progress of CBA activities in the region, a practice of publishing regional newsletters is in place. During the reporting period, OIUs in 12 oblasts published 33 issues of regional newsletter, which was printed and disseminated both electronically (2145 copies) and in printed copies (5825 copies), according to the distribution list including oblast administration and council, rayon administration and councils, village councils, local communities, local media and NGOs. The most active of them is Luhanska (11 issues), which is followed with Mykolaivska, Rivnenska, Vinnytska, and Zhytomyrska oblasts (3 issues for each). The number of issues of newsletters is connected with number of public events (OCC and LDF sittings) and trainings conducted in the region. The highest number of issues (11) published Luhanska oblast implementation unit. Data in progress since 2008 are given in Table - X.

Table – IX: Publication and Distribution of CBA Regional Newsletters

|  | 2008 | 2009 | 2010 | 2011 | Cumulative |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | I-Q |  |
| No. of issues published | 48 | 144 | 124 | 33 | 349 |
| No. of copies printed & distributed | 8207 | 25,617 | 20,198 | 5825 | 59,847 |
| No. of copies sent electronically | 3624 | 7478 | 3919 | 2145 | 17,166 |

Oblastwise details in Annex – X

Websites of partner oblast/rayon authorities were linked where possible for disseminating CBA related information, may it be tender or media events or CBA-newsletters. Cooperation of communication departments of these authorities were appreciative. During the quarter, 113 announcements/news appeared on partners web sites (902 since inception).

5.4	Donors’ visibility

Visibility of EU and UNDP was ensured at all micro-project sites though installation of temporary, boards and permanent plaques at all project sites. Additionally, community organizations produced information boards with EU and UNDP visibility items to display announcements on community meetings and other pertinent information.

5.5	Donor/Partner visits

# On 10 February, Deputy Country Director, Ms. Elena Panova visited 4 CBA communities in ARC with aim to observe the results of CBA activity. In each community a round table was organized with participation of community members to discuss their opinion about cooperation with the Project and satisfaction with results obtained.

| On 21 February, Ms. Laura Garagnani, Head of Operations of the Delegation to the European Union to Ukraine and Mr. Olivier Adam, UN Resident Coordinator visited Univ village in Lvivska oblast. During their visit to Lvivska oblast, Mr. Olivier Adam and Ms. Laura Garagnani met with Deputy Head of Lvivska oblast state administration and Head of Lvivska oblast council to discuss results of cooperation and perspectives for further implementation of common EU/UNDP Project CBA. Officials of Sambirskyi and Starosambirskyi rayons presented their results of cooperation with CBA Project and reported about self-organization of community on local development. | Ms. Laura Garagnani and Mr. Olivier Adam visited Univ village, Lvivska oblast |
| --- | --- |

# On 28 March, Ms Nuzhat Ehsan, Country Director, Ukraine, Bulgaria, Bosnia and Herzegovina, United Nations Population Fund and Mr. Pavlo Zamostian Assistant Representative, United Nations Population Fund visited Studenytsa village, Zhytomyrska oblast. During the visit participants met with representatives of CO ‘Dovira-1’, representatives of village council and other members of Studenitsya community. Mr. Viktor Gradovsky, Head of International Relations Department, OSA, and Nadiya Osinska, Head of Economic Department, Korostyshev RSA presented results of the Project implementation in Korostyshev rayon and Zhytomyrska oblast.

# 5.6	Media Events

# On 22 February 2011, the interregional conference ‘Community Initiative in Action: Local Development under Support of EU and UNPD’ was held in Ivano-Frankivska oblast state administration. The main goal of the event was to present the results and exchange success stories generated by the joint EU/UNDP Community Based Approach to Local Development Project. Representatives of local communities from 5 Western oblasts of Ukraine shared their experience in self-organization, establishing cooperation with local authorities, designing and implementing initiatives aimed at improving living conditions in their communities.

# On 25 February 2011 Olivier Adam, UN Resident Coordinator and Ms. Myroslava Didukh sector manager of EU Delegation to Ukraine, attended the conference “CBA Project in Donetska Oblast: Results, Perspectives, Innovations” marking the closure of the first phase of CBA Project, and outlining the perspectives of further cooperation.

# During the meeting a letter of intent was signed between Olivier Adam, UN Resident Coordinator and Anatoliy Blyznyuk, Governor of Donetska oblast outlining such priorities as promoting community based approach and creative effective participatory governance, building local and regional capacity for decentralized development etc. Among the participants of the conference was Mykola Zagorujko, Head of Association of local self-governance in Donetska oblast. Heads of RSA of pilot rayons and heads of pilot COs presents results of cooperation with the Projects.

5.6	Knowledge Management

National level application of community based approach to local development methodology produces tremendous effect on the local development processes. To make the best use of knowledge gained and lessons learned CBA aims to document and systematize the regional experience; to introduce community based approach in specific courses of higher education; to transfer the Ukrainian experience to the target audience in other countries. Details on these activities in first quarter 2011 are given hereunder:

Knowledge transfere:

| On 18 March, 30 students and 5 assistant professors of the College of Europe (Natolin, Warsaw) visited community of Univ village (Peremyshljanskyj rayon) to familiarize with results of CBA Project activities in Lvivska oblast. During the visit, participats met with members of Univ village community and observed with results of successful implemented initiatives of CO ‘Saint Klymentiy Sheptytskyj Charitable Foundation’. | Students of the College of Europe with pupils of Univ village school |
| --- | --- |

- In March 2011, CBA became a partner of ‘Do you know Europe?’ project developed within framework of ‘Ukraine-EU: Competition on cooperation and local development among senior pupils of Ukraine’. As a part of the project several teams of schoolchildren will visit pilot CBA communities to study about EU/UNDP activity in Ukraine in the realm of local development. After the visits each team is expected to develop a project paper of initiative or program for their village/city.

5.7 	Documentation of Experience

In light of necessity to ensure ownership and lay the foundation for future policy recommendations,  documentation of experience is being carried out under regional leadership in each region by a study team involving focal person from OSA/OC and RSA/RC, specialists from legal, technical and PR departments of OSA/OC or partner RSA/RC.

# 24 oblasts finalized their reports on experience documentation with 19 reports printed and 22 video films completed. Other oblasts are at the final stage of reports and films preparation. Published reports and film can be viewed at: http://cba.org.ua/ua/library/experience.

5.8	CBA Methodology in Academia

During overall period of CBA implementation, interest of academic institutions was evoked to introduce theory of area-based approach into the curriculum.

During first quarter 2011, letters of intention on future cooperation with UNDP were received from 8 universities. They also listed propositions for cooperation with CBA/UNDP in the second phase. Based on these propositions, a roadmap of cooperation with academia is to be elaborated.

In February 2011, CBA disseminated thought its network of partner universities information about conference on Baltic Program of Universities held by Upsala University, Sweden. Representatives of Chernihiv State University of Labour and Social Work and Sumy State University successfully applied and participated in the conference. A Memorandum about cooperation was signed between the Baltic Program of Universities and the two Ukrainian universities.

‘Participation in Baltic Program of Universities was very useful in establishing new contacts with colleagues working in the realm of sustainable development. We saw that they mostly work in the realm of ecological and economic sustainability, while social component is still underdeveloped. Using contacts established at the conference, one our student participated in conference on sustainability in Poland, it is expected to participate in several events in Germany’. Syla T., Dean of the Department of Social Work, Chernihiv State University of Labour and Social Work

On 15th March, meeting with representatives of Kyiv National Economic University took place. Main goal of the meeting was to discuss perspectives of cooperation. As a result of the meeting a letter of intention was sent by the University to CBA management with a proposition to sign a contract for mutual cooperation.

Chapter Six

# CBA Project is under direct execution of UNDP. UNDP ensures quality of management, resource utilization and timely achievement of results. Besides, partners and donors independently monitor the implementation of CBA Project, and regional/local authorities provide feed-back for effective implementation of the initiative. In this context, following actions took place in the first quarter 2011.

6.1	Assessment Survey and Policy Study

In first quarter 2011, final remarks for analytical report prepared by KIIS were made and preparation for publication of its Ukranian language version launched.

Draft assessment report prepared by ICPS was reviewed; discussion was organized in participation of experts from Association of towns and cities of Ukraine, and CBA Project. Draft was sent for comments of CDOs and focal persons from OSA.

# 6.2	Management

# First quarter 2011 was mainly devoted to activities related to finalization and closure of CBA-I. Key items of PMU and OIU activity initiated during first quarter are given hereunder:

# Archiving CBA-I documents

# Final report preparation

# Dissemination of CBA-I experience

# Training materials development

# Revising/updating of manuals, guidelines and templates

# Rating of rayon performance: OIU coordinators together with regional focal persons and other relevant officials from OSA and OC rate the performance of current partner rayons.

# Socio-economic ranking of rayons: Using the latest data set  prepared by regional authorities OIU coordinators prepare socio-economic status of all rayons in the regions.

# Stocking the lessons: based on experience of Project implementation during first phase, write up regarding lessons learned will be prepared.

6.3	Resource Utilisation

Financial progress of the Project as of March 2011 reached an estimated total of USD 744,259 which is 63.2% of the last budget revision approved by UNDP management for 2011 (Table –X).

Table – X : Expenditure in I Quarter 2011, USD

| № | Key Activities | Annual Budget 2011 | Expenditure Q-I |
| --- | --- | --- | --- |
|  |  | UNDP | EU | Total | UNDP | EC | Total |
| 1 | Training of Project staff and national counterparts | 36 999 | 7 453 | 44 453 | 5 253 | 13 908 | 19 161 |
| 2 | Establish mechanism of participatory planning process | 20 000 | 0 | 20 000 | 0 | 0 | 0 |
| 3 | Support COs for implementation of self-help initiatives | 75 170 | 276 974 | 352 145 | 80 753 | 306 323 | 387 076 |
| 4 | Establish partnership with oblasts & raiyons administrations, councils and other local stakeholders | 22 500 | 1 289 | 23 790 | 0 | 1 213 | 1 213 |
| 5 | Effective Project Management | 274 519 | 429 495 | 704 014 | 65 734 | 261 929 | 327 662 |
| 6 | PR, Communication and Monitoring | 32 000 | 792 | 32 793 | 0 | 9 146 | 9 146 |
| TOTAL | 461 188 | 716 006 | 1 177 194 | 151 740 | 592 519 | 744 259 |

Chapter Seven

7.1 	Lessons Learned

- At the end of CBA-I, significance of social mobilization became extremely apparent. The most mobilized, coherent and active community is, the easier it builds relations with local authority representatives, and the easier processes related to sustainability of the object.

- It became apparent the importance of technical and financial recommendations provided by the Project. The more precisely CO followed these recommendations, the easier it was for them to communicate with state structures (for example, treasury) and to prepare all financial and technical reports.

- Created COs confirmed their competence and sustainability. After finishing micro-projects, they could approach local authorities, national/international donors for grant support  and solve various issues related with pilot communities.

- Commitment of OIU personel is among important factors influencing success of the Project’s implementation in oblast. However, further capacity building support to them is desirable.

  - Future Outlook

Following activities will be carried out in remaining months:

- Completion of policy study;

- Organization of national round table;

- Finalization of experience documentation;

- Preparation for CBA – II;

- Project closing related activities (final financing and narrative report, inventory management; etc) will be undertaken;

- Final training to  community organizations;

- Training of academia and local authorities.

- Participation in Europe Day, organization of donor/partner visits;

- Participation in EU Energy Day

Annex -I:

Selected rayons, VC/CC, and Number of Pilot COs, Since Inception

| # | Oblast | No of Rayons | Selected VC/CC | Pilot COs |
| --- | --- | --- | --- | --- |
|  |  |  |  | Formed | Registered in VC/CC | Legally registered |
| 1 | ARC | 8 | 40 | 41 | 41 | 41 |
| 2 | Cherkaska | 8 | 40 | 42 | 42 | 42 |
| 3 | Chernihivska | 8 | 38 | 42 | 42 | 42 |
| 4 | Chernivetska | 11 | 47 | 47 | 47 | 47 |
| 5 | Dnipropetrovska | 8 | 42 | 42 | 42 | 42 |
| 6 | Donetska | 8 | 40 | 40 | 40 | 40 |
| 7 | I-Frankivska | 9 | 56 | 56 | 56 | 56 |
| 8 | Kharkivska | 8 | 41 | 42 | 42 | 42 |
| 9 | Khersonska | 8 | 45 | 45 | 45 | 45 |
| 10 | Khmelnytska | 8 | 50 | 50 | 50 | 50 |
| 11 | Kirovohradska | 8 | 45 | 45 | 45 | 45 |
| 12 | Kyivska | 9 | 47 | 50 | 50 | 49 |
| 13 | Luhanska | 9 | 46 | 46 | 46 | 46 |
| 14 | Lvivska | 8 | 50 | 51 | 50 | 50 |
| 15 | Mykolaivska | 8 | 44 | 45 | 45 | 45 |
| 16 | Odeska | 8 | 43 | 45 | 45 | 45 |
| 17 | Poltavska | 8 | 41 | 41 | 41 | 41 |
| 18 | Rivnenska | 8 | 41 | 49 | 49 | 45 |
| 19 | Sumska | 8 | 42 | 43 | 43 | 43 |
| 20 | Ternopilska | 9 | 55 | 57 | 57 | 57 |
| 21 | Vinnytska | 8 | 41 | 41 | 41 | 41 |
| 22 | Volynska | 9 | 47 | 47 | 47 | 47 |
| 23 | Zakarpatska | 9 | 58 | 58 | 58 | 58 |
| 24 | Zaporizka | 8 | 44 | 44 | 44 | 44 |
| 25 | Zhytomyrska | 8 | 40 | 40 | 40 | 40 |
|  | Total | 209 | 1123 | 1149 | 1148 | 1143 |

Annex - II:

Formation and Function of OCC, LDF and RCRC

| # | Oblast | OCC sittings, I-Q | OCC sittings since inception | LDF sittings, I-Q | LDF sittings since inception | RCRC created in I-Q | RCRC created since inception |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | ARC | 0 | 7 | 0 | 47 | 0 | 7 |
| 2 | Cherkaska | 0 | 6 | 8 | 64 | 0 | 8 |
| 3 | Chernihivska | 0 | 5 | 4 | 50 | 0 | 8 |
| 4 | Chernivetska | 0 | 3 | 2 | 44 | 0 | 1 |
| 5 | Dnipropetrovska | 0 | 2 | 1 | 39 | 0 | 6 |
| 6 | Donetska | 0 | 1 | 1 | 40 | 0 | 8 |
| 7 | Ivano-Frankivska | 0 | 3 | 0 | 36 | 0 | 5 |
| 8 | Kharkivska | 0 | 3 | 2 | 59 | 0 | 8 |
| 9 | Khersonska | 0 | 9 | 2 | 71 | 1 | 5 |
| 10 | Khmelnytska | 0 | 4 | 0 | 58 | 0 | 3 |
| 11 | Kirovohradska | 0 | 5 | 4 | 133 | 0 | 8 |
| 12 | Kyivska | 0 | 3 | 2 | 53 | 0 | 9 |
| 13 | Luhanska | 1 | 15 | 0 | 73 | 0 | 9 |
| 14 | Lvivska | 1 | 11 | 1 | 67 | 0 | 8 |
| 15 | Mykolaivska | 0 | 4 | 0 | 57 | 0 | 8 |
| 16 | Odeska | 0 | 7 | 4 | 60 | 0 | 6 |
| 17 | Poltavska | 0 | 4 | 12 | 72 | 0 | 8 |
| 18 | Rivnenska | 0 | 3 | 0 | 67 | 0 | 4 |
| 19 | Sumska | 0 | 6 | 4 | 80 | 0 | 8 |
| 20 | Ternopilska | 0 | 4 | 3 | 65 | 0 | 9 |
| 21 | Vinnytska | 0 | 10 | 6 | 40 | 0 | 8 |
| 22 | Volynska | 0 | 4 | 0 | 40 | 0 | 9 |
| 23 | Zakarpatska | 0 | 5 | 0 | 67 | 0 | 7 |
| 24 | Zaporizka | 0 | 4 | 0 | 111 | 0 | 8 |
| 25 | Zhytomyrska | 0 | 3 | 14 | 64 | 0 | 8 |
|  | Total | 2 | 131 | 70 | 1557 | 1 | 176 |

Annex - III:

Trainings Organized for COs in I Quarter 2011 and Since Inception

| # | Oblast | No of trainings | Total participants | Of Total Participants | of Total Participants |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Male | % | Female | % | CO-members | % | Local Authorities | % |
| 1 | ARC | 2 | 29 | 12 | 41,4 | 17 | 58,6 | 24 | 82,8 | 5 | 17,2 |
| 2 | Cherkaska | 8 | 302 | 211 | 69,9 | 91 | 30,1 | 203 | 67,2 | 99 | 32,8 |
| 3 | Chernihivska | 14 | 376 | 152 | 40,4 | 224 | 59,6 | 362 | 96,3 | 14 | 3,7 |
| 4 | Chernivetska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 5 | Dnipropetrovska | 2 | 80 | 36 | 45,0 | 44 | 55,0 | 79 | 98,8 | 1 | 1,3 |
| 6 | Donetska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 7 | Ivano-Frankivska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 8 | Kharkivska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 9 | Khersonska | 8 | 167 | 68 | 40,7 | 99 | 59,3 | 72 | 43,1 | 95 | 56,9 |
| 10 | Khmelnytska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 11 | Kirovohradska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 12 | Kyivska | 6 | 122 | 55 | 45,1 | 67 | 54,9 | 104 | 85,2 | 18 | 14,8 |
| 13 | Luhanska | 4 | 86 | 15 | 17,4 | 71 | 82,6 | 59 | 68,6 | 27 | 31,4 |
| 14 | Lvivska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 15 | Mykolaivska | 3 | 76 | 29 | 38,2 | 47 | 61,8 | 68 | 89,5 | 8 | 10,5 |
| 16 | Odeska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 17 | Poltavska | 16 | 436 | 294 | 67,4 | 142 | 32,6 | 356 | 81,7 | 80 | 18,3 |
| 18 | Rivnenska | 2 | 43 | 20 | 46,5 | 23 | 53,5 | 40 | 93,0 | 3 | 7,0 |
| 19 | Sumska | 6 | 144 | 57 | 39,6 | 87 | 60,4 | 123 | 85,4 | 21 | 14,6 |
| 20 | Ternopilska | 2 | 38 | 22 | 57,9 | 16 | 42,1 | 20 | 52,6 | 18 | 47,4 |
| 21 | Vinnytska | 18 | 412 | 252 | 61,2 | 160 | 38,8 | 372 | 90,3 | 40 | 9,7 |
| 22 | Volynska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 23 | Zakarpatska | 4 | 97 | 56 | 57,7 | 41 | 42,3 | 89 | 91,8 | 8 | 8,2 |
| 24 | Zaporizka | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 25 | Zhytomyrska | 8 | 220 | 98 | 44,5 | 122 | 55,5 | 180 | 81,8 | 40 | 18,2 |
|  | Total | 103 | 2628 | 1377 | 52,4 | 1251 | 47,6 | 2151 | 81,8 | 477 | 18,2 |
|  | Cumulative* | 1759 | 36929 | 15275 | 41,4 | 21654 | 58,6 | 29402 | 79,6 | 7527 | 20,4 |

*Excluding 111 Project staff trained during 2008-2009

Annex -  IV:

Number of Micro Projects Approved and Implemented Since Inception

| # | Oblast | # Appr. MPs | # MPs by typology |
| --- | --- | --- | --- |
|  |  |  | Health | Energy saving | Water supply | Environment | School bus |
| 1 | ARC | 45 | 6 | 29 | 6 | 1 | 3 |
| 2 | Cherkaska | 54 | 26 | 22 | 6 | 0 | 0 |
| 3 | Chernihivska | 45 | 12 | 27 | 6 | 0 | 0 |
| 4 | Chernivetska | 50 | 10 | 37 | 2 | 0 | 1 |
| 5 | Dnipropetrovska | 55 | 20 | 23 | 10 | 0 | 2 |
| 6 | Donetska | 51 | 9 | 29 | 9 | 1 | 3 |
| 7 | Ivano-Frankivska | 69 | 5 | 62 | 0 | 2 | 0 |
| 8 | Kharkivska | 47 | 3 | 36 | 5 | 1 | 2 |
| 9 | Khersonska | 54 | 13 | 34 | 7 | 0 | 0 |
| 10 | Khmelnytska | 50 | 8 | 33 | 4 | 0 | 5 |
| 11 | Kirovohradska | 53 | 3 | 36 | 7 | 1 | 6 |
| 12 | Kyivska | 55 | 13 | 36 | 6 | 0 | 0 |
| 13 | Luhanska | 55 | 13 | 30 | 11 | 0 | 1 |
| 14 | Lvivska | 54 | 13 | 36 | 3 | 1 | 1 |
| 15 | Mykolaivska | 52 | 1 | 34 | 14 | 0 | 3 |
| 16 | Odeska | 45 | 8 | 20 | 17 | 0 | 0 |
| 17 | Poltavska | 50 | 5 | 16 | 22 | 0 | 7 |
| 18 | Rivnenska | 49 | 17 | 26 | 0 | 1 | 5 |
| 19 | Sumska | 49 | 10 | 15 | 19 | 2 | 3 |
| 20 | Ternopilska | 63 | 13 | 41 | 5 | 1 | 3 |
| 21 | Vinnytska | 41 | 8 | 20 | 5 | 0 | 8 |
| 22 | Volynska | 57 | 7 | 47 | 2 | 0 | 1 |
| 23 | Zakarpatska | 61 | 18 | 39 | 3 | 1 | 0 |
| 24 | Zaporizka | 53 | 8 | 25 | 16 | 0 | 4 |
| 25 | Zhytomyrska | 46 | 26 | 17 | 3 | 0 | 0 |
|  | Total | 1303 | 275 | 770 | 188 | 12 | 58 |
|  | % |  | 21% | 59% | 15% | 1% | 4% |

Annex – V:

Co-Financing Pattern of Micro-Projects Processed Since Inception

| # | Oblast | # Approved MPs | Total project cost | Cost-Sharing Arrangement |
| --- | --- | --- | --- | --- |
|  |  |  |  | CO | CBA | Local Budget | Private Sector |
|  |  |  |  |  |  | Sub-Total | VC | RSA | OSA |  |
| 1 | ARC | 45 | 7759583 | 644124 | 3126290 | 3989169 | 2598522 | 1390647 | 0 | 0 |
| 2 | Cherkaska | 54 | 7077357 | 553667 | 3578409 | 2759392 | 1587771 | 1170121 | 1500 | 185889 |
| 3 | Chernihivska | 45 | 6625473 | 446426 | 3150834 | 2968011 | 513722 | 2454289 | 0 | 60202 |
| 4 | Chernivetska | 50 | 7761192 | 543540 | 3768836 | 3448816 | 75850 | 3372966 | 0 | 0 |
| 5 | Dnipropetrovska | 55 | 9584400 | 932146 | 3536554 | 4665311 | 2064316 | 1121216 | 1479779 | 70087 |
| 6 | Donetska | 51 | 7448787 | 405110 | 4866183 | 3467043 | 3059113 | 407930 | 0 | 40080 |
| 7 | I-Frankivska | 69 | 9167531 | 704842 | 3330080 | 3544463 | 221591 | 3322872 | 0 | 52043 |
| 8 | Kharkivska | 47 | 6742346 | 391317 | 3447507 | 2935495 | 711282 | 2247213 | 0 | 99454 |
| 9 | Khersonska | 54 | 7066218 | 402820 | 3350324 | 3189337 | 1506255 | 1459082 | 224000 | 26554 |
| 10 | Khmelnytska | 50 | 6925612 | 472656 | 3512276 | 3062448 | 427431 | 2535017 | 100000 | 40184 |
| 11 | Kirovohradska | 53 | 7236316 | 670688 | 3630975 | 2719779 | 665002 | 2054777 | 0 | 333573 |
| 12 | Kyivska | 55 | 7511183 | 401709 | 3447507 | 3379310 | 1474044 | 1913564 | 0 | 90891 |
| 13 | Luhanska | 55 | 8082413 | 633681 | 3553404 | 3459374 | 1594125 | 1655601 | 209648 | 435954 |
| 14 | Lvivska | 54 | 8864881 | 506095 | 4106835 | 4238946 | 375893 | 3863053 | 0 | 13005 |
| 15 | Mykolaivska | 52 | 7251106 | 452824 | 3563142 | 3235140 | 1229177 | 2005963 | 0 | 0 |
| 16 | Odeska | 45 | 6960297 | 570676 | 3430003 | 2908350 | 210990 | 2697360 | 0 | 51268 |
| 17 | Poltavska | 50 | 7206001 | 390948 | 3523746 | 3234176 | 79787 | 1799474 | 1354915 | 57131 |
| 18 | Rivnenska | 49 | 8318185 | 642679 | 3569155 | 4078146 | 737468 | 3340678 | 0 | 28205 |
| 19 | Sumska | 49 | 8740356 | 815306 | 3574242 | 4275885 | 546353 | 2221341 | 1508191 | 74923 |
| 20 | Ternopilska | 63 | 9820011 | 1115926 | 4590725 | 5688360 | 743052 | 3224406 | 0 | 145902 |
| 21 | Vinnytska | 41 | 7052721 | 427253 | 3129199 | 3389662 | 537106 | 2642660 | 209896 | 106607 |
| 22 | Volynska | 57 | 9249633 | 709848 | 3803673 | 4736112 | 829261 | 3237123 | 669728 | 0 |
| 23 | Zakarpatska | 61 | 9481397 | 511575 | 4318152 | 4598719 | 1833820 | 2764899 | 0 | 52951 |
| 24 | Zaporizka | 53 | 7571870 | 407023 | 3554162 | 2922927 | 503852 | 2419075 | 0 | 687758 |
| 25 | Zhytomyrska | 46 | 6120385 | 337628 | 3002749 | 2780007 | 860196 | 1919811,5 | 0 | 0 |
|  | Total | 1303 | 196315827 | 14135578 | 91178737 | 87,408,317 | 25160773 | 57430421 | 5,757,657 | 2,605,574 |
|  | In % |  | 100 | 7,2% | 46,5% | 44,9% | 12,8% | 29,2% | 2,9% | 1,3% |

Annex – VI:

Beneficiaries of Community Projects by Micro-project Type, Since Inception

| # | Oblast | # Approved MPs | No of beneficaries |
| --- | --- | --- | --- |
|  |  |  | Total | Health | Energy saving | Water supply | Environ ment | School bus |
| 1 | ARC | 45 | 22997 | 4859 | 13791 | 2620 | 929 | 798 |
| 2 | Cherkaska | 54 | 55107 | 27585 | 23944 |  | 3578 |  |
| 3 | Chernihivska | 45 | 28044 | 11768 | 14324 | 1952 |  |  |
| 4 | Chernivetska | 50 | 39070 | 13736 | 22710 | 1822 |  | 802 |
| 5 | Dnipropetrovska | 55 | 42208 | 24172 | 14648 | 2998 |  | 390 |
| 6 | Donetska | 51 | 70229 | 17316 | 38262 | 10437 | 1332 | 2882 |
| 7 | Ivano-Frankivska | 69 | 85590 | 3151 | 80722 |  | 1717 |  |
| 8 | Kharkivska | 47 | 31168 | 3259 | 20444 | 3229 | 3241 | 995 |
| 9 | Khersonska | 54 | 62803 | 27323 | 28784 | 6696 |  |  |
| 10 | Khmelnytska | 50 | 22789 | 6284 | 12877 | 1482 |  | 2146 |
| 11 | Kirovohradska | 53 | 61600 | 4133 | 48926 | 4867 |  | 3674 |
| 12 | Kyivska | 55 | 37815 | 12784 | 20425 | 4606 |  |  |
| 13 | Luhanska | 55 | 40265 | 12355 | 20770 | 5946 |  | 1194 |
| 14 | Lvivska | 54 | 72840 | 10315 | 50877 | 4454 | 4160 | 3034 |
| 15 | Mykolaivska | 52 | 30615 | 597 | 21161 | 8076 |  | 781 |
| 16 | Odeska | 45 | 42849 | 19324 | 17309 | 6216 |  |  |
| 17 | Poltavska | 50 | 23217 | 2792 | 9411 | 6906 |  | 4108 |
| 18 | Rivnenska | 49 | 63951 | 22092 | 39713 |  | 350 | 1796 |
| 19 | Sumska | 49 | 30329 | 8303 | 10185 | 4061 | 6683 | 1097 |
| 20 | Ternopilska | 63 | 34243 | 7586 | 19665 | 2574 | 3146 | 1272 |
| 21 | Vinnytska | 41 | 38540 | 6103 | 19514 | 4422 |  | 8501 |
| 22 | Volynska | 57 | 36844 | 4280 | 30869 | 1042 |  | 653 |
| 23 | Zakarpatska | 61 | 143619 | 62375 | 72915 | 4572 | 3757 |  |
| 24 | Zaporizka | 53 | 59395 | 10701 | 27679 | 18408 |  | 2607 |
| 25 | Zhytomyrska | 46 | 31815 | 21319 | 9184 | 1312 |  |  |
|  | Total | 1303 | 1201638 | 343981 | 685121 | 106274 | 28893 | 36730 |
|  | In % |  |  | 29% | 57% | 9% | 2% | 3% |

Annex – VII:

Institutional Benefeciaries of Community Projects, Since Inception

| # | Oblast | # Approved MPs | No of beneficaries |
| --- | --- | --- | --- |
|  |  |  | Health | School/kindergarten | Community Territory |
| 1 | ARC | 45 | 6 | 30 | 9 |
| 2 | Cherkaska | 54 | 26 | 14 | 14 |
| 3 | Chernihivska | 45 | 12 | 18 | 15 |
| 4 | Chernivetska | 50 | 11 | 34 | 5 |
| 5 | Dnipropetrovska | 55 | 20 | 20 | 15 |
| 6 | Donetska | 51 | 9 | 27 | 15 |
| 7 | Ivano-Frankivska | 69 | 5 | 57 | 7 |
| 8 | Kharkivska | 47 | 3 | 29 | 15 |
| 9 | Khersonska | 54 | 13 | 32 | 9 |
| 10 | Khmelnytska | 50 | 8 | 33 | 9 |
| 11 | Kirovohradska | 53 | 2 | 38 | 13 |
| 12 | Kyivska | 55 | 13 | 27 | 15 |
| 13 | Luhanska | 55 | 13 | 25 | 17 |
| 14 | Lvivska | 54 | 13 | 23 | 18 |
| 15 | Mykolaivska | 52 | 1 | 32 | 19 |
| 16 | Odeska | 45 | 8 | 17 | 20 |
| 17 | Poltavska | 50 | 5 | 15 | 30 |
| 18 | Rivnenska | 49 | 17 | 28 | 4 |
| 19 | Sumska | 49 | 10 | 11 | 28 |
| 20 | Ternopilska | 63 | 13 | 41 | 9 |
| 21 | Vinnytska | 41 | 8 | 21 | 12 |
| 22 | Volynska | 57 | 7 | 38 | 12 |
| 23 | Zakarpatska | 61 | 18 | 22 | 21 |
| 24 | Zaporizka | 53 | 8 | 19 | 26 |
| 25 | Zhytomyrska | 46 | 26 | 8 | 12 |
|  | Total | 1303 | 275 | 659 | 369 |
|  | In % |  | 21% | 51% | 28% |

Annex – VIII:

Completed Micro-Projects in 1 Quarter 2011, and Since Inception

| SN | Oblast | Post-completion Action Taken |
| --- | --- | --- |
|  |  | Completed MPs (works done) | Public Audit | Handover | Operation and Maintance Fund |
| 1 | ARC | 1 | 1 | 1 | 14 |
| 2 | Cherkaska | 0 | 0 | 0 | 0 |
| 3 | Chernihivska | 13 | 8 | 21 | 4 |
| 4 | Chernivetska | 13 | 14 | 13 | 11 |
| 5 | Dnipropetrovska | 1 | 2 | 35 | 1 |
| 6 | Donetska | 0 | 0 | 0 | 0 |
| 7 | Ivano-Frankivska | 0 | 0 | 0 | 0 |
| 8 | Kharkivska | 7 | 12 | 11 | 15 |
| 9 | Khersonska | 0 | 0 | 0 | 0 |
| 10 | Khmelnytska | 0 | 0 | 0 | 8 |
| 11 | Kirovohradska | 0 | 0 | 0 | 0 |
| 12 | Kyivska | 1 | 0 | 0 | 0 |
| 13 | Luhanska | 0 | 0 | 0 | 4 |
| 14 | Lvivska | 0 | 23 | 23 | 12 |
| 15 | Mykolaivska | 0 | 0 | 0 | 6 |
| 16 | Odeska | 0 | 0 | 0 | 32 |
| 17 | Poltavska | 0 | 0 | 0 | 3 |
| 18 | Rivnenska | 3 | 7 | 5 | 0 |
| 19 | Sumska | 0 | 0 | 4 | 0 |
| 20 | Ternopilska | 0 | 0 | 15 | 31 |
| 21 | Vinnytska | 4 | 10 | 10 | 0 |
| 22 | Volynska | 0 | 14 | 0 | 0 |
| 23 | Zakarpatska | 0 | 0 | 0 | 0 |
| 24 | Zaporizka | 0 | 0 | 0 | 0 |
| 25 | Zhytomyrska | 5 | 6 | 5 | 0 |
|  | Total | 48 | 97 | 143 | 141 |
|  | Cummulative | 1303 | 1302 | 1299 | 928 |

Annex – IX:

Media Coverage in Different Types of Media in I Quarter 2011, and Since Inception

| # | Oblast | Total coverage | Newspapers | TV | Radio | Electronic Media | Partners’ web sites |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | ARC | 1 | 1 | 0 | 0 | 0 | 0 |
| 2 | Cherkaska | 16 | 11 | 0 | 2 | 3 | 3 |
| 3 | Chernihivska | 5 | 0 | 1 | 2 | 2 | 3 |
| 4 | Chernivetska | 3 | 3 | 0 | 0 | 0 | 0 |
| 5 | Dnipropetrovska | 15 | 9 | 3 | 2 | 1 | 0 |
| 6 | Donetska | 16 | 1 | 12 | 0 | 3 | 5 |
| 7 | Ivano-Frankivska | 59 | 11 | 12 | 10 | 26 | 9 |
| 8 | Kharkivska | 0 | 0 | 0 | 0 | 0 | 1 |
| 9 | Khersonska | 14 | 0 | 2 | 1 | 11 | 1 |
| 10 | Khmelnytska | 22 | 10 | 7 | 5 | 0 | 5 |
| 11 | Kirovohradska | 55 | 9 | 18 | 13 | 15 | 3 |
| 12 | Kyivska | 15 | 6 | 3 | 1 | 5 | 1 |
| 13 | Luhanska | 22 | 6 | 2 | 1 | 13 | 12 |
| 14 | Lvivska | 14 | 10 | 2 | 0 | 2 | 8 |
| 15 | Mykolaivska | 13 | 6 | 2 | 2 | 3 | 5 |
| 16 | Odeska | 6 | 5 | 0 | 0 | 1 | 1 |
| 17 | Poltavska | 50 | 15 | 1 | 32 | 2 | 15 |
| 18 | Rivnenska | 17 | 4 | 4 | 5 | 4 | 2 |
| 19 | Sumska | 8 | 1 | 0 | 7 | 0 | 0 |
| 20 | Ternopilska | 6 | 2 | 1 | 3 | 0 | 6 |
| 21 | Vinnytska | 5 | 4 | 1 | 0 | 0 | 4 |
| 22 | Volynska | 10 | 1 | 2 | 0 | 7 | 1 |
| 23 | Zakarpatska | 11 | 4 | 0 | 4 | 3 | 18 |
| 24 | Zaporizka | 2 | 2 | 0 | 0 | 0 | 4 |
| 25 | Zhytomyrska | 48 | 27 | 17 | 4 | 0 | 6 |
|  | Total | 433 | 148 | 90 | 94 | 101 | 113 |
|  | Cumulative | 3281 | 1428 | 612 | 536 | 705 | 902 |

*Total coverage includes Newspapers, TV, Radio, and Electronic media only

Annex - X:

Publication and Dissemination of Newsletters in I Quarter 2011 and Since Inception

| # | Oblast | Newsletters in 2010 |
| --- | --- | --- |
|  |  | No. of issues published | No. of copies printed & distributed | No. of copies sent electronically |
| 1 | ARC | 0 | 0 | 0 |
| 2 | Cherkaska | 1 | 40 | 60 |
| 3 | Chernihivska | 2 | 25 | 16 |
| 4 | Chernivetska | 0 | 0 | 0 |
| 5 | Dnipropetrovska | 0 | 0 | 0 |
| 6 | Donetska | 1 | 120 | 50 |
| 7 | Ivano-Frankivska | 0 | 0 | 0 |
| 8 | Kharkivska | 0 | 0 | 0 |
| 9 | Khersonska | 0 | 0 | 0 |
| 10 | Khmelnytska | 1 | 50 | 50 |
| 11 | Kirovohradska | 2 | 700 | 700 |
| 12 | Kyivska | 0 | 0 | 0 |
| 13 | Luhanska | 11 | 790 | 341 |
| 14 | Lvivska | 0 | 0 | 0 |
| 15 | Mykolaivska | 3 | 2240 | 275 |
| 16 | Odeska | 0 | 0 | 0 |
| 17 | Poltavska | 0 | 0 | 0 |
| 18 | Rivnenska | 3 | 45 | 58 |
| 19 | Sumska | 0 | 0 | 0 |
| 20 | Ternopilska | 0 | 0 | 0 |
| 21 | Vinnytska | 3 | 225 | 75 |
| 22 | Volynska | 0 | 0 | 0 |
| 23 | Zakarpatska | 1 | 480 | 480 |
| 24 | Zaporizka | 2 | 210 | 0 |
| 25 | Zhytomyrska | 3 | 900 | 40 |
|  | Total | 33 | 5825 | 2145 |
|  | Cummulative | 349 | 59847 | 17166 |

# Footnotes

Including 8 micro-projects where works were particially completed, excluding works to be done on local budget expence

Oblastwise details on selected VC/CC, number of formed COs are in Annex – I.

Including 8 micro-projects where milestones from CBA support were practically completed although works related with local budget was only partially doneand would be accomplished later upn availability of budget

One MP was terminated without public audit

Including 8 micro-projects where milestones from CBA support were practically completed although works related with local budget was only partially doneand would be accomplished later upn availability of budget

# Text boxes

LDF sitting in Kotelivskyi rayon, Poltavska oblast