Community-Based Approach to Local Development Project-II

ANNUAL NARRATIVE REPORT 2012 August - 2013 March Authority: Ms. Ricarda Rieger E-mail : Ricarda.rieger@undp.org Contact person : Ms. Yuliya Shcherbinina E-mail : yuliya.shcherbinina@undp.org Report Period : August 2012 – March 2013 Date of report : June 2013 Author of report : Jaysingh Sah E-mail jaysingh.sah@undp.org

| Project is financed by the European Union |  | Project is cofinanced and implemented by UNDP |
| --- | --- | --- |

CONTENTS

| Abbreviations and acronyms | 1 |
| --- | --- |
| Executive summary | 2 |
| Statistical abstract | 5 |
| Chapter 1 | Project Background | 7 |
| Chapter 2 | Establishing partnerships | 10 |
| Chapter 3 | Development of support structures | 13 |
| Chapter 4 | Capacity-building | 20 |
| Chapter 5 | Community projects | 23 |
| Chapter 6 | Methodology replication | 31 |
| Chapter 7 | Rural economic development | 34 |
| Chapter 8 | Energy efficiency | 38 |
| Chapter 9 | Knowledge management | 45 |
| Chapter 10 | Communications and visibility | 50 |
| Chapter 11 | Advisory and management | 54 |
| Annexure |  | 57 |

ABBREVIATIONS and ACRONYMS

| ARC | Autonomous Republic of Crimea |
| --- | --- |
| BSP | Bodies of Self-Organization of Population |
| CBA | Community-Based Approach to Local Development Project |
| CDO | Community Development Officer (CBA staff in the region) |
| CDP | Community Development Plan |
| CO | Community organization |
| CRP | Current reporting period – Aug 2012 – March 2013 |
| EE | Energy efficiency component of CBA-II |
| EU | European Union |
| KMH | Knowledge management hub |
| RED | Rural economic development |
| LDF | Local Development Forum |
| MoU | Memorandum of Understanding (similar to PA) |
| MPP | Micro-project proposal |
| MP | Micro-project (community project) |
| OC | Oblast Council |
| OCRC | Oblast Community Resource Centre (same as OIU) |
| OIU | Oblast Implementation Unit (same as OCRC) |
| OSA | Oblast State Administration |
| PA | Partnership Agreement (similar to MoU) |
| PMU | Project Management Unit (CBA head office in Kyiv) |
| PRP | Previous reporting period - June 2011 – July 2012 |
| RC | Rayon Council |
| RCC | Region Coordination Council |
| RCRC | Rayon Community Resource Centre |
| RSA | Rayon State Administration |
| UADRC | Ukrainian Association of District and Regional Authorities |
| UNDP | United Nations Development Programme |
| VC/CC | Village Council/City Council |

EXECUTIVE SUMMARY

Project Background

The second phase of the Community-Based Approach to Local Development (CBA-II) Project commenced with the signing of an agreement between the Government of Ukraine and the European Union (EU) on 31 May 2011. CBA-II is funded by the EU and co-financed and implemented by UNDP, with the support of the Government of Ukraine and in partnership with local executive bodies/bodies of self-governance. CBA-II aims to promote a community-based approach to strengthen the process of participatory governance, to promote the idea of sustainable development and to enhance energy efficiency at local level. The project’s total budget is €17 million, with a 98.4 percent contribution from the EU and 1.6 per cent cost-sharing from UNDP. The project’s time-frame is four years (June 2011 to May 2015).

To achieve the objectives, the project utilizes social mobilization tools to mobilize local communities and local authorities for joint decision-making, cost-sharing, implementation of community projects and establishment of sustainable mechanisms. Establishment/strengthening of the necessary support structures to this end include community organizations (COs), Local Development Forums (LDFs), Regional Coordination Councils (RCCs) and rayon/regional-level Community Resource Centres (CRCs). The capacity of stakeholders is enhanced through training, exposure visits etc. Community projects are used as another tool for capacity-building, with basic needs – namely, health, the environment, energy efficiency, water supply and rural economic development – considered priority areas.

The project is being implemented in all 25 regions of Ukraine. Its target is to cover 200 rayons, 900 Village/City Councils (VCs/CCs) with populations of less than 10,000 people and 900 local communities. Other targets include: 900 COs and 200 LDFs formed; 900 community projects supported; 16000 community members and 2000 state/elected officials trained; 17 cooperatives established; and a knowledge management hub established.

Brief Information on First Tranche

The focus of CBA-II during the first year of its implementation (June 2011 to July 2012) was to lay the foundations for the implementation of concrete project activities. The Project achieved all targets set forth for the first year in the area of partnership establishment, support structure development, training, micro-projects (standard), methodology replication and knowledge management. It lagged behind the target in the area of cooperative development and energy efficiency due long time needed to prepare necessary environment for implementation of these two components.

€ 3,057,596 was received as the first installment on 21/06/2011 for CBA-II implementation in first year. 101% of this amount was disbursed by 1 August 2012.

Project Implementation from Second Tranche

€ 6,427,593    was received on 20/11/2012 for project implementation during second year. By March 2013, 82.4% of this amount was disbursed.

Activities during 2nd year of implementation focused on micro-project, knowledge management, methodology replication and laying foundation for cooperative development and energy efficiency component. Details of project activities are given hereunder.

- Partnership: CBA-II was launched massively across the country to ensure adequate transparency about the project, the donor’s contribution, the modus operandi and so on. In total, 1277 launching seminars were conducted from local to national level. As a result, a partnership for project implementation was established with 24 oblast authorities and the Crimean government, 261 rayon authorities and 1080 VCs/CCs. With this, all targets related to partnerships were accomplished.

- Support structure development: Support structures are the institutional mechanism through which the project’s objectives are achieved. During the reporting period, 99 community organisations (COs) were formed/grafted with the participation of 121165 men and women representing 88379 households. To facilitate the bottom-up planning process and participatory decision-making at rayon level, 12 local development forums (LDFs) were formed or strengthened, and 2 regional coordination councils (RCCs) were ‘grafted’  from CBA-I at regional level. To support the function of LDFs and RCCs, 12 rayon community resource centres (CRCs) were created or grafted and strengthened. In total, 1031 COs were formed, 253 LDFs, 25 RCCs and 281 community resource centres were established since inception. Thus the target for support structure development was accomplished.

- Capacity-building: In a bid to enhance the skill of the human resources involved in CBA-II implementation, 5,411 CO-executives and 1,512 state/elected officials were trained during the reporting period. The necessary operational manuals and guidelines were developed or updated for use by project staff, state/elected officials and community members. The capacity of 80 resource centres was also enhanced through technical/logistical support. Since inception, 21,045 CO-executives and 6,452 local officials were trained and capacity of 98 resource centres was enhanced. Thus, target of capacity building was achieved in full.

- Community planning: During the reporting period, 151 COs prepared community development plans. Through a bottom-up planning process, 246 community priorities were mainstreamed into local government planning through joint decision-making at LDF meetings. Since inception, 1029 CDPs were developed and 966 of them were mainstreamed.

- Micro-projects (communal infrastructure): During the reporting period, 210 micro-project proposals were approved for funding with 756 micro-projects approved since inception. Thus, target of communal infrastructure type micro-project was fully achieved. The total cost of these micro-projects was UAH 128.4 million, which was shared by COs (7.8 percent), local authorities (50.2 percent), the CBA Project (40.4 percent) and private sponsors (1.6 percent). Because of strong networking, the project succeeded in mobilizing more resources from local partners than expected, with the result that the project’s share of funding was only 40.4 percent, instead of the 50 percent envisioned.

Sectoral analysis of micro-projects indicates that 81.2 percent of them are related to saving energy, 9.6 percent to health, 9.2 percent to water supply, and 0.5 percent to the environment. Furthermore, 70 percent of these micro-projects are related to schools or kindergartens, 15 percent to health facilities and 15 percent to the community – for example, street lighting, water supply, waste management. A total of 839,600 people are expected to benefit from these micro-projects.

- Knowledge management: Knowledge hub established during first reporting period was brought to function by building capacity of the knowledge hub management team, developing web portal, developing guidelines and training potential users. Partnership was established with 3 universities, making it total 23 since inception. 13 teaching/training institutions introduced the course into their curriculum. Students were supported with training, internship and small research projects on CBA-supported activities. Thus target of curriculum and knowledge management was reached.

- Methodology replication: During the reporting period, activities on methodology replication continued in 61 rayons with addition of 18 village councils, 71 COs, 12 LDFs and 7 community resource centres making it total 248 village councils, 193 COs, 53 LDFs and 56 CRCs since inception. Also since inception, a total of 2,935 CO-executives and 1,026 local officials were trained and 97 micro-projects were supported. Of these micro-projects, 82 belonged to standard type and 15 belonged to energy efficiency category. Total cost of these micro-projects was UAH 11.3 million that was shared among CO (7.2%), local budget (74.4%), CBA (16.8%) and private sponsors (1.6%).

- Rural economic development: CBA-II envisions support to small-scale economic initiatives of rural communities. The main focus is on promoting collective actions that could lead to income generation and employment creation in rural areas. The project is expected to assist low-income households to organize and form 17 cooperatives to bring added value to local products through efficient production, packaging and shared marketing.

During the reporting period 11 agricultural service cooperatives were formed in participation of 467 households. 154 coop-executives and 39 local authorities were trained. One of the cooperatives developed economic development plan. It is expected that by end of 2013 most of the targets related with economic component will be fulfilled.

- Energy efficiency: The overall objective of the EE component of CBA-II is to enhance local capacity by enabling citizens and local authorities to learn about energy efficiency technologies and use them jointly to solve their energy problems sustainably. The project envisions to achieve this objective through implementation of 300 micro-projects, updating of regional energy strategy and raising public awareness on energy efficiency. Implementation of the energy efficiency (EE) component in the reporting period was devoted to shaping the concept; testing and improving operational guidelines; training; and initiating micro-projects and updating of regional energy strategy in 6 selected pilot regions.

During the reporting period 145 micro-projects were supported (130 in regular rayons and 15 in replication rayons); updating of regional energy strategy was accomplished in 3 oblasts and preparation of awareness materials (leaflet, video film) was initiated. Major part of the targets is expected to be accomplished by 2013.

- Information and communication: In the reporting period, 128 media events were organized (including regional, rayon seminars, press conferences etc.), 946 cases of media coverage were registered, 673 publications on websites was registered and 87 issues of regional newsletters were disseminated. In addition, 2 donor visits and one exchange visit from Armenia were hosted during the reporting period.

    - Financial delivery: During the reporting period, a delivery of € 5.3 million was achieved making it € 8.4 million since inception. With this, the project achieved 48.5% of total financial target and 88.4% of first two tranches received from EU.

Implementation of CBA-II during its first year of operation has given rise to some valuable experience for consideration:

Opportunities

      - Regional and rayon authorities have started the trend of approving socio-economic programmes in favour of supporting community projects relevant for the CBA methodology;

      - Ongoing acceptance of the replication of the CBA methodology offers scope for this strategy to continue on a larger scale;

      - Energy efficiency projects are given high priority at local level and should continue;

      - The readiness of universities to teach courses on sustainable development and the CBA methodology could be tapped further in years to come.

Challenges

      - The government has introduced new rules regarding the construction/rehabilitation of communal infrastructure which slow down the implementation of micro-projects;

STATISTICAL ABSTRACT

| SN | Activity | Unit | Target All Years | Achievement |
| --- | --- | --- | --- | --- |
|  |  |  |  | PRP+ | CRP++ | Total |
| 1 | Partnership agreement signed with regions | Number | 25 | 25 | - | 25 |
| 2 | Rayons selected and partnership established | Number | 200 | 261 | - | 261 |
| 3 | Partnership with Village/City Councils | Number | 900 | 1066 | 14 | 1080 |
| 4 | Community organizations |  |  |  |  |  |
|  | COs formed | Number | 900 | 932 | 99 | 1031 |
|  | Household participation/membership |  |  |  |  |  |
|  | Target households | Number |  | 349,927 | 67,397 | 417,354 |
|  | Participated households | Number |  | 263,114 (75.2%) | 88379 | 346,180 (82.9%) |
|  | CO members (total) | Number |  | 404,465 | 121165 | 525,630 |
|  | CO members male (total) | Number |  | 42.7% | 42.5% | 42.9% |
|  | CO members female (total) | Number |  | 57.3% | 57.5% | 57.1% |
| 5 | Local Development Forums formed | Number | 200 | 241 | 12 | 253 |
|  | LDF sittings held |  | - | 655 | 473 | 1128 |
| 6 | Regional Coordination Councils grafted | Number | 25 | 23 | 2 | 25 |
|  | RCC sitting held |  | - | 31 | 30 | 61 |
| 7 | Community Resource Centres formed | Number | 233 | 269 | 12 | 281 |
|  | Capacity of CRCs strengthened | Number | 100 | 19 | 79 | 98 |
| 8 | Human resource development |  |  |  |  |  |
|  | Training conducted | Number | - | 1216 | 405 | 1621 |
|  | Participants of the trainings | Number | 18000 | 20,574 | 6,923 | 27497 |
|  | CO members | Number | 16000 | 15,634* | 5,411 | 21,045 |
|  | Local authorities | Number | 2000 | 4940* | 1512 | 6452 |
| 9 | Community development planning |  |  |  |  |  |
|  | COs with CDP prepared | Number | 900 | 880 | 151 | 1029 |
|  | CDP approved and mainstreamed | Number | 900 | 720 | 246 | 966 |
| 10 | Micro-project supported (regular) | Number | 600 | 546 | 210 | 756 |
|  | Energy saving | % | - | 82.8 | 77.8 | 81.2 |
|  | Water supply | % | - | 8.6 | 10.7 | 9.2 |
|  | Health posts | % | - | 8.4 | 10.9 | 9.6 |
|  | Environment | % | - | 0.2 | 0.6 | 0.5 |
|  | Total cost of approved micro-projects | UAH ml |  | 86.3 | 42.1 | 128.4 |
|  | Shared by COs | % | 5 | 7.7 | 7.9 | 7.8 |
|  | Shared by local, rayon, regional authorities | % | 45 | 48.5 | 53.5 | 50.2 |
|  | Shared by CBA | % | 50 | 42.1 | 37.3 | 40.4 |
|  | Shared by others (private sponsors) | % | 0 | 1.7 | 1.3 | 1.6 |
|  | Beneficiary characteristics |  |  |  |  |  |
|  | Beneficiary population | No. ‘000 | - | 539 | 300.6 | 839.6 |
|  | Institutional beneficiary | Number | - | 546 | 210 | 756 |
|  | School/kindergarten (cum.) | % | - | 72.2 | 69.7 | 69.8 |
|  | Health facility (cum.) | % | - | 9.4 | 15.1 | 15.1 |
|  | Local communities (cum.) | % | - | 18.4 | 15.2 | 15.1 |
| 12 | Energy efficiency component |  |  |  |  |  |
|  | Micro-project supported | Number | 300 | - | 145 | 145 |
|  | Energy efficiency strategic plans | Number | 6 | - | 3 | 3 |
|  | Technical design development | Number | 6 | - | - | - |
| 13 | Rural economic development component | Number |  |  |  |  |
|  | Cooperative developed | Number | 17 |  | 11 | 11 |
|  | Economic micro-projects supported | Number | 17 | - | - | - |
| 14 | Knowledge management |  |  |  |  |  |
|  | Partnership with academia | Number | 10 | 20 | 3 | 23 |
|  | Curriculum introduced in academia | Number | 2 | 1 | 12 | 13 |
|  | Knowledge hub established | Number | 1 | 1 | - | 1 |
| 15 | Information campaign and media strategy |  |  |  |  |  |
|  | Media events | Number | - | 325 | 128 | 453 |
|  | Media coverage | Number | - | 2669 | 946 | 3615 |
|  | Publications (websites) | Number | - | 1043 | 673 | 1716 |
|  | Newsletters | Number | - | 120 | 87 | 207 |
| 16 | Financial progress (estimated) | Mill. € | 17.1 | 3.1 | 5.3 | 8.4 |

* Includes approximately 50 percent repetition of participants

+ Previous reporting period

++ Current reporting period

chapter One

1.1	Context and commencement

The first phase of the Community-Based Approach to Local Development (CBA) project succeeded in scaling up the community-led approach to local development countrywide. It contributed to strengthening participatory governance, supported and developed local capacities for community-based development and facilitated a collaborative relationship between communities and local authorities. While some progress was achieved in terms of transparency, accountability and quality of public services, there remained room for further improvement and dissemination of the approach. Some problem areas that warranted urgent attention were:

- Growing poverty and unemployment among the rural population: Unemployment level in villages and small towns was approximately 27 percent (2009). Half of the entire rural population used their private gardens and household plots for subsistence. Challenges they face include small plot size, lack of financial assets, lack of mechanization, high unit costs for factor inputs (such as seeds, stock acquired in small quantities), lack of market access, and the exploitative nature of intermediaries, processors, wholesalers and retailers.

- Deteriorating living standards in rural areas, declining social infrastructure and reduced access to social services: In 2009, only 30 percent of households in rural areas had access to centralized water supply and sanitation; about 30 percent household had access to hot water supply; and 50 percent households had a gas supply. About one-third of heat-producing and heat-supply-related equipment and systems needed replacement because they were obsolete and extremely inefficient. Unfortunately, the revenue of local governments (small village and towns) remained highly constrained due to a lack of a taxation base and inadequate allocation of central budgets making the local authorities incapable of addressing the issues effectively.

- Inefficient use of energy: The amount of energy consumption of the average Ukrainian household is three to seven times higher than the average in Europe. One of the key reasons is that most of the equipment in use are obsolete. Since energy costs now constitute more than half of all residential service costs, any increase in energy prices will lead to a significant increase in the cost of providing these services.

- The central-level policy and legal frameworks do not provide clear mandates, resources or division of responsibilities for local governments in the area of public service delivery: Local governments have only a limited ability to determine spending structure and reallocate expenditures within sectors; local civil servants lack capacities in designing local development strategies, planning allocation of resources and reporting to local communities; and there is a lack of a clear mechanism to engage civil society/community members in local decision-making processes.

Considering the above, the Government of Ukraine and the European Union (EU) decided to extend the duration of the CBA Project by four years. On 31 May 2012 an agreement was signed to this end between European Union and the Government of Ukraine.

The second phase of the CBA Project (CBA-II) is funded by the EU and is co-financed and implemented by UNDP, with the support of the Government of Ukraine and in partnership with local executive bodies/bodies of self-governance. The project’s total budget is €17.125 million (US$23.3 million), with a 98.4 percent contribution from the EU and 1.6 percent cost-sharing from UNDP. The project’s time-frame is four years (7 June 2012 to May 2015).

1.2	Objectives

The overall objective of the CBA Project is to promote sustainable socio-economic development at local level by strengthening participatory governance and encouraging community-based initiatives throughout Ukraine.

Specific objectives of the project:

- To promote a community-based approach to local governance and sustainable development by:

  - strengthening the capacity of local communities, local authorities and universities in applying community-led development;

  - integrating participatory mechanisms for local planning and public service delivery into the day-to-day practices of local governments;

  - supporting community-based initiatives for sustainable rehabilitation, management and operation of basic social and communal infrastructure; and

  - promoting small business development in rural areas.

- To enhance energy efficiency at local level by:

  - building the capacity of local communities and local authorities in energy planning and efficient energy use;

  - supporting innovative community initiatives in efficient energy use; and

  - raising public awareness on energy efficiency based on grassroots-level best practices.

- To support the creation of the locally owned and managed repository and network of good practices and knowledge on community mobilization and participatory governance by:

  - documenting and codifying lessons learned and institutional arrangements established during implementation of CBA;

  - establishing a network of knowledge hubs for the creation, analysis and sharing of innovative approaches to community-based development; and

  - supporting academia and other educational institutions in curriculum and capacity development for promoting community-based approaches to local governance and development.

The project will support community-led activities in the following priority areas: health (local health posts), the environment, water supply, rural economic development and energy efficiency.

1.3	Target results

The following results were envisaged for CBA-II:

| SN | Results | Target All |
| --- | --- | --- |
| 1 | Community organizations created/strengthened | 900 |
| 2 | Local Development Forums created/strengthened | 200 |
| 3 | Regional Coordination Councils created/strengthened | 25 |
| 4 | Capacity of Community Resource Centres strengthened | 200 |
| 5 | Curricula developed by universities/training institutions | 2 |
| 6 | Community members trained in CBA methodology | 6000 |
| 7 | Elected/state authorities trained in CBA methodology | 2000 |
| 8 | Micro-projects implemented for improved service delivery | 600 |
| 9 | Community members trained in energy efficiency | 10,000 |
| 10 | Community projects on efficient use of energy implemented | 300 |
| 11 | Knowledge management hub established | 1 |
| 12 | Cooperatives developed for rural economic development | 17 |

1.4	Implementation strategy

The strategic goal of the CBA Project is to build the capacity of local communities and local authorities to participate in joint decision-making processes and to use this capacity for multi-stakeholder cooperation and multisectoral interventions with ensured local ownership of the process. The process is bottom-up and involves stakeholders from grassroots, meso and macro level in the process as it moves upward. The CBA implementation process involves a series of activities and action points that ultimately yield the project’s intended results (Annex II).

At the national level the project works with line ministries, parliamentary committees, national associations of local councils and other counterparts under overall coordination of the Secretariat of the Cabinet of Ministers (SCMU) of Ukraine. At the regional level, the project cooperates with Oblast State Administrations (OSAs) and Oblast Councils (OCs) (in case of the Autonomous Republic of Crimea (ARC), with the ARC Council of Ministers and Verkhovna Rada of the ARC). At rayon level, CBA partners with Rayon State Administrations (RSAs) and Rayon Councils (RCs). At the local level, partnership is established with village/city councils (VCs/CCs).

Selected rayons, VCs/CCs and local communities form the functional area of the project. Their selection is done through open competition based on the level of socio-economic hardship, especially in the area of health, water supply, energy supply and the environment. Through the selection process, CBA reaches the areas/populations of the region/rayon that are suffering most.

Local-level CBA activities are carried out under the framework of partnership with the stakeholders. This is based on the willingness and commitment of the partners (communities, VCs/CCs, rayon authorities, regional authorities, academia, associations of local self-government, the private sector) for cost-sharing and joint decision-making.

The project uses a social mobilization tool to mobilize stakeholders and create the environment (support structures) for joint decision-making and joint implementation of activities. Community organizations (COs) are formed by the representation of 80 percent or more of the households in the selected community, to reflect a common community vision and implement community priorities. Local development forums (LDFs) are developed at rayon level for joint decision-making, resource mobilization and local coordination. Regional Coordination Councils (RCC) are developed at regional (oblast/ARC) level to monitor CBA activities in the region, to resolve issues related to local policies/procedures, to support programming and for resource mobilization. At the national level there is a steering committee to ensure national-level coordination and advisory support.

Capacity of the COs is built so that they are able to make joint decisions with local authorities, mobilize resources, implement local priorities and sustain the results. Capacity of the partners (VC/CC, rayon/oblast etc.) is strengthened in terms of human resources to implement the participatory approach promoted by the project. Training, exposure visits, dialogues and small grants (for community projects), appropriate institutional mechanisms etc. are used as tools for building capacity.

Knowledge and experience acquired in the course of implementation will be gathered, analysed and disseminated through a knowledge hub in cooperation with academia and the association of local self-government bodies.

1.5	Project management

The project is managed by UNDP Ukraine under overall guidance of the Country Director and under direct supervision of a Senior Programme Manager. The project is executed by an implementation team with a central body in Kyiv and 25 regional implementation units, one in each region. Oblast Implementation Units (Regional Community Resource Centres, RCRCs) are further supported by oblast authorities in terms of office premises and human resources. Similarly, each rayon partner has deputed one official for coordination and implementation and has established a modest type of district Community Resource Centre (CRC). Together they implement the local component of CBA activities. LDFs and RCCs serve as a guiding body at local and regional level, and the project’s steering committee serves as a guiding body at the national level. The CBA management structure is given in Annex III.

Appropriate management and information systems (MIS) are established to make the stakeholders directly involved in the process of monitoring and assessment of the project activities. They include process, input, output and impact monitoring. The flow of information is bottom-up and participatory.

Various media outlets are encouraged to raise public awareness about CBA activities, to ensure transparency.

Chapter Two

Over the reporting period the project achieved targets by forging partnership with 25 regional authorities, 261 rayon authorities and 1080 VC/CCs in total since inception. Details of the process are given below.

Establishing formal partnerships with local/regional authorities is essential to formalize the role and commitment of the partners and to provide an official basis to work with COs. The project’s targets include partnerships with 25 regional authorities, 200 rayon authorities and 900 VC/CCs.

2.1 Partnership with Regional Authorities

Establishing of partnership with regional authorities was completed in 2011 thereby reaching 100% of the target. Memorandums of Understanding (MoU) were signed with all 25 regional authorities. In general the MoUs were tripartite involving regional state administration, regional council and UNDP. Details on establishing partnership are available at: http://cba.org.ua/ua/activities/partners.

2.2 Establishing partnership with rayon authorities

Partnerships were established with 261 rayon authorities (against the target of 200) by first quarter of 2012. Of these, 200 were regular interventions and 61 were for replication. Also, 128 of them took part in CBA-I, while 133 joined CBA for the first time. A list of the selected rayons by region is available on the CBA website: http://cba.org.ua/en/partners

2.3 	Establishing partnerships with Village/City Councils

Establishing partnerships with VCs/CCs comprised five steps: (a) competition announcement; (b) ranking of VCs/CCs; (c) selection of VCs/CCs; (d) holding VC/CC-level CBA-II launch seminar; and (e) signing of MoU. By the reporting period, target of establishing partnerships with VCs/CCs was fully achieved. Details of the different steps of the process are given below:

- Competition announcement: The competition for participation of VCs/CCs in CBA-II was announced in each rayon seminar along with competition criteria that included (a) level of problems with basic infrastructure and services with regard to CBA-II priorities; (b) level of socio-economic hardship; (c) willingness to cooperate in and support participatory planning and resource mobilization for micro-projects; (d) satisfactory performance during CBA-I (for CBA-I pilot VCs/CCs only). The participants were supplied with application forms and guidelines.

- Selection of VCs/CCs for partnership: Following the competition announcement during the rayon seminars, interested VCs/CCs sent an application for participation in the competition. A total of 3441 applications were received. They were analysed in light of the above-mentioned criteria and ranked for each rayon. A selection committee comprising of a CBA community development officer in the region, a rayon focal person and headed by a regional focal person reviewed the ranking list and selected the top four VCs/CCs for each rayon, with up to 25 percent in reserve. In total, 832 VCs/CCs were selected for partnership, with 382 VCs/CCs in reserve, for regular partnership, and 248 VCs/CCs were selected for partnership for replication, with 96 VCs/CCs in reserve.

In total since inception, 1080 VCs/CCs were selected of which 832 were regular and 248 were replication category. Also, 19 percent came from CBA-I and 21 percent were new (see Table 1). For the purpose of transparency, the results of the selection were publically announced in each rayon by the rayon authorities.

Of the selected VCs/CCs, 87.7 percent belonged to the category of village council, 8.2 percent were town council/urban-type villages, and 4.1 percent were city councils.

Table 1. Selection of VCs/CCs for Partnership

| SN | Activity | Previous reporting | Current reporting | Sub-total | Total |
| --- | --- | --- | --- | --- | --- |
|  |  | Regular | Replication | Regular | Replication | Regular | Replication |  |
| 1 | Application received | 2807 | 262 | 0 | 372 | 2807 | 634 | 3441 |
| 2 | Selected for partnership | 836 | 230 | -4 | 18 | 832 | 248 | 1080 |
|  | Old (CBA-I) VC/CC | 158 | 43 | 2 | 2 | 160 | 45 | 205 |
|  | New VC/CC | 678 | 187 | -6 | 16 | 672 | 203 | 875 |
| 3 | Selected for reserve | 382 | 96 | 0 | 0 | 382 | 96 | 478 |

* Details by region are in Annexes – I & Annex –II. Negative data indicates termination of partnership

- Establishing partnerships with VCs/CCs: After the selection of partner VCs/CCs, seminars were conducted in each of them with the participation of the VC/CC head, focal person (and other officials) from the rayon, focal person (and other officials) from the region, local NGOs, local businesses, representatives of local social infrastructures (e.g. schools, kindergartens, health facilities etc.) and interested active people of the community.

During the seminar, details about the effectiveness of CBA-I at local level were shared, often with the help of a film, leaflets and case studies. The process of CBA-II implementation and community selection and the terms of the partnership with VCs/CCs and beneficiary communities were explained. In reporting period, 75 VC/CC seminars (2 regular and 73 replication) were conducted. An average of 32 people participated in each village seminar.

Table 2. Participation in CBA launch seminars in VCs/CCs

| Purpose of seminar | # of VC/CC Seminars | Participants |
| --- | --- | --- |
|  |  | Oblast Authorities | RSA/RC heads/ deputy heads | Other RSA/RC officials | VC/CC heads | NGO | Media | Others | Total |
| PRP | 1052 | 210 | 974 | 1999 | 1031 | 11,056 | 370 | 17,128 | 32,768 |
| CRP | 33 | 3 | 49 | 107 | 57 | 333 | 11 | 1203 | 1763 |
| Total | 1085 | 213 | 1023 | 2103 | 1088 | 11389 | 381 | 18331 | 34531 |

Usually, VC/CC heads signed the MoU in the course of the seminar or at a later date. In the reporting period, 73 MoUs were signed with VCs/CCs (1 regular and 72 replication).

“In contemporary world, representatives of local authority are aware that one community is not able to solve local problems of their territory. Therefore, local authority is looking for partners and support of active communities. Cooperation is the key factor of successful community”. N.M. Skrypchenko, Head of Tomakivska rayona rada, Dnipropetrovska oblast “During the first phase of CBA Project, Terebovliansky rayon was one of the most successful in the region, and despite the fact that today we cooperate through replication modality, we will continue to strongly support every initiative of our communities. The most important is not the amount of allocated funds. Important is the focus on the problems of people”. Mykhayliuk Dmytro Vasylyovych, First Deputy Head Terebovliansky Rayon State Administration (replication rayon

2.4 	Experience

As such, no major problems were faced that might hinder the progress of CBA-II during the partnership development process. Nonetheless, passivity was observed among a few partner rayons, village/city councils and communities. It resulted in termination of partnership and substitution from the reserve list. Lack of local budget for cost sharing was the main reason of passivity followed by change in the vision of the leaderships.

Box - 1: Mykolaivska Oblast Extends Efficient Partnership Using CBA Methodology Both Mykolaivska oblast communities and authorities have gained a substantial experience of cooperation with the CBA-II project. Up to the end of 2012, 34 micro-projects were completed benefiting more than 37`000 population in the rural communities of Mykolaivska oblast. The transparent and clear system of monitoring of the micro-projects implementation and accountability for each Hryvna spent have played the main role in growing confidence to the CBA methodology. Positive results are reflected in oblast reports on the budget fulfillment. Often high-level oblast officials take part in the CBA activities, monitor quality of implementation and resolve operational issues. Oleksandr Smyrnov, the Head of the Permanent Commission of Deputies on Planning, Вudget and Investments at the Oblast Council, is the focal point and a liaison between the authorities and the CBA project. He regularly informs the Head of the Mykolaivska OSA about reports on the phased implementation of the micro-projects. This allows the senior officials of the oblast to be aware about CBA’s methodology and use it as the basis for enhancing cooperation with village councils and communities. Mykolaivska Oblast Council has approved the decision on support of the local communities’ initiatives through the oblast development programme. The idea of co-financing of the community initiatives has been communicated from the Oblast Council to all rural communities. Moreover, according to the educational plan of the Council, representatives of CBA explain the CBA-methodology and share experience on its application at the annual training courses on professional upgrading of 320 heads of village councils of Mykolaivska Oblast. The detailed information about the CBA Project progress is available to the residents of the oblast via internet; the oblast council puts the reference to the Project website on its web portal. Due to the press and media, the residents of the most remote locations promptly know about possibilities of using the co-financing mechanism for solving local problems. Mykolaivska oblast is one of some 15 oblasts of Ukraine where oblast authorities provide financing for micro-project and small grant competitions of rural communities, using the CBA project methodology.

Chapter Three

Over the reporting period, 99 community organizations were formed, 12 Local Development Forums were created, 2 Regional Coordination Councils were grafted, and 269 Community Resource Centres were established. With this, the project achieved 100 percent of its target results.

Establishing support structures is one of the important elements of the community-based development approach methodology. Appropriate support structures are developed for participatory decision-making and monitoring at all levels of project implementation. Target of key support structures include 900 COs at local level, 261 LDFs and CRCs at rayon level, 25 RCCs and 23 CRCs at regional level.

3.1 	Development of community organizations

COs are the foundation block for the community-based approach. They enable community members to unleash their potential through collective action. They also help to make governance at local level more participatory. Development of COs involves (a) selection of pilot communities; (b) assisting the community members to get organized into a CO; and (c) getting the CO formalized. Details of these steps are given below:

- Selection of pilot community: Following a VC/CC-level seminar, a community selection committee comprising of the VC/CC head, CBA staff and headed by a rayon focal person selected the community to be supported in the VC/CC. The selection was based on key criteria including (a) level of problems with basic infrastructure and services with regard to CBA-II priorities facing the community; (b) willingness of the community to undertake joint decision-making and actions to solve their problems on a collective and self-help basis; and performance during CBA-I (if appropriate).

During the reporting period, 45 communities were selected for partnership. In total, 1085 communities were selected since inception (Table-3). Of those, 18 percent had participated in CBA-I, and 82 percent were ‘new’ communities. This participation by a large number of new communities ensures that the CBA methodology has succeeded in reaching further in society.

Table 3. Selection of pilot communities

| SN | Activity | Previous reporting | Current reporting | Sub-total | Total |
| --- | --- | --- | --- | --- | --- |
|  |  | Regular | Replication | Regular | Replication | Regular | Replication |  |
| 1 | Selected for partnership | 834 | 206 | 3 | 42 | 837 | 248 | 1085 |
|  | Old (CBA-I) | 151 | 41 | 3 | 3 | 154 | 44 | 198 (18%) |
|  | New | 683 | 165 | 0 | 39 | 683 | 204 | 887 (82%) |
| 2 | Selected for reserve | 690 | 42 | 0 | 57 | 690 | 99 | 789 |

* Details by region are in Annexes - I & Annex - II

- Formation of COs: Following the community selection, dialogues were held between the selected communities and the community mobilization team. During the first dialogue, the community members were introduced to the CBA principles and methodology and were motivated to improve their living conditions by following the participatory approach recommended by the project. The communities which accepted the principles of collective action were encouraged to form COs. Each CO elected an executive body (CO management team, COMT), consisting of five members (head, treasurer, secretary and active members).

Dialogue with local community (Menchykury village, Sumska oblast)

The existing COs (from CBA-I or otherwise) went through a special assessment before being accepted for CBA-II. It was done in participation of CO-members to measure strengths and weaknesses of the CO and its activities.  The CO was required to make the necessary improvements to become eligible for CBA-II, if the level of quality was low.

During the reporting period, 99 COs were created or grafted  with the participation of 121,165 men and women from 88,379households. In total 1031 COs were formed/grafted in participation of 346,180 households which represented 82.9% percent of the entire households in the communities.

Table 4. Formation of community organizations

| SN | Activity | Previous reporting | Current reporting | Sub-total | Total |
| --- | --- | --- | --- | --- | --- |
|  |  | Regular | Replication | Regular | Replication | Regular | Replication |  |
| 1 | No. of COs formed/grafted | 810 | 122 | 28 | 71 | 838 | 193 | 1031 |
| 2 | Household participation |  |  |  |  |  |  |  |
|  | Target households | 305,076 | 44,851 | 52,239 | 15,158 | 357345 | 60,009 | 417,354 |
|  | Participated households | 245,338 (80.4%) | 17,776 (39.6%) | 52,074 (99.7%) | 30,992 - | 297,412 (83.2%) | 48,768 (81.2%) | 346,180 (82.9%) |
| 3 | Membership | 382,338 | 22,127 | 76,442 | 44,723 | 458,780 | 66,850 | 525,630 |
|  | Male | 43% | 42.8% | 42.6% | 43.2% | 44.5% | 42.4% | 42.9% |
|  | Female | 57% | 57.2% | 57.4% | 56.8% | 55.5% | 57.6% | 57.1% |

* Details by region are in Annexes – I & Annex - II

c)	Formalization of COs: The newly formed COs enrolled with their respective VC/CC and went through legal registration with the relevant agencies. The status of a legal entity is essential for the COs to carry out business formally and to open a bank account for financial transactions. This status also makes them eligible to receive grants from national or international agencies.

During the reporting period, 104 COs enrolled with VCs/CCs, and 134 COs received the necessary legal status (see Table 5).

Table 5. Legal forms of COs

| SN | Activity | Previous reporting | Current reporting | Sub-total | Total |
| --- | --- | --- | --- | --- | --- |
|  |  | Regular | Replication | Regular | Replication | Regular | Replication |  |
| 1 | Enrolled with VC/CC | 809 | 114 | 29 | 75 | 838 | 189 | 1027 |
| 2 | Legally registered | 799 | 91 | 39 | 95 | 838 | 186 | 1024 |
|  | ACMB | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Public organization | 762 | 91 | 29 | 88 | 791 | 179 | 970 |
|  | BSP | 28 | 0 | 10 | 0 | 38 | 0 | 38 |
|  | Cooperatives | 4 | 0 | 0 | 0 | 4 | 0 | 4 |
|  | Other | 5 | 0 | 0 | 7 | 5 | 7 | 12 |

Most COs choose public organization as their legal form. Each legal form has its own specific characteristics and is suitable in a particular context. For example, the legal status of public organization is relatively open to mobilizing resources from various donors but has limitations in accepting communal property on its balance sheet. Bodies of Self-Organization of Population (BSPs) function somewhat under the control of the local authorities, and a cooperative has several benefits of administrative and financial rights, as it can make a profit, own assets and distribute dividends among its members. An association of co-owners of multi-storey buildings (ACMB )is appropriate for multi-storey buildings where one building represents one community. It has financial autonomy to undertake income and expenditures and accept communal property on its balance sheet.

Box – 2: Opinions on Co-operation with CBA Project “Such projects contribute to the development of self-consciousness of citizens. If a person himself contributes something in the development and improvement of his village then his attitude changes". Yefim Fix, Executive secretary of the Center of legislative initiatives of the ARC Parliament “We have been waiting for a long time for this project in our area; we held ourselves meetings and registered organization. We received much information from those rayons which first started their work in 2008, we went to Gornostaivka to get acquainted with their experience. Then we received a possibility to try ourselves. What has started here! In our village, such activity was even surprising - the general meeting on defining of priority issues and later - on contractor`s selection had been lasting for more than 3 hours! Each person proved his opinion, everyone wanted to speak. All questions had to be put to a vote - so different were the thoughts! Neither me, nor the village head have observed such situation for many years”. Artishchev Volodymyr Ananiyovych, the Head of CO “Promin Mayaka”, v. Chervonyi Mayak, Beryslavsky rayon, Kherson region “Participation in the project has opened our eyes to the fact that we do not just live in the same village but we also are the part of the community which power is in unity”. I. P. Stroya, the Head of CO “Rozvytok sela Dolynske”, Reniysky rayon, Odesa region “Thanks to participation in CBA-II our community appeared to be able to mobilize and organize itself. Community members became more organized, and united, we understood that we are able to solve prioritized problems if we work hard and in cooperation with our partners”. O.O. Harkavenko,Deputy Head of Kotelivska rayon council, Poltavskyi region “Before we were usual suppliants, and constantly asked our local authorities for something. After successful implementation micro-projects on energy saving in secondary school and village health post, our community organization became welcome visitor in village and rayon council and rayon administration” B.Lobach, Head of CO ‘Tzvitnenski horyzonty’, Kirovohrad region “CO ‘Konstantinovka’ is quite a successful community organization which implemented already three micro-projects beyond CBA Project. We renovated bus stop in our village, purchased new edgings for the road at the beginning of the village, whitewashed trees in the village and put flowerbeds into order. However, the main achievement of our community is getting successful experience of independent work and confidence in our own forces”. I.Tyshkina, Head of CO ‘Konstantinovka’, Konstantinovka village, Simpheropolskyi rayon, ARC ‘I can say that we did a lot. We participated in trainings; learned, technical manual became the main book for our community organization. We did a lot of mistakes, of course, and started again. We learned how to conduct tenders, prepare financial reports, and control quality of work. It was really difficult, but it was worth it!’ S. Bevzenko, activist of CO ‘Yednist’, Vinnytska region

3.2 	Local Development Forums

LDFs are created at rayon level and are expected to facilitate dialogue, coordination, planning and decision-making at local level between the oblast and rayon authorities and communities for promoting community-driven local development. Usually LDFs consist of RSA and RC heads, heads of VCs/CCs, chiefs of relevant departments in RSAs/RCs, representatives (focal person) of oblast authorities, and heads of COs formed within CBA.

In the case of CBA-I (old) rayons, existing LDFs were re-initiated (grafted) by adjusting the composition of members, while in the case of new rayons, new LDFs were created under the leadership of the RSA/RC head.

During the reporting period, 12 LDFs were formed or grafted making it total 253 since inception (Table 6). It reflects 97% of the target achieved. All the regular rayons established LDF by previous reporting period and 3% remaining target lies with the replication rayons which started their activities about six to nine months later than the regular rayons.

Table 6. Formation and grafting of LDFs

| SN | Activity | Previous reporting | Current reporting | Sub-total | Total |
| --- | --- | --- | --- | --- | --- |
|  |  | Regular | Replication | Regular | Replication | Regular | Replication |  |
| 1 | LDF formed/grafted | 200 | 41 | 0 | 12 | 200 | 53 | 253 |
|  | From CBA-I | 100 | 22 | 0 | 1 | 100 | 23 | 123 |
|  | New | 100 | 19 | 0 | 11 | 100 | 30 | 130 |
| 2 | No. of sittings | 599 | 56 | 363 | 110 | 962 | 166 | 1128 |

* Details by region are in Annexes – I & Annex - II

Meetings were held regularly to discuss local development issues such as mainstreaming of community plans, mobilizing resources for implementation of community projects, providing guidance and technical backstopping to the COs during community project implementation etc.

| LDF meeting in Kostyantynivskyi rayon (replication), Donetska oblast | LDF meeting in Trostyanetsky rayon (Sumska oblast) |
| --- | --- |

Box – 3: Opinions of Authorities About Local Development Forums “This project allows us to solve problems of the social sphere and helps our communities to become more proactive. Therefore, all rayon departments / services should work most efficiently and provide full support to the communities in implementation of their initiatives”. Yaroslav Stets, Head of Chortkivsky RSA, during LDF meeting ‘Starting from the first sitting of LDF in Novopskovskyi rayon activists of CO ‘Sukha Plotyna’ felt their significance. At the beginning rayon authority planned to replace old windows in Novorozsoshnska village school. However, at general community meeting it was decided that it is more important to make ceiling warmer, and to change heating system in the school. We were surprised when head of rayon administration supported our idea, and helped us a lot.’ O.Kotova, Head of CO ‘Sukha Plotyna’, Novorozsosh village, Novoprosvskyi rayon, Luhanska region. ‘Sittings of LDF are very important in order to support community initiatives. Those ideas that were discussed and approved at LDF sitting are usually included into program of economic and social development of rayon, with allocation of finance resources from local budget. Besides, we try to invite private entrepreneurs for partnership.’ V. Volchenko, Head of Department of Economy, Hadyatsk rayon state administration, Poltava region "Village communities, at their meetings, must independently choose a problem they want to have solved with the help of our project and with our help, dear village heads. I am asking all representatives of local authorities not to interfere with the communities in making their decision". Leonid Zabela, Chairperson of Yemilchyne RSA in Zhytomyrska Oblast "Recently our rayon established a Local Development Forum. We carefully prepared for its first session. Leaders of public organizations defended their micro projects, asked questions to line divisions of rayon state administration seeking to receive answers and support. The attending leaders of COs and village heads also shared their experiences and reported on their work. Problem issues were resolved in the course of the meeting, co-financing for each of the four projects was planned. It did not matter that the LDF met for the first time, it is more important that it was effective». Olena Kuzmenko, focal point, Head of Finance Department at the Kirovohrad RSA, Kirovohrad Oblast “Financial support provided by an international project in the crisis times, is doubtlessly important. Local communities do not have a lot of their own money, the rayons here are subsidized. However, the most important thing is that community participation is noticeable here." Vladimir Klychnikov, Member of the ARC Supreme Council, during a LDF meeting in Nyzhniogirsky rayon. “At first I did not see a great need to hold the meetings of the Forum; I considered that everything could be solved on a routine basis by addressing to each individual specialist. And I recommended the heads of our village councils doing in such way. However, as the time passed, I realized that I was losing control on the situation when the requirements were changing, new legislation acts were approved, when events occurred that could have negative consequences and that would be difficult to eliminate if you did not interfere directly at the start. It is necessary to discuss this experience, we should gather together and looking at each other`s eyes talk about problems and achievements”. Vitaliy Oleksandrovych Yarmak, the Head of Novovorontsovsky RSA, Kherson region

3.3 	Regional Coordination Councils

RCCs are created at regional level with the aim of coordinating and facilitating financing for micro-projects. They serve to disseminate information about the project among officials, monitor the project’s activities in the region and provide consultations on strategic issues of implementing micro-projects. RCCs are chaired by the deputy head of the Oblast State Administration (OSA) or Oblast Council (OC) and consist of representatives of the rayon administration/council heads, appropriate OSA/OC departments, selected VC/CC heads, COs, NGOs and the private sector.

During the reporting period, 3 RCCs were formed making it total since inception. They held 30 sittings during the reporting period with 61 in total. Most of the sittings held during the reporting period focused on:

- Review of the progress of micro-projects’ implementation;

- Involvement of relevant departments into acceleration of MPP approval and implementation;

- Organization of CBA methodology replication;

- Participation in the energy efficiency and rural economic development components.

3.4 	Community Resource Centres

To facilitate the functioning of LDFs and RCCs, community resource centres (CRCs) are established by the partner rayon authorities and regional authorities, which provide premises and depute a focal person. CBA provides logistical facilities as necessary and trains the focal persons. CRCs are important in that they support non-CBA communities in carrying out local development activities in line with the CBA methodology – something considered valuable from the perspective of methodology replication.

During reporting period 10 rayon level CRCs were established making it total 256 since inception. With this, the target was achieved to the level of 128 percent. In case of regional level CRCs, the target was achieved during previous reporting period itself.

| In addition to providing information about the CBA Project, rayon resource centres display information about other donors’ initiatives | Example of an information board in a rayon community resource centre |
| --- | --- |

Table 7. Creation of Community Resource Centres

|  | Level of CRC | Previous reporting | Current reporting | Total |
| --- | --- | --- | --- | --- |
| 1 | Regional CRC | 23 | 2 | 25 |
| 2 | Rayon CRC - regular | 197 | 3 | 200 |
| 3 | Rayon CRC - replication | 49 | 7 | 56 |
|  | Total | 269 | 12 | 281 |

* Details by region are in Annex – I & Annex - II

Box – 4: Best Practice of RCRC: Bashtansky Rayon Community Resource Centre In the 1st phase of CBA Project, Bashtansky rayon of Mykolaivska oblast was not selected to become pilot. Nevertheless, the idea of mobilizing communities for cooperation with local government sounded very interesting to the authorities. Therefore they decided to closely follow the process of CBA implementation and try to replicate it. Thus, employees of rayon administration participated in CBA trainings and learned about CBA methodology. They formed 19 COs and established LDF in late 2010. With a view of enhancing cooperation with organized communities and attract more donors’ funding, a RCRC (official title - investment department) was created. It was staffed with 4 employees and UAH 110000 was allocated to equip it. According to Ivan Rubskyi, Head of Bashtanska RSA, in 2 years such investment has paid off with UAH 2 mln of investments for social projects. Training at Bashtanka RCRC, Mykolaivska oblast In 2011, Bashtanskyi rayon was selected to become pilot of CBA-II. Advanced position of Bashtansky RCRC distinguishes itself among other pilot rayons of CBA, and was presented as a model of establishing and running a resource centre during training of representatives from 61 replication rayons, held in March-April 2012. Such an excellent example of RCRC would not be possible without visionary, strategic and action oriented leadership.

Box – 5: Shumsky Rayon Community Resource Center, Ternopilska oblast Shumsky rayon council took decision on 10 January, 2012 to establish the RCRC in the framework of CBA implementation in the rayon for the period 2012-2014. It allocated office premises and a budget of UAH 5000 for purchasing a computer, a scanner, a printer and a copier. Since then, the RCRC has been actively supporting implementation of CBA activities in the rayon and promotion of CBA methodology in non-CBA communities. It has carried out substantial amount of information dissemination through various means including newsletter, official websites and Facebook: Facebook: http://www.facebook.com/SumskijRajonnijResursnijCentrGromad, Official website of the Ternopilska OSA: http://www.oda.te.gov.ua/shumska/ua/2622.htm Official website of Shumsky RSA: http://www.shumsk.org.ua/xabitat/xabitat.html Newspaper “The News of Shumsky rayon” 5 articles (3 on front page) about communities activities The Coordinator of Shumsky Resource Center has effectively managed regular and replication COs and supported them in planning, micro-project proposal preparation and implementation. Besides CBA, the RCRC coordinates implementation of UN-Habitat program.

Box – 6: Oblast Centre for Regional and Local Development Created in Cherkaska Oblast Considering the fact that the terms and conditions in the MoU between UNDP and Cherkaska OSA for implementation of CBA, stipulates sustainability of the project, the oblast administration experts decided to look into the matter. Upon studying specifics of CBA/OIU activities as a community resource centre, conclusion was made that the OIU should continue to work as Oblast Community Resource Centre after completion of CBA-II Project. A decision was taken at the board meeting of the Oblast State Administration to extend the scope of OIU to cover all the rayons in the region. Respective. Accordingly, Oblast Centre for Regional and Local Development was established as a part of the administration’s structure. A staff of the foreign relations department of the OSA was deputed as head of the Centre, who manages activities of the Centre. Within support of the Centre, two rayons received grant assistance from the "Kusanone" Programme of the Japanese Embassy in Ukraine; several communities received grants from the state fund for local self-government support. Many village councils that were not included in the CBA Project started to create and manage community organisations. The number of projects developed by community initiatives and submitted for contest-based funding to various charitable foundations and programmes, increased. The Centre launched a course of lectures in "Community-Based Local Development" for village heads within the framework of qualification upgrading programme for staff members of bodies of local self-government. Together with CBA/CDO, officials of the Centre manages implementation of CBA component on replication of CBA methodology in 4 rayons of Cherkaska Oblast. Experts at the Centre. OSA leadership highly evaluated the Centre’s achievements and provided separate premises for it. Also, decision was taken to employ a specialist to be in charge of implementation of the replication component, and also to create a powerful information and methodical advisory Centre for the rayons. On 16 – 17 January 2012, Cherkaska OSA undertook monitoring visit to all the 9 RCRCs in the oblast. The specially created commission was composed of representatives of oblast state administration, oblast council, CBA regional coordinators and independent experts. Effectiveness of RCRCs was assessed in the light of (a) institutional capacity, (b) efficiency of work, (c) communication activities, (d) activities beyond cooperation with CBA. According to the mission’s conclusions, RCRC of Zvenihorodskyi rayon was found to be the best followed by RCRCs of Smilyanskyi and Shpolyanskyi rayons.

Box – 7: Opinions About Rayon Community Resource Centres “Certainly Milovsky Resource Center headed by Svitlana Kozhokar was necessary to coordinate the work of all communities living on the territory of Milovsky rayon. This was the first authority where we applied for help. Svitlana Oleksandrivna, despite the large amount of work, always helped us to find the right solution. During our work with the Resource Centre there was no single denial of consultation and assistance in the preparation of documents and solving problems. “ L. M. Kyslytsyna, the secretary of CO “Maybutnie Milovschyny”, Luhanska region “Oleksandrivsky rayon resource centers provide us help to find new partners for the implementation of our initiatives. From the resource centre we have a possibility to get acquainted with the experience of communities not only of our rayon, but also of other rayons and the whole Ukraine.” V. Oleksiyenko, the treasurer of CO, Kirovohrad region “The rayon community resource center has helped greatly to our communities in implementation of micro-projects. Also, if I have an idea related to the implementation of community initiatives, then I go to the rayon community resource center. The rayon authorities are interested in projects and programs and will help to find a competent department or a person who is responsible for solving of such questions. The rayon community resource center helps to establish such cooperation.” B. Boychuk, the Head of Debeslavtsivsky village council, Ivano-Frankivsk region “The community resource centre of Artemivsk rayon organizes workshops, seminars, trainings for COs, initiative groups, and representatives of the local councils on planning, coordination, implementation and monitoring of the COs’ activities at the rayon level. It also provides consulting services to the local communities for the establishment and operation of community organisation and implementation of social initiatives and provides ties with the donor organisations and foundations.” Maryna Yuhno, Head of economic department of Artemivsky rayon state administration, Donetska oblast Due to the work of RCRC the activists of the COs have the opportunity to participate in the competitions or micro-projects, get acquainted with the documentation and legislation that regulate the work of the third sector. The main objective is dissemination of experience and good practices.” Vitaly Kuruch, head of economic department of Bolgradsk rayon state administration, Odeska oblast

Chapter Four

By March 2013, 21,045 representatives of COs and 6,452 officials from state/elected authorities were trained by the Project. Logistic capacity of 98 resource centres was enhanced. Thus target of training and capacity buiding was achieved.

Capacity-building involves such activities as training, exposure visits and other techniques used to enhance skills or transfer knowledge. The purpose is to enable local communities, local authorities and other partners to adopt and practice CBA methodology. To this end, the Project aims to train 16,000 representatives of COs and 2,000 officials from state/elected authorities and build capacity of 100  community resource centres. The following capacity-building activities were carried out during the reporting period:

4.1 	Preparation of training materials

During the reporting period, manuals on energy efficiency component and on rural economic development were developed, field-tested, finalized, published and distributed among partners and stakeholders. Also, a video film on cooperative development was prepared, field-tested, finalised and disseminated to pilot regions. Financial manual for COs (developed in 2011) went through field-test, finalization and publication.  Besides, accounting manual and business planning manual were prepared for cooperatives and sent for publication. Also, posters were prepared, published and disseminated for mass awareness on principles and methodology of CBA.

Manuals on energy efficiency, financial management and RED

4.2	Training for CO-executives and representatives of rayon/regional authorities

In the reporting period, 405 trainings were conducted in 24 oblasts and the ARC for 5,411 CO executives and 1512 representatives of local authorities. The training included such areas as CO management, accounting, planning, micro-project preparation and implementation, participatory assessment and public audit. Since inception, 21,045 CO-executives and 6452 representatives of local governments were trained through 1621 trainings held since 2011 (Table - 8)

Table 8. Trainings organized

| SN | Activity | Previous reporting | Current reporting | Sub-total | Total |
| --- | --- | --- | --- | --- | --- |
|  |  | Regular | Replication | Regular | Replication | Regular | Replication |  |
| 1 | No. of training held | 1107 | 109 | 251 | 154 | 1358 | 263 | 1621 |
| 2 | CO-executives trained | 14490 | 1144 | 3620 | 1791 | 18110 | 2935 | 21045 |
| 3 | Officials of local/regional authorities trained | 4439 | 501 | 987 | 525 | 5426 | 1026 | 6452 |

* Details by region are in Annex – I and Annex - II		** including repetition

4.3	Trainings for CBA staffs and state/elected officials on special components

Following trainings were organized during July 2012 – March 2013 for CBA/PMU for CBA staffs and local authorities:

- Trainings on energy efficiency component

Training was held in Kyiv on 12-14 July for 6 CDOs and 6 representatives of OSAs/OCs (coordinators of energy efficiency component in their regions). Similarly, training on energy efficiency was conducted in Cherkassy on 11 December 2012 and in Khmelnitsky on 17 December 2012 respectively. Details on training are available in Chapter - VIII

- Trainings on rural economic development component

Training was organized on how to implement rural economic development in the framework of CBA-II during 10-12 July 2012 in Kyiv. Seven representatives of OSA/OC coordinating RED component participated in this training along with 7 CDOs from the respective regions. Upon the training, the participants initiated RED activity in their regions.  A follow up training was held during 17-18 December 2012 in Kyiv for the same set of participants to train them in subsequent round of implementation activities. Details on training are available in Chapter- VII

- Cluster training on methodology replication

In 2012, four cluster trainings were organized for over 75 focal persons from oblasts and rayons selected for partnership with CBA within its replication component. Training agenda included the overview of theoretical and practical aspects of social mobilization, micro-project cycle, monitoring and evaluation and instruments of public relations. Participants also learnt about the mechanisms of joint planning and the role of each of the structures created for this purpose: LDF and RCC. Each training included a visit to community, allowing focal persons to meet with organizations that already have accomplished several projects and witness their results. Visits to exemplary Rayon community resource centres demonstrated best practices of RCRC work, and inspired each rayon focal person to create  a vision of his/her future RCRC.

- Cluster training financial management of CO

On 19-22 August 2012, last cluster training on financial management of CO was organized in Lviv for 17 CO representatives, coordinators of rayon community resource centres and CDOs of Lvivska, Rivnenska, Volynska, Khmelnytska and Ternopilska oblasts. Objective of the training was:

- to eliminate major issues of finance management for CO economic activity on yearly basis through analysis of registration documents, statements of financial and tax reports, income & expenditures budgeting with data on MPP implementation.

- to clarify and eliminate weak points and recurrent failures within tranches reports on MPP implementation.

- to strengthen potential cooperation between COs and representatives of RCRC / authorities;

Besides theoretical part and question-answer session, practical work was organized in the field: the group visited CO “Novy obriy” and studied their financial management and documentation.

- Equipping community resource centres for effectiveness

In a bid to enhance capacity of resource centres, CBA Project provided such grant support as equipment (e.g. computer, printer, camera, projector, copier etc.), furniture (book shelves, chairs, tables etc.), visibility items (e.g. screen, display board, flags etc.) and minor repair of the premises. In case of rayon resource centres, the support was provided on competition basis while for regional resource centres, the support was provided on case by case basis.

All regional authorities were informed in June 2012 to participate in the competition for enhancing capacity of rayon resource centres in their regions. Key criteria of competition included:

# Availability of premises for CRC

# Availability of delegated staff to manage the resource centre

# Provision of logistic support to the resource centre by the rayon authority

# No. of communities in the rayon that implemented micro-projects

# Resource center conduct trainings on projects implementation

# Provision of technical, financial, administrative support by the rayon authority to communities

This support was available for both regular as well replication rayons but not for those rayons which received this award in 2010 (i.e. during first phase of CBA). All regions participated in the competition. In total, 180 rayon authorities applied for support. Among them 73 received the award (Table - 9) worth up to $1,000 equivalent. They utilised the support by March 2013 equal to UAH 580,678 ($ 72,584) with an average of UAH 7,954. In general, a region received award between 2-5 resource centres (Annex - III). Besides, all 25 regional resource centres received capacity enhancement support over 2011-12 period totaling UAH 402,155 ($ 50,271) with an average of UAH 16,086 ($ 2,011).

By March 2013, focal persons of 261 CRCs were trained; visibility support was provided to all CRCs and 98 CRCs received equipment and logistic support. Thus, the target of building capacity of 200 CRCs was achieved.

Table 9. Resource centre support *

|  | Regular | Replication | Total |
| --- | --- | --- | --- |
| Total rayons | 200 | 61 | 261 |
| Rayon participated in competition | 140 | 40 | 180 |
| Rayon won the competition | 63 | 10 | 73 |
| Total amount of rayon award (UAH) |  |  | 580,678 |
| Support to regional CRCs (UAH) |  |  | 402,155 |

* Region-wise details in Annex –  III

| Example of information board in rayon community resource centre | Working placed equipped in Svalyavskyi rayon community resource centre, Zakarpatska oblast |
| --- | --- |

Box – 8: Creative Training Activities Creative workshops in Donetska Oblast "CBA II Creative Workshops” was launched in 2012 by Donetsk Oblast Implementation Unit for representatives of communities. Main aim of this initiative was to ‘hear, share and adopt’ positive practical experience on local development from the source: demonstration CO, demonstration village and demonstration rayon community resource centres. In selecting participants for the workshop, main criteria were willingness and ability to implement the gained knowledge in their community. Specific objective of the Workshop was: To keep abreast of innovations occurring in communities in the course of the CBA-II implementation To train communities and rayons to analyse, generalize, disseminate and present their best practices To create a network of Donetsk oblast communities and rural RCRCs on Facebook In the frame of "CBA II Creative Workshops” three round of workshops and practical seminars was held during 2012. The seminar participants reviewed criteria of RCRC quality work in CBA II Project, conditions of RCRC competition, analysed intermediate results of project implementation in main and replication rayons in Donetska oblast, budget cost sharing issues, EE and RED components peculiarities. Useful recommendations were received as a result of the Workshops. It is planned to continue the “Creative Workshop” in 2013 as well.

Box – 9: Opinions of Training Participants "We especially appreciate project’s training sessions, which presented complex issues in a simple, accessible and understandable way for every village resident." Vadym Gorpynych, Head of the CO "Zubkivchany" in the village of Zubkovychi, Olevsk rayon, Zhytomyrska Oblast. "I am grateful for invitation to the first training on CO management for representatives of the Rayon Department of Justice and the state registrar - it considerably accelerated some of our actions on registration of public organizations." Yuri Prokopets - village head of the Sinhurivka village, council Zhytomyrska rayon "The most important thing for us is those skills and knowledge that enable us to work together in the future, to unite people around different issues ...." A.D. Kryzhanovska, head of the "Oberig Katerynky" CO, Mykolaivska oblast

Chapter Five

From July 2012 to March 2013, 210 micro-projects were approved for funding, making it 756 in total since inception. It marked 100 percent of the target achievement.

To support the improvement of living conditions in rural areas, strengthening participatory governance and enhancing energy efficiency, CBA supports the implementation of community ‘micro-projects’ through small grants based on equity, feasibility, sustainability and cost-sharing criteria. The following key sub-activities took place in regard to achieving 600 standard type micro-project target:

Key steps required to accomplish implementation of community projects include community planning, mainstreaming of plans, approval of micro-project proposal, implementation of micro-project, and sustainability of resulting object. Details of each step are given hereunder.

5.1 	Community planning and mainstreaming of plans

After creating a CO, community members prioritize the problems of their village they want to solve. Through training, CO members are familiarized with the need for and process of participatory planning and the bottom-up planning process. The CO members identify their development needs, set priorities and prepare a conceptual proposal called a community development plan (CDP). When it is approved by the VC/CC, it is submitted to the LDF for review and approval. CDPs from various communities are discussed at the LDF meeting, and the most appropriate plans are approved along with recommendations for an allocation from the rayon budget.

During the reporting period, 151 COs defined priorities in their CDPs making it 1029 since inception. Of total CDPs, 1017 CDPs were approved at VC/CC level, and 966 of them were approved at LDF sittings.

Table 10. Community Development Plans*

| SN | Details | Unit | Previous reporting | Current reporting | Sub-total | Total |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Regular | Replication | Regular | Replication | Regular | Replication |  |
| 1 | CDPs prepared/grafted | No. | 809 | 71 | 27 | 124 | 836 | 195 | 1029 |
| 2 | Sectoral distribution of priorities |  |  |  |  |  |  |  |  |
|  | Energy | % | 75.3% | n.a. | 76.0% | 80.4% | 76.3% | 77.0% | 75.3% |
|  | Water supply | % | 12% | n.a. | 8.0% | 3.9% | 10.6% | 8.4% | 12% |
|  | Health | % | 11.8% | n.a. | 16.0% | 15.6% | 12.3% | 13.1% | 11.8% |
|  | Environment | % | 0.9% | n.a. | 0% | 0.1% | 0.7% | 1.6% | 0.9% |
| 3 | CDPs approved at VC/CC level | No. | 787 | 63 | 40 | 125 | 827 | 188 | 1017 |
| 4 | CDPs approved at LDF level | No. | 671 | 49 | 141 | 105 | 812 | 154 | 966 |

* Details by region are in Annex – I & annex - II

The majority of problems prioritized for cooperation with the CBA Project are devoted to energy saving (replacing windows and doors, replacing or repairing heating systems, street lighting etc.), followed by energy efficiency and renewable energy technology, water supply (repairing or renovating water supply systems) and health care (repair of health facilities, purchasing medical equipment etc.).

CO members established the priority for their plans based on such criteria as intensity of need (80 percent or more of households considered it the highest priority), feasibility (the micro-project is simple enough to be implemented within the capacity of the CO members), resource availability (willingness of donors, community members and local authorities to support the priority), and sustainability (the beneficiary community should be able to sustain the object/services created under the project).

Box – 10: Opinions of Authorities About Cooperation With CBA “Due to participation in the CBA Project, level of people`s trust to local authorities has increased". Volodymyr Rudenko, the Head of Krasnoarmiyska rayon state administration, Donetsk region "The advantage of this project is that the community coordinates and defines the priority areas of the project implementation for improvement of the socio-cultural conditions of the territory." Oleksandr Krynytskyi, the Head of Dolynska rayon state administration, Ivano-Frankivsk region "Participation in such projects is important for the rayon as it significantly reduces the load of the district budget and successfully resolves important social problems of the rayon." Volodymyr Lutskyi, the Head of Dolynska rayon council, Ivano-Frankivsk region

5.2		Approval of micro-project proposals

Preparation of micro-project proposal, Rivnenska oblast

During the reporting period, 210 micro-project proposals submitted by COs were appraised and approved for funding by CBA making it total 674 micro-projects since inception.

A typical proposal includes a set of documents such as technical documentation, cost estimates with proposed cost-sharing, a letter of commitment from stakeholders, protocols of decisions made at various times, the CO’s statute, bank account details, micro-project proposal, the result of a participatory assessment and/or maturity index, sustainability mechanisms etc.

Table 11. Implementation of micro-projects

| SN | Activity | Previous reporting | Current reporting | Sub-total | Total |
| --- | --- | --- | --- | --- | --- |
|  |  | Regular | Replication | Regular | Replication | Regular | Replication |  |
| 1 | Micro-project proposals approved for funding | 546 | 0 | 128 | 82 | 674 | 82 | 756 |
| 2 | Micro-projects completed (works done) | 51 | 0 | 489 | 19 | 530 | 19 | 549 |

* Details by region are in Annex – IV A, B

The total cost of the approved micro-projects was UAH 128 million, which was shared by partners as presented in Table – 12. CBA contribution was 42.3% in regular rayons and 16.9% in replication rayons. In replication rayons contribution from local budget was 74.2%, which indicate bigger ownership of the local authorities to CBA methodology.

Table 12. Sharing of micro-project costs

| SN | Cost sharing entity | Previous reporting | Current reporting | Sub-total | Total |
| --- | --- | --- | --- | --- | --- |
|  |  | Regular | Replication | Regular | Replication | Regular | Replication |  |
| 1 | Total cost (UAH million) | 86.3 | 0 | 32.6 | 9.5 | 118.9 | 9.5 | 128.4 |
| 2 | Cost distribution (%) |  |  |  |  |  |  |  |
| a | Community organization | 7.7 | 0 | 8.0 | 7.5 | 7.8 | 7.5 | 7.8 |
| b | Village/city councils | 12.2 | 0 | 10.9 | 18.3 | 12.0 | 18.3 | 12.5 |
| c | Rayon authority | 32.9 | 0 | 35.8 | 45.6 | 33.4 | 45.6 | 34.3 |
| d | Oblast authority | 3.4 | 0 | 0.8 | 10.3 | 2.9 | 10.3 | 3.4 |
| e | CBA Project | 42.1 | 0 | 43.2 | 16.9 | 42.3 | 16.9 | 40.4 |
| f | Private sector | 1.7 | 0 | 1.3 | 1.4 | 1.6 | 1.4 | 1.6 |

* Details by region are in Annex – IV A, B

Sectoral distribution of the approved micro-projects is as follows:

Table 13. Sectoral distribution of approved micro-projects (percent)

| SN | Cost sharing entity | Previous reporting | Current reporting | Sub-total | Total |
| --- | --- | --- | --- | --- | --- |
|  |  | Regular | Replication | Regular | Replication | Regular | Replication |  |
| 1 | Energy saving | 82.8 | 0 | 76.4 | 77.6 | 81.6 | 77.6 | 81.2 |
| 2 | Water supply | 8.6 | 0 | 10.6 | 4.5 | 9.0 | 4.5 | 8.4 |
| 3 | Health | 8.4 | 0 | 12.3 | 13.4 | 9.1 | 13.4 | 9.5 |
| 4 | Environment | 0.2 | 0 | 0.7 | 4.5 | 0.3 | 4.5 | 0.9 |

* Details by region are in Annex – IV A, B

The approved projects are expected to benefit more than 839,600 people with female participation higher in the benefit. In terms of institutional beneficiaries, the distribution of 674 approved micro-projects shows school/kindergartens were the biggest beneficiaries of the micro-projects (Table – 14).

Table 14. Beneficiaries of micro-project

| SN | Cost sharing entity | Previous reporting | Current reporting | Sub-total | Total |
| --- | --- | --- | --- | --- | --- |
|  |  | Regular | Replication | Regular | Replication | Regular | Replication |  |
| 1 | Beneficiary population (‘000) | 539 | 0 | 209 | 91.6 | 748 | 91.6 | 839.6 |
| a | Male (%) | 54.4 | 0 | 46.5 | 46.0 | 45.9 | 46.0 | 45.9 |
| b | Female (%) | 45.6 | 0 | 53.5 | 54.0 | 54.1 | 54.0 | 54.1 |
| 2 | Institutional beneficiaries | 546 | 0 | 128 | 82 | 674 | 82 | 756 |
| 3 | School/kindergarten (%) | 72.2 | 0 | 64.1 | 68.2 | 69.9 | 68.2 | 69.8 |
| 4 | Healthpost (%) | 9.4 | 0 | 33.8 | 15.9 | 15.0 | 15.9 | 15.1 |
|  | Local communities (%) | 18.4 | 0 | 2.1 | 15.9 | 15.1 | 15.9 | 15.1 |

* Details by region are in Annex – IV A, B

Benefits includes –

- Warm and cozy classrooms for children (i.e. improved learning environment,

- Better living condition through improved health service, quality water supply and better sewerage/waste disposal;

- Average saving of UAH 19,888 per year/micro-project is expected to take place through increased energy efficiency and/or reduced energy consumption;

- Employment generation due to the investment made through micro-projects;

- Communities learn skill of planning and undertaking initiatives in a sustainable manner;

- Improved relationship between people and local authorities;

- Process of participatory governance, transparency and accountability strengthened.

Box – 11: Significant Gain From Energy Saving and Energy Efficiency A random sample of 250 energy saving/efficiency MPPs was reviewed in light of amount saved through increased energy efficiency and/or reduced energy consumption. Analysis of ‘saving amount’ estimated by the COs in their MPPs showed that in an average UAH 19,888 is saved per micro-project per heating season. Considering 606 energy micro-projects (77.8% of 779 micro-projects) approved by CBA as of 2012, a total saving of UAH 12 million can be expected per season. This saving may be considered as a strong incentive to invest in energy sector. A brief analysis of the saving data is as follows: SN No. of MP Range of Saving Av. Saving 1 8 70000 - 145000 94245 2 5 60000 - 70000 64589 3 7 50000 - 60000 56087 4 18 40000 - 50000 44204 6 20 30000 - 40000 35394 7 30 20000 - 30000 25488 8 44 10000 - 20000 14474 9 118 500 - 10000 4951 Total 250 4,972,037 19,888

Problems and solutions

The procedure of MPP preparation took longer than expected. This is related to the changes introduced in Ukrainian legislation. According to Article 31 of the Law ‘On regulation of city construction’ and the Regulation #560 of the Cabinet of Ministers’ (dated 11.05.2012) on expertise of construction projects, projects related to construction of new buildings, repair and renovation should undergo a special expertise. The time frame of the expertise of project documentation is up to 30 days, and the expertise its budget/cost estimate of the project – up to 15 days. If amendments are recommended to the project proposal, it should undergo another round of expertise. The time frame of the second expertise might take up to 15 days. Therefore, in case if micro-project proposals had to undergo several rounds of expertise, the process was often delayed.

Furthermore, budgetary constraint occurred due to national election and it caused delay in initiation and implementation of micro-project since the local authorities found it difficult to commit/provide resources under cost sharing arrangement.

Two main factors influenced successful solution to the problem:

- Strong support from local/regional authorities;

- Effective role of LDFs and RCCs where the issue was discussed and solutions sought. Relevant departments were instructed by the leadership to facilitate the MP-approval process. Representatives of state committee on architecture and building were invited to RCC sittings where they got full information about the Project and adopted simplified procedures and document requirements for processing of proposals submitted by COs.

5.3	Implementation of micro-projects

Signing of grant agreement with CO takes place in transparent environment in ARC

All the micro-projects approved were put into the process of funding/implementation, which includes signing a grant agreement between the CO and UNDP and releasing the first tranche of funds into the beneficiary CO’s bank account. Signing the grant agreement at CO’s general meeting develops a strong sense of ownership and accountability among the CO members regarding the resource utilization and timely completion of the work.

Training on micro-project implementation (Lvivska)

Following the release of the first tranche of funding, the CO starts the process of necessary preparation for implementation. It forms a functional group which also serves as a tender committee. Training is provided to each functional group on how to implement micro-project with due diligence to ensure intended quantity and quality of results. They are familiarised with key steps of implementation such as tendering, selection of contractor, financial management and reporting, supervision system, public auditing, commissioning and handover and sustainability of results. The trainings is provided in pieces in line with the stage of implementation.

Accordingly, the CO announces a tender to select a contractor. The best bid is chosen by the CO, and a contract is signed for implementation of the micro-project. As the implementation proceeds, a quality supervision committee monitors the work from time to time. When the work, reporting and verification are completed, the total grant amount is released in three tranches.

Tender opening in Akimovka village, ARC (left) and Ptycha community organization, Rivnenska oblast

Box – 12: Opinions About Quality Supervision Committee “In my opinion, the quality supervision committees are very effective because they make it possible to achieve high-quality results and efficient usage of resources”. V. B. Melnychenko, the Head of Architecture Department of the Balta rayon state administration, Odesa region “It is essential that there is a quality supervision committee. This is one more control on the quality of the project implementation, financial flows and their usage. The community believed in themselves, in their capabilities. The level of trust in each other and to the government authorities has been increased”. Bogdan Vasylyovych Bilyi, CO functional group member, Ivano-Frankivsk region “The activities of the Quality Supervision Committee enable the community to be sure that all works on the project implementation will be executed efficiently. Because the work of the contractor is evaluated by the experts”. Roman Kos, the Head of regional development and construction department of the Dolynsky RSA, Ivano-Frankivsk region “The Quality Supervision Committee, in my opinion, is very necessary because the communities are not competent in all aspects concerning the construction, and the committee consists of experts from the rayon state administration and can control the accuracy of performance and compliance with all standards and provide technical assistance to the community “. Zoriana Orlovska, the Head of the economic department of the Galytsky RSA, Ivano-Frankivsk region

Problems and solutions

Nature of micro-projects vary from technically simple to complex. Implementation requires multi-stakeholder coordination and cost-sharing from multi-agencies, which operate in the institutional/financial environment of their own. Thus, the MP implementation posed several challenges such as -

- Tender process of some COs was temporarily affected by lack of adequate bidder and conflict during tender finalization, thus, leading to such action as cancellation (and re-announcement) of tender; review of tender results and even black-listing of the bidder;

- COs are expected to follow UNDP-financial procedures (for the grant money) while national financial procedures ought to be followed in case of budget money. A series of training and backstopping was arranged from CBA to build skill of the COs;

- New legislation introduced from January 2012, required that only licensed contractors would be eligible to undertake construction. It affected all the micro projects that aimed to carry out construction.  Without license, a contractor would not be allowed to work on construction even if he/she won the bid. There was a severe scarcity of licensed contractors in the regions. Many of the existing contractors applied for license but found that the pace of issuing license from relevant agency was very slow.

- Due to lack of adequate license holder contractors, small number of contractors won several bids within and outside their region. They started work in several sites simultaneously with their own (small) capital and with first tranche released from CBA. But as their capital exhausted the work stopped or got delayed. These contractors did not dare to undertake more activities than they were really paid for in advance. It specially affected the part of the micro-project that belonged to budget responsibility. Due to financial constraint, budget money remained blocked for large part of the year for development purpose.

5.4 	Post-completion activities

The issue of sustainability of the object created or repaired through the micro-project was ensured at the outset by getting the COs and relevant local authorities to reach mutual agreement on jointly carrying out operation and maintenance. All of the 756 micro-projects approved until March 2013 had a sustainability arrangement built-in. By March 2013, 549 micro-projects had been completed, 493 of which were publicly audited and 405 handed over to the relevant department.

Table 15. Post-completion of micro-projects

| SN | Activity | Previous reporting | Current reporting | Sub-total | Total |
| --- | --- | --- | --- | --- | --- |
|  |  | Regular | Replication | Regular | Replication | Regular | Replication |  |
| 1 | Public audit conducted | 44 | 0 | 435 | 14 | 479 | 14 | 493 |
| 2 | O&M funds established | 482 | 0 | 192 | 82 | 674 | 82 | 756 |
| 3 | Handover completed | 25 | 0 | 364 | 16 | 389 | 16 | 405 |

* Details by region are in Annex - IV A, B

| CO of Korniivka village (Zaporizka oblast) completed their micro-project on energy saving in local school | Children in a local kindergarten - upon replacement of old windows with new ones |
| --- | --- |

Box – 13: Opinions About Public Audit “We had been carrying out public audit for the second time. What conclusions have I made? The community where people from the very beginning gathered together for the meetings, listened to their suggestions and informed about each step – never would have problems with public audit! And all actions of the organization would be evaluated as “excellent”!” L. V. Pavliuchenkova, the Head of Velykoblagovischensky village council, Kherson region “At first we were surprised when at the next general meeting of our CO we were asked to analyze and evaluate the implementation and completion of the micro-project because before villagers never had been involved into such actions. And then during the process of public audit we felt responsible for every small mistake, but this did not minimize our optimism in future initiatives.” T. Koroliuk, the member of CO “Zorya”, v. Gvizdiv, Koretsky rayon, Rivnenska region “During the public audit there is an additional opportunity to provide to all participants and community members honest and transparent information about the usage of funds - because this issue is always problematic, and people should be assured that every kopeck had been spent with benefits.” O. Demidova, the Head of CO “Dobrobut”, Mykolaivska region “When we carried out public audit in the community for the first time we thought that it was some necessary formality, but when public audit became the normal practice we were surprised by the results ourselves how the teamwork brought people together and the adherence to principles in the assessment helped to solve current problems.” S. M. Zaluzhna, the Secretary of CO “Neptun”, Poltava region “Due to the public audit the work on the project becomes publicized. During the audit the community sees if rationally have been used involved finances, both from the community or the Program side”. Yulia Zharonkina, the treasurer of Luhanska CO “Luhan”, Artemivsky rayon, Donetsk region

Problems and solutions

Public audit: Getting clearance from dozens of departments and making a handover is a time taking tasks. Linking commissioning event with public audit is found to be helpful when department authorities could see the results and clear the documents with confidence.

Maintenance fund: COs try various options to actualize the idea of maintenance fund. Despite appreciation from local authorities, lack of policy and procedures make adoption of this idea difficult. COs have no motivation to hold adequate size of maintenance fund due to problem of reporting to tax authorities and due to risk of getting the fund used for some unintended purpose. Experience sharing, lobbying and advocacy is required to make this important idea adopted widely and consistently.

Box – 14: Micro-projects as a Way of Problem Solution Micro-project brings solution to health problem According to the results of the survey of inhabitants of v. Verba (Dubensky rayon) it was found that the most important problem was the problem of bad quality of drinking water: for decades inhabitants of v. Verba had been drinking water from harmful asbestos pipes. Two 24-apartment houses, Verbsky hospital, boarding school, kindergarten and 3 streets Verba were connected to the water supply system. This created a threat to people's lives, and most important - to lives of children. The community united and the work started: gathering documents micro-project proposal, selection of contractors, research for sources of co-financing. Villagers looked in horror on dismantled asbestos pipes ... Here it was - the reason of the increased number of gastrointestinal, blood diseases and tumors ... Transparent activities of CO gave the possibility to save much money according to the results of the organized tender – additionally the control station was equipped by the deep pump with frequency converter. Today the work on the micro project has been completed. Nearly 1,000 residents receive safe drinking water; food in the kindergarten and children's boarding school no longer threatens the health of babies and kids. To some extent, the solution of one of the burning problems of the community reduced social tension in the village and returned the confidence in the power of every single member of the community which is united by a joint work. Community enjoys sigh of relief in mining area Problem with water supply is a common situation for the territories that are close to oil fields and gas deposits. The effect of output is a low level of water in wells and contamination with harmful substances. The central water supply system in the village Zasullia was built almost 30 years ago. And it was connected only to three streets. All other villagers were using water from wells that besides contamination in hot years almost got dried up. The problem was known at all levels, but its solution was not stopped not only because of financial constraints, but also because of technical aspects. The nearest well with safe drinking water was situated within half a mile distance from v. Zasullia. In addition, the village is separated from wells by the river Sula. When in the end of 2011, it became known that Zasully received the right to participate in CBA Project - decision of the villagers was unanimous. The CO “Vodogray-2012” was formed and members selected building of a new water supply system by consensus. The functional group had to work hard to solve this burning issue. The only engineering solutions was the building of the pipeline across the river at the bottom of it with the help of the so-called aqueducts. It was possible to perform such works only with the help of divers. Of course, from the engineering point of view, it was a bold project not only for the CO, but, in general, for the specialists of the rayon. However, the developed design estimates impressed the participants and the partners because the budget was 344 thousand UAH. As financial obligations of the Project could not exceed the equivalent of 10 thousand dollars, the partners had to agree about the share of co-financing. And it is difficult to overestimate the initiative of the Head of Zasulsky village council Ivan Mykhaylovych Gordiyenko who has set for itself a matter of honor - to help the community organization to complete the begun initiative. The question was put to the rayon local development forum where the participants agreed that local budgets and the Project would allocate 80 thousand each and the rest of the funds (which constituted - 184 thousand rhinos) would be collected by the community of v/ Zasullia itself. The head of CO “Vodogray-2012” Oleksandr Tatsenko remembers that it was difficult to convince people in feasibility of this project, to overcome mistrust and modern pessimism. Of course, the goal of the project has been achieved – the quality of life of the inhabitants of v. Zasullia has been improved. But now, looking back, all partners understand that the implementation of this project was a real test for professionalism, ability to negotiate and interaction. Each participant has learnt his lesson: the community has received the understanding that it can actively participate in solving of their own problems, regardless of their complexity and local government authorities have seen tremendous potential in partnership with local communities.

Box – 15: Opinions About Realisation of Community Dream “Today, the village knows how to solve complex issues independently. Most people themselves define who will be responsible for completion of specific tasks and who will control the money. And nowhere any misuse of the allocated funds was detected because everyone understands that it is for the benefit of the community. Moreover, I believe that the punishment of the community for unfair usage or embezzlement of funds can be worse than any court decision”. Grygoriy Derkun, the Deputy Head of Vinnytska Regional State Administration "When we only start our work with the community, our primary task is to convince the community that only together we can implement such projects." Volodymyr Snigur, the Head of the department of education of Krasylivsky RSA of Khmelnitsky region, “At the beginning people had mistrust to this project, but when the work had been started – the community activity increased. At 21:00 pm I received a call from an old woman. I thought something was wrong but she gleefully shouted into the phone - "Nina, in our small village a street lamp is lightening". In this part of the village street lighting was absent for about 20-30 years, and without participation in the project CBA-II we were unable to lighten the village”. Nina Laput, village Buzhanka, Lysiansky rayon, Cherkasy region

Chapter Six

Concrete foundations were laid during by mid-2012 for implementation of the concept of methodology replication launching of the component and establishment of partnership. In the reporting period additional partnership was established leading to full achievement of target. Furthermore, a series of activities were initiated during the reporting period namely in the area of capacity building, planning and micro-project implementation. Most of the tasks related with replication will be accomplished by mid–2014.

CBA-II envisions that the community based development methodology will be gradually internalised into the national framework of local development. From this perspective, there is a provision for capacity building support to competent partners at regional/local level. According to the project document, the action period for this component is from the 14th to the 42nd month of the project. Target for replication component is 60 rayons, 240  village councils and 240 communities and 240 micro-projects. Details about the replication component is given at the site: http://cba.org.ua/en/activities/methodology-revival

Under the component of CBA methodology replication, it is expected that oblast and rayon focal persons will be intensively involved in model implementation, with technical support and backstopping from CBA team. Grant for community projects is based on special cost sharing - local/rayon/regional authority – 70%, CBA Project – 25% (up to USD 2600 equivalent in UAH) and community organisation – 5%.

Methodology replication component was launched in 20 selected oblasts during first half of 2012. By July 2013, partnership was established with 61 rayons, 248 village councils and 248 communities following the standard practice of ‘competition based partnership’.

Focus of the component in the reporting period was devoted to initiation of micro-project implementation, which will continue through 2013 and beyond. Key activities and consequent results achieved during reporting period are described below:

6.1 Establishment of Partnership

During the reporting period, partnership was established with 18 village councils and 42 communities . With this target of partnership with rayons, village councils and communities was achieved in full. Details on partnership is given in Chapter-2.

6.2 Developing Support Structures

During the reporting period, 71 COs were formed by selected communities; 12 local development forum and 23 community resource centres were established by partner rayons. Since inception, 193 COs, 53 LDFs and 56 resource centres were formed thereby reaching near achievement of the targets. Details about support structure development is given in Section-3.

Table 16. Support structure development under methodology replication

| SN | Activity | Unit | Target All Years | Achievement |
| --- | --- | --- | --- | --- |
|  |  |  |  | PRP | CRP | Total |
| 1 | Rayons selected and partnership established | Number | 60 | 61 | - | 61 |
| 2 | Partnership with Village/City Councils | Number | 240 | 230 | 18 | 248 |
| 3 | Community organizations |  |  |  |  |  |
|  | COs formed | Number | 240 | 122 | 71 | 193 |
|  | Household participation/membership |  |  |  |  |  |
|  | Target households | Number |  | 44,851 | 15,158 | 60009 |
|  | Participated households | Number |  | 17,776 | 30,992 | 48,768 |
|  | CO members (total) | Number |  | 22,127 | 44,723 | 66,850 |
|  | CO members male (total) | % |  | 42.8% | 43.2 | 42.4% |
|  | CO members female (total) | % |  | 57.2% | 56.8 | 57.6% |
| 4 | Local Development Forums formed | Number | 61 | 41 | 12 | 53 |
|  | LDF sittings held |  | - | 56 | 110 | 166 |
| 5 | Community Resource Centres formed | Number | 61 | 49 | 7 | 56 |

6.3 Capacity Building

As described in Chapter 4 and Table – 17, various activities were implemented to build the capacity of stakeholders in the replication pilot areas. In particular 1791 community members and 525 representatives of local authorities were provided with training and exposure visits during the reporting period. Training included areas of CO management, planning, project implementation etc.

Table 17. Capacity building under methodology replication

| Activity | Unit | Target All Years | Achievement |
| --- | --- | --- | --- |
|  |  |  | PRP | CRP | Total |
| Training conducted | Number | - | 109 | 154 | 263 |
| Participants of the trainings | Number | - |  |  |  |
| CO members | Number | - | 1144 | 1791 | 2935 |
| Local authorities | Number | - | 566 | 525 | 1026 |

6.4 Community Projects

As described in Chapter 5 and Table - below, activities were initiated to support COs to implement micro-projects. It started with preparation of community development plan, mainstreaming of community plan through approval at LDFs, technical document and micro-project proposal, appraisal and approval of micro-projects by CBA, signing of grant agreement, implementation of micro-projects.

During the reporting period, a total of 124 COs prepared CDPs. During the same period, 136 CDPs were approved by their respective VCs/CCs and LDFs. In total, 191 CDPs were prepared and 105 were mainstreamed for funding. Also, during the reporting period 97 micro-projects were supported by CBA. Thus, by reporting period, 40% of micro-project target was achieved.

Most of the micro-projects were dedicated to energy saving sector and energy efficiency (15/97 micro-projects). Cost sharing occurred more or less in line with the projection as described in section 5.2 and section 8.4.

Table 18. Micro-project support under methodology replication

| Activity | Unit | Target All Years | Achievement |
| --- | --- | --- | --- |
|  |  |  | PRP | CRP | Total |
| Community development planning |  | - |  |  |  |
| COs with CDP prepared | Number | 240 | 71 | 124 | 195 |
| CDP approved and mainstreamed | Number | 240 | 49 | 105 | 154 |
| Micro-project supported | Number | 240 | 0 | 97 | 97 |
| Standard type | Number | - | 0 | 82 | 82 |
| Energy efficiency type | Number | - | 0 | 15 | 15 |

6.6 Experience

Problems and solutions

Effectiveness of methodology replication fully depends upon initiatives and financial capacity of the partner rayons and oblast authorities. Since, replication component requires more active role and larger share of cost, not all rayons, which showed keen interest at the outset could sustain their enthusiasm at the later stage.

- Lack of budget with the rayon authorities was identified as the biggest challenge. In a few cases related village council and oblast authorities were able to supplement a part of the cost from their budget. In some other cases, this support was not available and thus caused delay in initiation and implementation of micro-project. A few rayons terminated partnership due to lack of budget. The Project had to find substitution. CBA Project, on its part released its share in an accelerated pace so as to enable completion of the micro-project, wherever the contractors agreed to complete the task with an understanding that local authorities would disburse their part of the cost at a later date upon availability of the budget. It is expected that budgetary situation may improve slightly in 2nd half of 2013.

- New Ukrainian legislation caused centralization of technical document approval process and thus the procedure of MPP preparation  took longer than expected. In a few cases, rayon/regional authorities were able to influence the speed of approval. In general it was not possible. So far no immediate solution to this problem is foreseen.

Opportunity

Majority of regional and local partners seem to have recognised value of methodology replication as is clear from their strong support to replication activities of CBA. It is also found that several of these authorities have adopted CBA methodology while executing their ‘small grant’ programme.

Box – 16: Opinions About Methodology Replication “The main thing, of course, it not money, but the positive changes we see in other communities. People become more interested in the life of their village. Not indifferent to the initiatives. People are willing to work together. " O.I. Smashnyuk, focal point at Pervomayske RSA, Mykolayiv Oblast “During 2009-2010 years my community had been observing how other communities in the rayon collaborated with the CBA-I Project; their achievements were constantly highlighted by the local press. Due to this and to the support of the Kostiantynivsky rayon community resource centre the community organization “Eneyida” has been established on the territory of the village council. In the beginning, even without the support of the Project we implemented 2 small social projects, but it became apparent that the community initiative group didn`t have enough knowledge on sustainable development of the CO and organizational issues. Therefore, the participation in the CBA-II became very important for us, even on the condition of the proposed funding.” V. V. Shapovalov, the Head of the Oleksandro-Kalynivsky village council, Kostiantynivsky rayon, Donetsk region During the first phase of CBA Project, Terebovliansky rayon was one of the most successful in the region, and despite the fact that today we cooperate through replication modality, we will continue to strongly support every initiative of our communities. The most important is not the amount of allocated funds. Important is the focus on the problems of people”. Mykhayliuk Dmytro Vasylyovych, First Deputy Head of Terebovliansky Rayon State Administration (replication rayon)

Chapter Seven

Formation of 15 agricultural service cooperatives was initiated during the reporting period. A total of 9 cooperatives were formed during the period. Change in cooperative law and lack of understanding among the target population and related authorities caused delay in accomplishment of the target. Future outlook is positive.

Under the rural economic development (RED) component CBA-II envisions supporting small-scale economic initiatives of rural communities. The main focus is on promoting collective actions that could lead to generating income and creating employment opportunities in rural areas. The project is expected to assist low-income households to become organized and form cooperatives to bring added value to local products through efficient production, packaging and shared marketing.

The envisioned duration of the RED component of CBA-II was from the eighth to the 30th month of the project. It was launched in mid-March 2012. By June 2012, operational guidelines was prepared and selection of 7 pilot regions was made. Five of these regions were categorized as ‘normal pilot regions’ where development of cooperatives would take place in CBA communities while two of the regions were categorized as ‘special pilot’ where cooperative development would take place in non-CBA communities. Later one more region (Dnipropetrovska) was added as a special pilot.

Following activities were carried out during the reporting period:

  - Holding regional seminar

In July 2012, launching seminar was held in each ‘normal pilot’ region with an aim to launch RED program. Participants of the seminar were heads/deputy heads and contacts person of CBA-rayon authorities, heads of CBA-village/city councils, chairpersons of those COs in the region, that  were interested to participate in RED programme of CBA. During this seminar, terms of partnership were presented, action plan and competition among CBA/COs was announced.

In ‘special’ pilot’ regions, launching seminars were organized in Cherkaska and Chernivetska regions in participation of CBA-II rayons. Terms of cooperation were presented, and competition of rayons was announced. Four rayons were selected through the competition. In each of selected rayon, rayon seminar was organized and competition of non-CBA village councils was announced.

  - Selection of pilot communities

As a result of competition announcement during the seminars,  applications from CBA/COs (in normal pilot regions) and village councils (in special pilot regions) were received and ranked by RIUs and submitted to PMU for review and approval. Ranking was carried out based on the criteria -  (a) level of unemployment and poverty, (b) level of CO-members/community members willing to join cooperative and undertake economic activities, (c) past performance while working with CBA (only in case of CBA/CO), and (d) commitment of rayon authority to support cooperative activities. Most competent two COs/communities per region were selected by selection committee of CBA/PMU upon necessary review of the applications except in Dnipropetrovska region, where Petrivka village was selected as a special case to pilot production and marketing of local crafts. The selection process also ensured reserve communities so as to make substitution in case a community opted to exit.

“The present day realities leave the ordinary farmer on the territory where there is no work. For households the ability for households to develop their own business is vague, because the loan funds are unwieldy burden, also there are no institutions that would provide for free the knowledge about new technologies and their implementation in the small agricultural business for the farmers. Creation of the cooperative with CBA-II will become sufficiently effective lever to change this situation and to shift this question from its point.” O. V. Zhadan, the inhabitant of the village Oleksandro-Kalynove, Donetsk region

List of pilot regions, pilot rayons and pilot communities/COs is provided in Table – 19.

Table 19. RED pilot areas

| № | Oblast | Type of Pilot | Rayon | Village | Name CO |
| --- | --- | --- | --- | --- | --- |
| 1 | Donetska | Normal | Artemivskiy | Berestove | Vidridgennia |
|  |  |  | Kostiantynivskyi | Olexandro-Kalinove | Eneida |
| 2 | Kirovogradska | Normal | Olexandrivskiy | Pidlisne | krok u maibutne |
|  |  |  | Dolinskiy | Gurievka | Gurivka maibutnogo |
| 3 | Mykolaivska | Normal | Snigurivskiy | Barativka | Ellada |
|  |  |  | Bashtanskiy | Novopavlivka | Impuls |
| 4 | Sumska | Normal | Burinskiy | Chernecha Slobidka | Chernechoslobidske |
|  |  |  | Lipovodolinskiy | Pobivanka | Pobivanka |
| 5 | Ternopilska | Normal | Pidvolochiskiy | Koshliaky | Zelena Krinitsa |
|  |  |  | Kremeneckiy | Losiatin | Dobrobut |
| 6 | Cherkaska | Special | Zgashkivskiy | Kryvchunka |  |
|  |  |  | Zvenigorodskiy | Majdanetska |  |
| 7 | Chernivetska | Special | Storogenetskiy | Ropcha |  |
|  |  |  | Kitsmanskiy | Khlivyshche |  |
| 8 | Dnipropetrovska | Special | Petrykivskyi | Petrikivka |  |

7.3 Capacity Development

a) Training of staffs and authorities

On 10-11 July 2012, training was organized in Kyiv for 7 focal persons from OSA/OC deputed by the authorities to supervise implementation of RED component in their regions and 7 CBA community development officers. Programme of training included:

- concept and principles of cooperation,

- legal framework for cooperatives in Ukraine,

- strategy of RED component and its implementation procedure,

On 17-18 December 2012, training was organized for 8 CBA community development officers. Programme of the trainings included experience exchange on 1st dialogues in communities, practical tasks on business-plan development, discussion of possible changes in Ukrainian legislation. Two guest speakers from successful cooperatives (‘Zahid’, Rivnenska oblast, and ‘Khutir Sokolynyi’, Chernihivska oblast) presented their experience of cooperation and business activity in rural area.

b) Preparation of training/awareness materials: During 2012, Leaflet, operational manual and training materials were prepared, field-tested, printed and distributed among partners and stakeholders in pilot regions. A 13-minutes video film about cooperatives was prepared, to be used during 1st dialogues with communities. In December, because of changes in Ukrainian legislation related to service cooperatives, RED manual was revised and second edition was prepared, published and disseminated. Besides, an accounting manual was prepared and field tested and a manual on business skill was prepared.

7.4 Cooperative Development

As of end of 2012, dialogues were held with target communities in all pilot oblasts. Сommunity members were sensitized about necessity of mutual cooperation and collective actions for ameliorating their economic wellbeing. Initiative groups were created by community members to perform study of economic status and priorities of local households.

| Box - 17: Key Steps of Cooperative Formation Informing selected communities (1st dialogue) Formation of initiative group by the community Training of initiative group by CBA Household survey by initiative group Identification of target (low income) households and potential economic activity Statute development in perspective of target households and potential economic activities; General assembly and formation of ASC |  |
| --- | --- |
| h) Registration of ASC | Training of initiative group in Mykolaivska oblast |

As CBA methodology is aimed to support not less than 80% of target low income population it requires more intensive social mobilization and awareness raising of community members. In some (Sumska, Dnipropetrovska, Donetska, Cherkaska oblasts) community members decided not to continue with cooperative creation therefore other communities from reserve list were selected for the implementation of RED component.

Interaction with cooperative members in Bashtansky rayon, Mykolaivska oblast

In total, 11 agricultural service cooperatives (ASCs) were formed during the reporting period in participation of 467 households. During the same period, 4 ASCs got registered under non-profit multi-functional agricultural service cooperative form and one of the ASCs established a technical information centre under CBA support (Table – 20)

Table 20. Cooperative development

| Activity | Unit | Target All Years | Achievement |
| --- | --- | --- | --- |
|  |  |  | PRP | CRP | Total |
| Community selected | Number | 17 | - | 14 | 14 |
| CBA community | Number |  | - | 11 | 11 |
| Non-CBA community | Number |  | - | 3 | 3 |
| Cooperative development | Number | 17 | - | 9 | 9 |
| Target households | Number | - | - | 1326 | 1326 |
| Participated households | Number | - | - | 467 | 467 |
| Cooperative registered | Number | - | - | 4 | 4 |
| Priority area of the cooperative |  |  | - |  |  |
| Dairy (milk collection, chilling, supply) | Number | - | - | 1 | 1 |
| Vegetable farming (equipment, storage) | Number | - | - | 2 | 2 |
| Fruit cultivation (equipment, storage) | Number | - | - | 1 | 1 |
| Training organised | Number | - | - | 20 | 20 |
| Coop-members trained | Number | - | - | 154 | 154 |
| Local authorities trained | Number | - | - | 39 | 39 |
| Technical information centre supported | Number | - | - | 1 | 1 |

7.5 Experience

Problems and Solutions

Study of ongoing/traditional cooperative activity in Ukraine shows that CBA methodology differ significantly in that (a) it targets low income households, (b) 80% participation of target households, (c) proposes multi activities to capture economic potential of all members, (d) high degree of transparency in decision making, (e) financial commitment of members to ensure ownership. These elements, although appreciated, are not easily understood by community members as well as other stakeholders and lot of hesitation was observed during the dialogues the conditions proposed by CBA might cause exclusion of smart and non-poor families and the steps of cooperative formation proposed by CBA were considered as cumbersome and time taking. Training and sensitization efforts were to be repeated again and again to make the concept and methodology clear.

Low income households found it difficult to contribute share amount or find source of borrowing to run economic activities, despite their willingness to get involved. Since pro-poor banking sector is yet to develop in the country, many target households lost interest in joining the cooperative.

Serious challenge appeared in understanding of the newly enacted legislation on cooperative. Authorities in different regions/rayons interpreted concept of ‘profit’ v/s ‘non-profit’ ASC differently. As a result many communities failed to get their cooperatives registered under ‘non-profit format.

Enthusiasm among regional/rayon authorities and local councils was observed at the level more than expected and room was created for cost sharing from them. Role offered by the Project to the authorities for economic activities in the remote parts of the region was positively perceived by them . As a result, more output could be expected. However, new legislation makes it too difficult for the authorities to fund a cooperative.

It is planned to hire a legal expert to look into the issue of taxation, registration and funding from local budget.

It is expected that the cooperatives will submit micro-projects of size more than expected. In lack of cost-sharing from local budget and in absence of pro-poor credit mechanism, CBA may have to increase its share to enable low-income members to undertake economic activities. Therefore, original target of 17 cooperatives ought to be reduced to 15.

Pace of target participation in the cooperative development is lower than expected due to following factors:

- Risk avert behavior of low-income households make them reluctant in making financial commitment compared to ‘donation’ for public infrastructure rehabilitation;

- Low income households demonstrated dependency syndrome which is natural as traditionally they have depended upon non-poor households. As a result, they took more time to come forward;

- It was found that better-off households/businessmen in some communities succeeded in motivating the low income households to avoid joining cooperative;

- The process of cooperative formation and registration requires only a few persons to start with as founder members. Others join gradually once the cooperative gets into function and demonstrates scope for benefit;

- Often target households differ in economic portfolio due to difference in resource ownership, competence and interest. As a result, the target households come under pressure to accept the activity which offer benefit to majority of the households. The remaining households are offered second chance if the cooperative succeeds in getting resources. In such a situation, those households which miss to receive benefit in the first round choose to become passive.

Future Outlook

It is expected that process of cooperative development, capacity building and to great extent micro-project support will take place in 2nd half of 2013 and will continue into 2014. Concrete support from local budget is expected. Also, some of the cooperatives will require 2nd round of micro-project support in 2014 to achieve full exploitation of their potentials.

Chapter Eight

.

Implementation of the energy efficiency (EE) component in the reporting period was devoted to updating regional energy strategy, initiating implementation of micro-projects and developing energy awareness materials. Three of six regional energy strategy were updated and 145/300 micro-projects were supported. The major part of the activities will take place during the second half of 2013 through 2014.

Overall objective of the EE component of CBA-II is to enhance local capacity by enabling citizens and local authorities to learn about energy efficiency technologies and use them jointly to solve their energy problems in a sustainable way. This is to be achieved by though (a) review and improvement of regional energy efficiency strategies; (b) support to pilot micro-projects of energy efficiency based on introduction of micro-scale innovative technology and renewable energy sources; (c) awareness raising campaign.

In an attempt to assist citizens in rural areas to achieve the vision of energy efficiency through collective action, CBA-II aims to provide technical and financial assistance to Ukrainian authorities and rural communities so that they can improve the energy situation in their community. Key support will include:

- development of an energy efficiency strategy at regional level;

- advocacy/motivation for psychological preparedness to come together and to act together;

- training, roundtables, workshops and exposure visits to raise awareness and develop skills;

- seed grants for implementation of community initiatives.

According to the project document, the action period for this component is from the eighth to the 47th month of project implementation. Until June 2012, following results were achieved:

- Six advanced pilot regions and 19 normal pilot regions were selected;

- Operational manual and training materials were developed;

- Regional launching of the component was initiated.

During the reporting period, the following activities were carried out to achieve the intended results:

- Launching of EE component at the regional level was completed

During June-July 2012, launching seminars of EE component were organised in all 25 regions with an aim to launch both kinds of piloting. During these seminars, terms of partnership were announced, as well as the action plan. In each region, competition among CBA rayons was announced for selection of pilots for implementation of EE component. Quota of rayons per region is:

- 4 rayons per region through advance piloting;

- 3 rayons per region through normal piloting.

- Selection of pilot rayons

During July-August 2012, rayons submitted their applications: 58 rayons applied from ‘advance pilot’ regions and 142 applications were received from rayons of ‘normal piloting’ regions.  Applications were analysed, evaluated based on a set of criteria (Box -18), and approved by CBA in close cooperation with the officials of the regional authorities. Accordingly, 24 rayons in the advanced piloting regions and 54 rayons in the normal piloting regions (except Zhytomyrska oblast) were selected. Among the selected rayons 13 were replication rayons.

Box – 18 : Criteria for Selection of Pilot Rayons for Implementation of EE Component Potential of renewable energy sources in the rayon; No. of rural communities lacking gas supply; No. of rural communal infrastructures facing serious energy inefficiency; Availability of special programme & budget to exploit renewable energy opportunities; Level of technical capacity (in term of human resource) to work on renewable energy sector; Level of pro-activeness (performance) in implementing CBA methodology

Map – II. Area of implementation of EE component

- Launching of EE component at the rayon level: During August-September 2012, introductory seminars were organized in the selected rayons of ‘normal piloting’ regions in order to present the terms of participation in the EE component and announce the competition of micro-project ideas.

Box - 19: Micro-project Idea for Finding Most Potential Project Under EE component, opportunity is given to all communities in the rayons selected for EE component. A community (CBA-II or otherwise) that has a sound idea of energy efficiency micro-project could become eligible for competition. The idea includes a clear estimate of the nature (energy saving, innovative technology, renewable energy) of the energy project the community would like to implement along the cost estimation and cost sharing vision. Among all applicants from the selected rayons, two MP-ideas per rayon are selected for support based on following criteria: Nature of MP Idea (energy production and/or saving) Nature of Technology (innovative, renewable, mixed) Energy Independence (contributes, consumes, both) Level of Coverage (comprehensive, partial) Level of Expected Benefit (pollution reduction, energy saved/added) Proposed cost sharing arrangement Past performance of CO Potential of demonstration effect In case, the selected community is not a CBA-II community, then the process is initiated to bring the community into CBA-II framework through implementation of all the steps required to this end, before extending concrete support towards implementation of micro-project idea.

8.3 Capacity Building

- Training\information materials development: in 2012 manual on energy efficiency component was prepared, tested, published and disseminated among partners in regions. 5000 copies of leaflet on the EE component was prepared, printed and disseminated.

- Trainings: In order to develop necessary capacity for advanced piloting, training was organized on EE implementation during 12-14 July, for 6 focal persons from OSA/OC and 6 CDOs from advance pilot regions. Programme of the training in Kyiv included presentation of EE component and modality of its implementation, regions’ needs assessment in terms of energy efficiency and case study of best practice of regional energy strategy. By the end of the training, each region drafted an action plan of EE component implementation, based on the actual needs and vision.

8.4 Micro-project Support to Local Communities

Under EE-component, micro-project support is provided to local communities carry three features:

- Complex type EE- micro-project that strictly observes norm of innovative energy efficiency/ renewable energy technology, energy auditing (before and after implementation of MP) and complex technical documentation that go through sophisticated approval process. CBA shares 70% of the cost up to $ 20,000 while local cost sharing is 30% including 5% from CO and 25% from local budget;

- Standard type EE- micro-project that observes normal form of energy efficiency technology and standard technical documentation, approval and funding mechanism. Thus, CBA shares 50% of the cost up to $ 10,000 while local cost sharing is 50% including 5% from CO and 45% from local budget;

- Replication type EE-micro-project that observes normal form of innovative energy efficiency technology and normal technical documentation and standard approval and reduced funding mechanism. Thus, CBA shares 25% of the cost up to $ 2,600 while local cost sharing is 75% including 5% from CO and 70% from local budget;

Inter-rayon local development forum on energy efficiency, Donetska oblast

- Implementation of complex EE micro-project

A total of 163 MP-ideas is expected from all regions for complex EE micro-project. During the reporting period, 81 micro-project ideas were received from  pilot regions. Of them 71 MP-ideas were approved upon due assessment.  Based on MP-idea approval -

- 81COs received approval of their proposal from respective LDFs;

- 15 COs prepared technical documentation to be sent to the approving agency;

- 14 COs got the proposed project object energy-audited;

- 16 Communities were new and therefore process was initiated to develop them into full fledge CBA-II COs.

It is expected that approval and implementation of complex type EE-micro-project will start from 3rd quarter of 2013 and will continue along 2014.

Problems and solutions

Review of MP ideas revealed that the local authorities and local communities had not well understood the idea behind energy efficiency. Despite CBA’s presentations during roundtables/launching seminars and dialogues, they strongly carried the experience on energy saving and heavily reflected this component in the MP-idea making energy efficiency component just a token in the proposal. CBA staffs had to work with the communities and authorities to get the MP-ideas improved. It was learnt that need of energy saving component is so big in the communal buildings of the rural areas that villagers and authorities could hardly imagine anything innovative. CBA however, persisted with its vision and initiated an orientation training for all potential communities and relevant authorities in each region before they developed MP-idea. The initial result was encouraging. Several communities decided to change their idea altogether. This process caused delay in executing the component. Besides, 16 communities were new and did not have CBA-II CO. They required to go through the whole process of institutional development, maturity and participatory planning before undertaking the MP. This situation further caused delay.

- Implementation of standard type EE micro-project

During the reporting period, 130 standard type micro-projects were approved and funded for implementation. In total since 2011, 130 micro-projects were supported (Table - 22). Most used technology was modernization of heating system followed by street lighting. A total of UAH 21.7 was foreseen for these micro-projects, which was shared by local budget (49,0%), CBA (44,8%), COs (5,4%) and private sponsors (0,8%).

- Implementation of replication type EE micro-project

During the reporting period, 15 replication type micro-projects were approved and funded for implementation (Table - 21). Most used technology was street lighting followed by modernization of heating system. A total of UAH 1.8 mln was foreseen for these micro-projects, which was shared by local budget (75.2%), CBA (16.6%), COs (5.4%) and private sponsors (2.8%).

Table 21. Energy efficiency micro-project implementation*

| Activity | Unit | Complex type | Standard type | Replication type | Grand Total |
| --- | --- | --- | --- | --- | --- |
|  |  | PRP | CRP | Total | PRP | CRP | Total | PRP | CRP | Total |  |
| Micro-projects approved | No. | 0 | 0 | 0 | 55 | 75 | 130 | 0 | 15 | 15 | 145 |
| Nature of EE micro-projects |  |  |  |  |  |  |  |  |  |  |  |
| Innovative technology | % |  |  |  | 54 | 74 | 128 |  | 15 | 15 | 143 |
| Renewable energy | % |  |  |  | 1 | 1 | 2 |  | - | - | 2 |
| Both – innovative + renewable | % |  |  |  | 0 | 0 | 0 |  | - | - | 0 |
| Total cost of approved MPs | UAH ml |  |  |  | 8.0 | 13.7 | 21.7 |  | 1.8 | 1.8 | 23.5 |
| Shared by COs | % |  |  |  | 5,6 | 5,4 | 5.5 |  | 5.4 | 5.4 | 5.5 |
| Shared by local budget | % |  |  |  | 47,6 | 49,6 | 48.9 |  | 75.2 | 75.2 | 50.9 |
| Shared by CBA | % |  |  |  | 45,8 | 44,4 | 44.9 |  | 16.6 | 16.6 | 42.6 |
| Shared by private sponsors) | % |  |  |  | 1.0 | 0,6 | 0.7 |  | 2.8 | 2.8 | 1.0 |
| Beneficiary characteristics |  |  |  |  |  |  |  |  |  |  |  |
| Beneficiary population | Number |  |  |  | 45758 | 93258 | 139585 |  | 10305 | 10305 | 149890 |
| Institutional beneficiary | Number |  |  |  |  |  | 130 |  | 15 | 15 | 145 |
| School/kindergarten (cum.) | % |  |  |  | 10 | 27 | 37 |  | 3 | 3 | 40 |
| Health facility (cum.) | % |  |  |  | 1 | 8 | 9 |  | 0 | 0 | 9 |
| Local communities (cum.) | % |  |  |  | 44 | 40 | 84 |  | 12 | 12 | 96 |
| Micro-project completed | Number |  |  |  | 27 | 9 | 36 |  | 0 | 0 | 36 |

* Regional details in Annex – V A, B

8.5 Updating of Regional Energy Strategy in Advance Pilot Regions

During first reporting period, a national study was carried out and an international workshop was supported in collaboration with UNDP/Bratislava Regional Centre on the subject of energy efficiency in the rural areas. Recommendation of these two activities were used to shape the policy and procedure for implementing energy efficiency component.

Following activities were taken during the reporting period in the realm of improvement\development of regional energy efficiency strategy:

- The concept of regional energy strategy improvement was elaborated and ways of cooperation with region authorities was sought. Accordingly, the  advance pilot regional authorities deputed an energy focal person to support the implementation of energy efficiency component;

- In September 2012, announcement was made for 6 consultants on energy strategy – one for each of 6 advance pilot regions. However, only three consultants could be selected due lack of adequate number of competent candidates.

- The selected consultants were provided with necessary orientation and field exposure. In November 2012, joint vision and methodology of reaching the objective was developed;

- In December 2012, launching session was held in three pilot regions, Lvivska, Ivano-Frankivska and Zaporizka. Energy working group was formed in each region involving energy focal person and experts and officials from the relevant departments.

- The consultants carried out the task of improving regional energy strategy in the framework of following order:

  - Basic information collection and analysis by the consultant

  - Presentation of vision and methodology of updating regional energy strategy by the consultant in a round table organised in each oblast

  - Collection of additional data and information as necessary with the help of oblast working group on energy strategy

  - Field visit, by the consultant and oblast authorities, to gather first had experience at the local level;

  - Preparation of the draft report by the consultant and review of the report by CBA specialists;

  - Discussion of the draft report at an oblast level roundtable involving regional experts, officials, private sectors, local councils, NGOs and media

  - Finalisation of the report and formal submission to the regional authorities

  - Discussion of the report/recommendations at oblast council meeting and decision of the oblast authorities to utilise the recommendations during current phase and/or during the forthcoming strategy phase 2015-20

Roundtable on energy strategy development – Dnipropetrovska oblast

The energy strategy improvement support produced a positive impact on the vision and programme of the oblasts. In principle they recognised the necessity of including into their strategy the micro-level interventions in the rural areas to promote innovative energy technology renewable energy sources in community participation. Besides, they approved small programme to support this vision in current strategy period.

Problems and solutions

Energy strategy exists in each region in line with the national vision. However, their structure and content varies greatly from region to region. Also, vision on energy efficiency/innovative technology/renewable energy suitable for rural areas is almost non-existent. The same is true about concept of sustainability and people based implementation of energy efficiency concept. In course of roundtables and expert consultations, environment was developed in favour of this vision thanks to exposure of authorities with CBA methodology since past many years.

The existing strategy is for the period up to 2015. In 2014, the regional authorities will undertake the task of developing energy strategy for 2015-20 period. In this situation updating of current strategy in 2013 will have less value from the perspective of getting into implementation. Therefore, the regional authorities suggested to support strategy development in two steps: first prepare concept for 2015-20 strategy this time and then support strategy development for 2015-20 period upon approval of the concept from regional council. This proposition sounded appropriate and the Project carried out the task of energy strategy improvement in the same spirit.

Box - 20: Preliminary Recommendations for Improving Regional Energy Strategy Analyze corresponding sectoral programs approved by oblast council for 2013 and make changes to suit the vision of energy component of CBA Project. Development and approval of project documentation on the objects of urban development (building, reconstruction, capital repair), alternative and renewable energy sources should receive priority; Analyze rationality of a system of collecting, transportation, recycling of communities’ economic activities waste products with following utilization of recycled products; Calculate potential of annual accumulation of households’ organic waste for possible recycling for biofuel; Develop proposition of legislative stimulation of territorial village/ urban village communities, for storage and recycling of wastes for biofuel. Analyze rational use of water resources by local territorial communities (for the purpose of micro-hydro power). Analyze efficiency of current energy sources use in village communities calculating of unit of superficial heating area and hot water in calculation for thousand cubic meters. Analyze possibility of establishing cooperative relation between agricultural enterprises and households on joint processing and applying of organic waste products under the terms of cooperation and providing of joint propositions. Provide propositions on the structure of electronic system (including acting) monitoring and analyzing of sustainable development of region; Prepare propositions for adoption of changes to the regional programme on increasing energy efficiency in oblast for 2010-2015 including study on creation of the system of alternative energy use by local communities of oblast. Submit proposal on adoption of changes to the regional programme on increasing of energy efficiency in oblast for 2015 and development of the proposals to the next period (2015-2020) with the principle of rational use of renewable energy sources; Submit proposals on adoption of changes to regional programme, acting on the oblast territory, which are related to implementation of infrastructure and investment projects/programmes supported by budget costs, with involvement of local territorial communities co-financing share in amount of 15%, taking into account their material conditions, as of main beneficiaries, in accordance to the Strategy. Oblige the heads of rayon state administrations, recommend to the heads of city and village councils to evaluate amount of necessary investments on each object, which is maintained by budget costs, to bring it up to energy efficiency standards and compare it to the amount of investments required with possible costs of new construction in accordance to modern technologies; to determine the feasibility of reconstruction or capital repair of the building, and public sector in comparison to the new construction.

8.6 Raising Public Awareness on Energy Efficiency

It is visualized that public awareness on energy efficiency will be raised through various methods upon documentation of the results and experience gained through implementation of energy efficiency component.  The methods include publication and airing of the experience in local/national media, roundtables, trainings etc. It is expected that this activity will gain start during 2nd half of 2013 and continue in 2014.

Following preparations were made during the reporting period towards raising public awareness on energy efficiency:

- Information about best practice in energy saving and energy efficiency was regularly disseminated via mailing list and through CBA Facebook page: http://www.facebook.com/cbaproject;

- CBA communities, local councils, rayon authorities and regional authorities are motivated to invite professional companies and organization for helping in study and choosing technology.

- Draft leaflet was prepared on ‘energy for all’ in line with the UN publication on the subject. This leaflet will be published for wider dissemination in 2nd half of 2013;

- Materials were collected for preparing a video film on energy efficiency awareness. The film will be prepared in 2nd half of 2013 and will be used widely for raising public awareness;

- Vision was developed to adopt the document ‘Heat Is On’ prepared by Bratislava Regional Centre based on Odesa workshop to suit Ukrainian needs and bring out the adopted version for wider circulation. This publication is expected in 2nd half of 2013.

8.7 Future course of action

Following activities are to be undertaken within EE component in 2013:

- Improvement of energy strategies in the remaining 3 regions;

- Support of technical documentation development for big projects in the realm of renewable energy;

- Support to energy efficiency micro-projects

- Experience documentation and dissemination for raising public awareness on energy efficiency

Box – 20: Opinion on Energy Efficiency Component “I would like to ​​draw the attention of the rayon leaders: take an active part in the competition of projects on energy efficiency in the frame of the CBA project, it's a great opportunity to introduce innovative technologies in the communities." Head of Volyn OSA, Borys Klimchuk “If it were introduced earlier at least on twenty years, namely, together with the formation of Ukrainian statehood, it would be possible to achieve significant economic effect of implemented measures and already would have saved several annual budgets of local communities.” Yuriy Golota, the First Deputy Head of Veselivsky RSA, the deputy of Zaporizhka Regional Council “The main objective is to improve regional energy efficiency strategy, focusing on rural areas, innovative energy efficient technologies and renewable energy sources.” Vasyl Pliaviuk, the First Deputy of Ivano-Frankivsk Regional State Administration “Artemivsky Rayon State Administration believes that innovative energy technologies on energy efficiency at the moment are a promising direction of development. Each year more and more becomes a question of reducing the cost of energy resources required for heating and hot water supply. Crisis, increasing the prices of energy resources and improvement of environment bring renewed interest to alternative sources of energy.” Viktor Danylov, the Head of Artemivsky rayon state administration, Donetsk region “For a long time we considered the replacement of windows on metal-plastic ones, repairing roofs, facades as innovation projects on energy efficiency... Today these works do not surprise anybody, though they do keep heat in the premises. What is required actually - alternative sources of energy, new heating systems and lighting. But here the demands differ greatly, even to construction estimates, and the project costs are considerably higher, and the experts are not always can be found and ensure the high level of professionalism. So the responsibility also differs.” Oleksandr Fedorovych Grushko, the Head of Nyzhnyosirohozky village council, Nyzhnyosirohozky rayon, Kherson region “The usage of alternative energy allows saving of hundreds of thousands tons of equivalent fuel. At the same time this is the most important direction of energy efficiency growth of economy and the best way to take care of the environment.” Oleksandr Sergiyenko, the Head Paraskoviyivsky village council, Artemivsky rayon, Donetsk region “Alternative energy is the friendliest for environment among the energy sources. It kept limited mineral resources and significantly reduces the amount of harmful substances in the atmosphere. The usage of alternative energy not only has a positive impact on the environment, but also saves a lot of money, monthly and annually. “ Oksana Sopelnyk, Head of the Sector for Investment Policy and Territorial Dev. of Economic Department of Artemivsky RSA, Donetsk “The implementation of energy efficient technologies will not only allow us to stop using natural gas and use less costly natural resources, but also to improve the natural environment, which is also an important recent problem.” N. G. Sardina, the Head of CO "Kindrativets", v. Kindrativka, Kostiantynivsky rayon, Donetsk region “The project support formation of the energy independent system of local communities that allows receiving energy from multiple sources, reducing tariffs on utilities and saving the budget and community funds.” Pavlo Trypolsky, the Head of CO “Omelnyk”, v. Omelnyk, Orikhivsky rayon, Zaporizhka region

Chapter Nine

Concrete foundations were laid to operate the knowledge management hub established during first reporting period at the Ukrainian Association of District and Regional Councils. Also, support was provided to introduce the curriculum on sustainable development and the community-based approach. A series of activities were undertaken during the reporting period towards raising interest among students, teachers and policy makers towards necessity of community based sustainable development.

National-level application of the community-based approach to local development methodology produces a tremendous effect on the local development process. To make the best use of knowledge gained and lessons learned, the knowledge management component of CBA activities aims to document and systematize the regional experience and lessons learned; to introduce the community-based approach to specific courses of higher education; and to transfer the Ukrainian experience to the target audience in other countries. Details on these activities are given below.

During the first reporting period agreement was signed with  the Ukrainian Association of District and Regional Councils (UADRC) for establishment of knowledge management hub (KMH), partnership was established with 20 universities for teaching the course on community based sustainable development and a series of activities were supported to promote research and teaching on the subject.

Following activities were undertaken during the reporting period to enhance the effectiveness of the  KMH and teaching of the course:

9.1 	Knowledge Management Hub

The sustainability of CBA results and the scale of replication of the community-based development methodology greatly depend on accessibility of knowledge and expert/advisory support and the quality of information channels between communities, authorities, business, experts and researchers. To meet the huge demand for information and experience related to CBA, the establishment of a knowledge management hub (KMH) was envisioned. The overall objective of the activity is to support the creation of a locally owned and managed repository and network of good practices and knowledge on community-based development and participatory governance. Following activities were carried out during the reporting period in context of establishing KMH:

- UADRC recruited a knowledge management team which was trained by the CBA during July 2012;

- Equipment and logistic required for the hub were procured;

- The concept of the KM web platform was developed and agreed with stakeholders;

- A web portal was developed by an expert recruited under terms of reference drafted in line with the concept. The hub can be accessed at http://rozvytok.in.ua/

- On the 13th of September, the knowledge hub and the web platform was launched at the board meeting of UADRC in front of 30 heads of rayon councils;

- On the 24th of  September, the concept of knowledge hub was presented by CBA Communications & Monitoring Specialist at Social Good Summit ‘How new technologies and social media can help solving the problems of community and humanity’, organized in Taras Shevchenko National University of Kyiv;

- On the 3rd and 4th of  December, training for coordinators of 15 rayon resource centres from 15 regions was held.  The main aim of the training was to test the web portal and knowledge hub. The participants were familiarized with the purpose of the web portal, its structure and functions. They were asked to conduct various practical tasks like - registering a new user; uploading information about their resource centres including photos and videos; etc.;

The total cost of the KMH activities in 2012 was estimated to be UAH 402,300 of which 19% was borne by UADRC and UAH 81% was supported by CBA as grant.

Problems and solutions

The Idea of KMH is relatively new to Ukraine and the UADRC-authorities have low understanding about its value and function. The same was true in cases of KMH-staff. Thus, the authorities and KMH-staff need to be sensitized time and again and exposed to successful knowledge management cases in other counties;

Internalization of KMH into its structure is an important milestone to sustainability of the hub. However, capacity building support must be continued to equip it and train additional staff recruited by the association;

Capacity building support will also be needed to (a) further develop the portal, (b) enrich the hub with relevant information, (c) make a membership drive and (d) make efficient moderation.

9.2 	Partnership with Academia

- Introducing ‘Sustainable Society Development’ course into curriculum

In the autumn semester, 12 universities introduced the course into their teaching curriculum. Thus, target of reaching academia during CBA-II was achieved in 2012. List of partner university is given in Annex – VI.

- Summer school ‘Sustainable development and community participation’

On the 6th to the 10th of  August, a Summer school entitled  ‘Sustainable development and community participation’ was held in Yevpatoriya. Fourteen young scientists from five Ukrainian universities presented results of their research of social, economic and environmental aspects of sustainable development.

The opening of the Summer school was attended by the Deputy Country Director of UNDP in Ukraine Elena Panova and the Head of Operations Section of the EU Delegation to Ukraine  Mr. Jose Roman Leon Lora. Welcoming the participants, Mr. Jose Roman Leon Lora highlighted the important role of sustainable development issues in the vision and activities of the European Union. Ms. Elena Panova mentioned that taking into consideration the multiple-aspect character of sustainable development problems it is possible to achieve success in this direction only by joining of government efforts and the efforts of communities and businesses with involvement of national scientists to the dialogue and practical cooperation.

| The opening of the Summer school was attended by Jose Roman Leon Lora, Head of operations section II of the EU Delegation to Ukraine and Elena Panova, UNDP Deputy country Director | Participants of Summer school visiting a community organization in AR Crimea |
| --- | --- |

During the weeks of the summer school participants exchanged their visions on various aspects of sustainable development as well as learned about the achievements of international organizations in reaching sustainable development goals. Study tours to two CBA communities and one pilot community of MGSDP were organized to give the opportunity to communicate with people who had implemented principles of sustainable development in practice.

- Support for research on community based development

CBA-supported research ‘Impact of CBA Project Activities on Social Capital in Sumy Region’ carried out by a group of researchers from Sumy State University, continued. Results of the first round of survey were summarized and analyzed. The second round of interviews will be organized in October and November 2012 with an aim to reveal the impact of CBA activities on social capital.

Box – 21: Impact of CBA Project Activities on Social Capital in Sumy Region* In January 2012, Sumy State University (SSU) launched the research ‘Impact of CBA Project on Social and Economic Indicators in Sumy Region’, carried out by a group of researchers from SSU. Objective of this study is to assess impact of CBA-I socio-economic characteristics and social capital characteristics. The study was conducted in Sumska oblast considering CBA-I communities as intervention group and newly selected CBA-II communities (yet to receive benefit from CBA) as a comparison group to understand what would be socio-economic and social capital situation in those CBA-I communities had they not been benefited from CBA-I. The study utilised secondary data on 11 social-economic characteristics of villages of Sumy oblast pertaining to 2005-2010 period. A survey of 960 households was undertaken to gather information on 9 social capital characteristics from intervention and comparison group using sociological survey and pipeline matching methodology. The information was analysed and inferences were dawn using percentage analysis and regression analysis tools. Findings of the research shows that – Intervention communities experienced significant impact on the socio-economic characteristics over comparison communities, namely (a) village population; (b) bus connectivity; (c) migration; (d) No. of people employed per sector; (e) No. of people employed out of the village; (f) No. of people employed in the entrepreneurial sector; (g) No. of seats at school and kindergartens; (h) No. of health centre visits; The rate of growth of social capital characteristics was significantly higher in intervention communities compared to comparison communities. The characteristics included (a) traditions of the community, (b) information and communication, (c) empowerment and political action, (d) (anti-)paternalism, (e) level of trust, (f) solidarity and inclusion, (f) general norms, (g) collective action and cooperation, and (h) general characteristics of the community (e.g. propensity to migrate, employment conditions, safety and others); Communities in the districts belonging to culturally and historically known for collectivism offered higher propensity of adopting organizational and financial mechanism of CBA compared to the districts who carried individualism in their culture and history. * Detail in Annex – VII.

- Workshop for partner universities

On the 13th and 14th of  December 2012, the annual workshop for coordinators of partner universities was held in Lviv. The National University ‘Lvivska Politechnika’ hosted this even. The main aim of the event was to assess results of academia related activity in 2012, and to develop a vision of further cooperation in 2013. Followings are the findings of the workshop:

Results of  activities during the reporting period

- First experiences in teaching the course\module on ’Sustainable Society Development’ revealed that (a) the textbook on sustainable society development provided by CBA Project was very useful and (b) sustainable society development is a very wide topic and may be included in a variety of courses (sociological, economic, political science, ecology etc.);

- Competition of student papers was proved to be useful. However, (a) it should be announced in March and involve students of not only the third and fourth year but in the second year also. This is because students in their second and third years are still interested in learning and undertaking different forms of research, while those in their final year may be more focused on finding a graduate job rather than their studies; (b) criteria of papers should be more specific and on given topics;

- The Summer school ‘Sustainable Development with community participation’ was effective in terms of motivation and exchange of inter-regional experience and should be continued. However, it should also include winners of the students’ debate;

- Student internships offered positive result as the students gained practical experience in communication with communities and knowledge on bureaucratic procedures. Later on students had the opportunity to apply for jobs in official institutions. Therefore, this activity should be continued. However, a data base of available OIUs for internship with specification of dates and duration of internship along with a guidelines on methodology of internship should be circulated to universities.

Proposal for next reporting period:

- To develop a collection of successful and unsuccessful cases of community activities in the realm of solving their problems (for example, using CBA cases);

- To develop a set of teaching video materials;

- To invite guest speakers to participate in lectures. Community organization’s head, activists might serve as guest speakers and present their experience of community mobilization and local development of their territories;

- To develop a distant course in order to involve more students with sustainable development topics;

- To involve students in internship, debate on sustainable development, small research on CBA and Summer school;

- To link academia with the knowledge management hub established at UADRC under the support of the CBA.

9.3	Knowledge Sharing

Sharing and dissemination of knowledge is the key priority of the CBA-II knowledge management component. Responding to frequent requests, CBA often hosts or participates in information-sharing visits. In the reporting period, the following event took place:

From the 3rd to the 7th of September, the CBA hosted a study visit of the Arminian delegation, including representatives of  UNDP Armenia, Ministry of Territorial Administration, Ministry of Labor and Social Affairs, Ministry of Nature Protection  and Deputy Governor of Tavush region.

Armenian delegation meetings with communities

The visit was organized with the aim to present Ukraine’s experience of community based development. The programme of the visit included a meeting with UNDP Ukraine management, briefings on local development cluster and its projects, presentations about CBA methodology and a two day field visit to Cherkaska and Kirovohradska oblasts.

Armenian delegation meetings with rayon and regional authorities

During the visit, the delegation met with pilot communities of Kirovohradska and Cherkaska oblasts, interacted with representatives of rayon and oblast authorities, visited micro-projects sites and interacted with community members.

9.4 	Policy recommendations

In 2012, the CBA Project continued to supported UADRC for development of policy recommendations and amendments to draft Law on Bodies of Self-Organisation of Population (BSP). Several round tables were organized to discuss the draft law. In August, the finalized draft was submitted to the Ministry of Regional Development, Housing and Construction, to be reviewed and submitted to Verkhovna Rada.

Box – 22: Opinion on Process of Policy Formulation "For improving local policy directions, it is necessary to pay attention to work at the community level, which must become an important aspect of that policy. The Implementation of the CBA project may be regarded as an important step in development of the participating communities, as well as in establishment of civil society in our country. However, in spite of significant achievements in working with the community, many aspects of work with this category still require new developments, improvements and implementations." O.S. Kapelyukha, Deputy Head of the Economics Directorate of the Chernihivska OSA.

Chapter Ten

The project succeeded in raising the visibility of CBA activities and its key donors, the EU and UNDP, in the regions. The role of national counterparts at regional and local levels was also highlighted. This was made possible due to 128 media events, 946 items of media coverage, 87 issues of newsletters and 2 visits by donors and partners during the reporting period.

The CBA Project aims to maximize the level of transparency of its implementation, and strives to involve the media to inform the public about its milestones. The following activities took place during the reporting period in this regard:

10.1 	Media Events

During the reporting period, opportunities for organizing public/media events occurred. These were mostly opening ceremonies of micro-projects, partners’ and donors’ visits. Media events at local and regional level were often organised in coordination with authorities at the level. Very often the press departments of OSA/OC played significant role in inviting media at the level and coordinating the event. In total, 128 media events took place during the reporting period. Since inception, 453 media events were organized (Table – 22).

Table 22. Media events

| Activity | Achievement |
| --- | --- |
|  | PRP | CRP | Total |
| Media events | 325 | 128 | 453 |

- EU journalists’ tour: On 6th of September, a press tour to Yabluneve village (Kyivska oblast) was organized for 12 journalists of Ukrainian and Armenian mass media. The press tour was organized in framework of the EU-supported Media Neighbourhood Programme. During the press tour journalists had opportunity to meet and communicate with community members, and representatives of rayon state administration and rayon council. Journalists got familiarized with results of first micro-project implementation in energy saving.

Group of Armenian and Ukrainian journalists participated in the opening of micro-project (energy saving in school) and met with the community organization to learn about their path towards self-organization

Selected journalists’ reports can be viewed at following links. In general, the writings depicts positive impressions after observing the results of community’s self-organization and implementation of micro-project:

- http://www.facebook.com/photo.php?v=545155415498143

- http://glavcom.ua/articles/8177.html

- http://www.mynews.am/hy/node/2017

- http://blogs.pravda.com.ua/authors/andrushko/504c6d3193c51/

b) TV journalists visit: In September, 4 visits to communities of Poltavska, Luhanska and Lvivska oblasts were organized for journalists of Channel 5 with the aim to create video stories. Stories were aired on Channel 5 in “Window to Europe”, and posted on CBA Facebook page and uploaded on YouTube:

- Univ, Lvivska oblast:  http://www.youtube.com/watch?v=CAJ0eiQOs0A&feature=player_embedded;

- Milove, Luhanska oblast: http://www.youtube.com/watch?v=YzxHZGSBCZ4&feature=player_embedded;

- Novi Martynovychi, Poltavskla oblast: http://www.youtube.com/watch?v=yMDG28yVr3Y&feature=relmfu;

- Luka, Poltavska oblast: http://www.youtube.com/watch?v=CUr_n023_Q4&feature=youtu.be

# 10.2 	Media Coverage

# During the reporting period, 946 cases of media coverage were traced. The most used media was TV (40.8%) for dissemination of information followed by electronic media (25%), newspapers (18%) and radio (16.2%). Total number of the recorded media coverage since inception of CBA-II is 3615 (Table – 23).

Table  23. Media coverage

| Activity | Achievement |
| --- | --- |
|  | PRP | CRP | Total |
| Media coverage | 2669 | 946 | 3615 |

* Region-wise details are given in Annex – I

Chart - I: Distribution of Media Coverage in 2012

# 10.3	CBA in Social Media

# CBA page on Facebook (http://www.facebook.com/cbaproject) was launched at the end of August 2011, allowing for real time reporting and instant access to information about partners’ activities. After the special training module for coordinators of Rayon Community Resource Centres, RCRCs followed the suggestion on creating their pages on Facebook and actively use them to publish and exchange information and experience.  As of end of 2012, 67 RCRCs became part of the virtual network of RCRCs created under initiative of CBA.

# An analysis of the users of CBA Facebook during 2012 shows that –

# Number of unique people who saw content associated with CBA page ranges from 1 to 17 per day;

# Facebook page mostly reached the age group of 25-34 years old (43.9%), followed by the group of 35-44 years old (almost 25%) and 13% of visitors between 18-24 years old;

# People from 17 countries visited the sites, with Ukrainian occupying the highest number

# 10.4	Regional Newsletters

In order to disseminate information about the Project among stakeholders, potential participants and wider public audience, regional implementation units published newsletters regularly. During the reporting period, 87 issues of newsletters were published in all regions. They were disseminated both electronically (1855) and printed copies (5482) according to the distribution lists. The recipients of the newsletters were regional administrations, regional councils, rayon administrations and councils, village/city councils, local communities, local media, and NGOs. Since inception, 207 issues of regional newsletters were produced, with 21812 hard copies disseminated among stakeholders, and 5763 copies disseminated electronically (Table - 24).

Table 24. Distribution of CBA regional newsletters*

| Activity | Achievement |
| --- | --- |
|  | PRP | CRP | Total |
| No. of issues published | 120 | 87 | 207 |
| No. of copies printed & distributed | 16330 | 5482 | 21812 |
| No. of copies sent electronically | 3908 | 1855 | 5763 |

* Oblast wise details in Annex –  I

10.5. Communications Activities on RCRCs and COs

Rayon community resource centres and pilot communities of CBA are encouraged to apply in their actions the same principles of transparency and accountability.  Thus, many rayon resource centres have adopted the good practice of publishing their news at the RSA/RC web site, and RCRC’s Facebook page. Many RCRCs started to issue their own newsletters, at their own expense.

In the attempt to provide due level of transparency and accountability, COs regularly inform members of their organization about each step taken by the CO management team. For this purpose, COs often install information board where key information and announcements are placed.

Information boards in community organizations of Maryivka village, (Mykolaivska oblast) and the CO “Nadiya” (Luhanska oblast)

# 10.6	Donor/partner visits

# Regional/local-level visits were organized for donors/partners during the reporting period to familiarize them with the CBA process and results. Such visits also empower local communities and enhance their confidence to keep undertaking community activities together. Some of the events are as follows:

- On 9-10 August 2012 Ambassador Jose Manual Pinto Teixeira, Head of the EU Delegation to Ukraine and Mr. Olivier Adam, UN Resident Coordinator and UNDP Resident Representative paid a two-day working visit to Dnipropetrovska region to witness their efforts towards grass-roots democracy.

During the first day of the visit Mr. Adam and Mr. Pinto Teixeira together with the Oblast council Head Mr. Yevgen Udod met with community of Ordzhonikidze village, who carried out self-help initiatives on improvement of their living conditions under support of EU, UNDP and local / regional authorities.

In Ordzhonikidze village, the local community got organized created the community organization ‘Association “Nadiya”’ and initiated energy saving project in the kindergarten and school. On 10th August the diplomats visited ‘Petrykivska Beregynya’ – another pilot community supported by CBA project, and rayon community resource center in Petrykivske.

While interacting with the community members Mr. Teixeira expressed that CBA has succeeded in strengthening the democratic process in Ukrainian villages and has improved the living condition of the citizens. It has inspired the European Union to further support the Ukrainian people with additional resources to cover more communities." Mr. Adam, on this occasion, underlined that in its local development programmes, UNDP puts a strong emphasis on community self-empowerment, regeneration, building up the spirit of self-organization and social inclusion.

At the end of a two-day visit to Dnipropetrovsk region, the  delegate participated in the final working meeting with the Governor Mr. Alexander Vilkul and the Head of the Regional Council Mr. Yevgen Udod. On this occasion Mr. Udod explained that a systematic approach to cooperation between international foundations, oblast council and local communities has been implemented in Dnipropetrovska oblast within frameworks of Complex strategic program of region development. Mr. Vilkul appreciated the  support of EU and UNDP and opined, “common coordinated activity and implementation of cost-sharing principle are key factors that have contributed to increase life quality in towns and rayons of Dnipropetrovska oblast. This is a significant contribution to region development”.

Mr. Teixeira thanked the leaderships of the oblast and informed that CBA project is important for the European Union. It perfectly self-organizes people, teaches them to select priorities, mobilize efforts and successfully resolve common problems. We already see that the initiative has passed to regional authorities. We are encouraged for the achievements and would like to extend the project to third phase.

- On 23-24 August, UNDP Resident Representative Olivier Adam visited Zakarpatska oblast. Programme of the visit included meeting with the Governor, participation in OCC and LFD, visit to Rayon community resource centre and a visit to community. Mr. Olivier Adam participated in Oblast coordination council sitting, where 8 pilot rayons reported about results of micro-projects’ implementation.

UNDP Resident Representative Mr. Olivier Adam, met with the Governor of Zakarpatska oblast Mr. Oleksandr Ledyda, and participated in the oblast coordination council meeting

On 24th August, Mr. Adam participated in the sitting of Local development forum of Mukachivskyi rayon. He also visited community of Vyshkovo village and observed results of implementation of two micro-projects – energy saving and reconstruction of sewage system of the village healthpost.

Chapter Eleven

# The CBA Project is under the direct management of UNDP. UNDP ensures quality of management, resource utilization and timely achievement of results. Partners and donors independently monitor the implementation of the project, and regional/local authorities provide feedback for effective implementation of the initiative. The following actions took place during the reporting period in respect of project management:

# 11.1 Personnel Management

In the reporting period, Some of the old staff left during the work period while additional staff were recruited for new components of CBA-II. The newly recruited staff were provided with all necessary theoretical and practical training before commencing their duties. At the end of the year, the performance of all staff was evaluated and tenure for competent staff was extended for 2013.

# 11.2 Annual workplan

# The annual work plan for 2013 was prepared by the CBA Project were approved by UNDP management. Estimated budget for 2013 is US $ 8 million.

# 11.3 Procurement & Asset Management

# In the reporting period, equipment (e.g. laptops, photo cameras etc.), supplies (e.g. fuel for vehicles) and services (e.g. vehicle insurance) were procured. Purchase of equipment was for new staff as well as for replacement of old/worn-out equipment.

# 11.4 Steering Committee Meeting

# The second meeting of CBA Steering Committee took place on the 17th of October 2012 at the office of the Delegation of the European Union to Ukraine. Twenty four participants took part including representatives  from the relevant ministries, secretariat of cabinet of ministers, associations of local self-government bodies, union of agricultural service cooperatives, academia, regional state administration regional councils and donors (EU & UNDP) and CBA project (Annex - VIII).

# Prior to the meeting, representatives of the member agencies visited local community and rayon resource centre in Kyivska oblast to get a firsthand experience of CBA implementation. The visiting team was highly impressed by the results obtained by the joint action of citizens and the local authorities.

An official of CO in Kyivska oblast briefing the steering committee members regarding her CO

# The Meeting was chaired by Mr. Andrew Rasbash, the Head of Operations Section of the Delegation of the European Union to Ukraine and co-chaired by Ms. Ricarda Rieger, UNDP Country Director in Ukraine.

Mr. Rasbash praised the success of CBA-II implementation and underscored that the Project’s success has resulted in initiation of the 3rd phase of CBA with an increased budget of EUR 23 million. He recognised the existing high demand for CBA among communities as well as among the authorities and expressed that the EU would like to see the CBA methodology to be more widely replicated and used by the regional and local authorities. From this point of view, the Steering Committee meetings are of great importance as they bring together key stakeholders who may help facilitate the process of internalization of CBA methodology.

Ms. Ricarda Rieger, UNDP Country Director in Ukraine underscored the value of cooperation with the key national partners - Ministries, agencies and associations of local governments - as crucial for the work of UNDP and, in particular, for the CBA Project. In its implementation, CBA devotes a major effort to community development, but also pays attention to building viable partnerships with authorities of all levels in order to secure sustainability of results.

During the meeting the results of the Project pertaining to 2012 were shared. Difficulty in micro-project implementation and new opportunities (e.g. knowledge management hub) were highlighted. The Committee members appreciated the results and brought to attention the huge demand from the local population for CBA support. They proposed to link CBA with national resources and programmes (through synergy to obtain further scaling up). The members estimated and recognised KMH highly as a national resource centre for sustainable local development. UADRC was encouraged to intensify its activities in this direction. A need was expressed to build human resources and extend its networking to academia.

On the occasion the deputy governor of Zaporizhka oblast Mr. Petro Honcharuk shared the vision of the Zaporizhka regional authority on development of his oblast and underscored the indispensable role of CBA methodology in fulfilling the vision.

Mr. Vyacheslav Andronovych Negoda, Head of the territorial organization department of the government authorities and First Deputy Director of the department of coordination with Verkhovna Rada and the regions of Ukraine, Secretariat of the Cabinet of Ministers of Ukraine praised CBA achievements and characterized it as one of the best technical assistance projects currently operating in Ukraine. He noted that the high expectations from this Project were fulfilled and exceeded. The strength of CBA project lies in its systematic work and comprehensive methodology, as well as active and professional work of its team. The main value of the Project consists in going beyond solving problems of local infrastructure, towards uniting the efforts of the citizens and local governments and creating instruments for their permanent cooperation towards sustainable regional development.

In order to address the issues raised by CBA management regarding existing challenges in Project implementation, Mr. Negoda proposed to hold a working meeting to discuss the best solutions in participation of representatives of the relevant departments of the Ministry of Regional Development, the relevant committee of the Verhovna Rada and the Secretariat of Cabinet of Ministers.

# 11.5 Support to Preparation of CBA-III

# Support was provided to UNDP country office in context of preparation for third phase of the CBA Project. It involved supporting roundtable for stakeholder consultation and contributing towards preparation of draft project document.

# 11.6 Financial management

# During the reporting period, the project expenditure was € 5.3 million. Total expenditure since inception was € 8.3 million (48.5% of total budget). Itemwise details of expenditure is given in Table 25 below.

# Table 25. Project budget and expenditure by item, August 2012 – March 2013 (Euro ‘000)

| SN | Activity | Total Budget (Euro '000) | Expenditure Status During Aug12 - March 13 | Delivery until Jul12 | Total Cum. Delivery |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Total Expenditure | Committed | Total Delivery |  |  |
| 1 | Human resource | 3,511.3 | 860.9 | 0.0 | 860.9 | 1,139.1 | 1,999.9 |
| 2 | Travel | 92.2 | 8.6 | 0.0 | 8.6 | 13.3 | 21.9 |
| 3 | Equipment & supplies | 97.0 | 19.2 | 0.0 | 19.2 | 60.1 | 79.3 |
| 4 | Local office | 1,016.2 | 120.8 | 0.0 | 120.8 | 445.9 | 566.8 |
| 5 | Other costs & services | 265.2 | 21.0 | 0.0 | 21.0 | 99.8 | 120.8 |
| 6 | Others | 11,023.6 | 3,900.4 | 0.0 | 3,900.4 | 1,156.8 | 5,057.2 |
| a | Seed grant (social/communal) | 4,357.8 | 3,221.9 | 0.0 | 3,221.9 | 960.3 | 4,182.2 |
| c | Seed grant (energy efficiency) | 5,190.0 | 529.3 | 0.0 | 529.3 | 0.0 | 529.3 |
| d | Seed grant (small business) | 474.8 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 |
| e | Approach internalization | 367.5 | 2.0 | 0.0 | 2.0 | 0.0 | 2.0 |
| f | Curriculum development | 96.0 | 9.2 | 0.0 | 9.2 | 0.0 | 9.2 |
| g | Training/visits | 177.5 | 61.5 | 0.0 | 61.5 | 125.3 | 186.8 |
| h | LDF/RCC/Review meetings | 225.0 | 24.7 | 0.0 | 24.7 | 41.3 | 66.0 |
| i | Capacity of CRCs | 70.0 | 51.9 | 0.0 | 51.9 | 7.1 | 59.0 |
| j | Knowledge management | 65.0 | 0.0 | 0.0 | 0.0 | 22.8 | 22.8 |
| 7 | Contingency & Administrative | 1,120.4 | 365.1 | 0.0 | 365.1 | 173.8 | 538.8 |
|  | Total | 17,125.9 | 5,295.9 | 0.0 | 5,295.9 | 3,088.8 | 8,384.7 |

Annex I. Details of CBA-II activities by region (regular) – As of March 2013 since inception

| Oblast | Rayons selection | PA signed by rayons | Rayon seminars | VC/CC selection | VC/CC level seminar | PA signed by VC/CC | Community selection | CO Formation | LDF | RCC sittings | Training |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | # of rayon selected | CBA-I rayons | New rayons |  |  | # of VC/CC selected | CBA-I VC/CC | New VC/CC |  |  | Community selected | CBA-I communities | New communities | COs formed/grafted | COs enrolled at VC/CC | CO legally registered | Target HH | Participated HHs | Total Members | LDF grafted from CBA-I | New LDF formed | Total LDF | LDF sittings |  | Number of Training | CO-members (with repetition) | Authorities (with repetition) |
| ARC | 8 | 5 | 3 | 8 | 8 | 32 | 9 | 23 | 35 | 32 | 32 | 9 | 23 | 32 | 32 | 32 | 13734 | 12172 | 41637 | 5 | 3 | 8 | 17 | 3 | 63 | 1527 | 302 |
| Cherkaska | 9 | 3 | 6 | 9 | 9 | 39 | 3 | 36 | 39 | 39 | 39 | 4 | 35 | 39 | 39 | 39 | 11081 | 10753 | 12413 | 3 | 6 | 9 | 57 | 3 | 66 | 186 | 122 |
| Chernihivska | 6 | 3 | 3 | 6 | 6 | 25 | 3 | 22 | 25 | 25 | 25 | 3 | 22 | 25 | 25 | 25 | 13470 | 12122 | 26869 | 3 | 3 | 6 | 24 | 3 | 31 | 385 | 36 |
| Chernivetska | 6 | 6 | 0 | 6 | 6 | 24 | 6 | 18 | 24 | 24 | 24 | 5 | 19 | 24 | 24 | 24 | 19505 | 19324 | 19505 | 6 | 0 | 6 | 12 | 1 | 24 | 330 | 21 |
| Dnipropetrovska | 9 | 3 | 6 | 9 | 9 | 39 | 6 | 33 | 39 | 39 | 39 | 5 | 34 | 39 | 39 | 39 | 7030 | 4050 | 9838 | 3 | 6 | 9 | 32 | 2 | 48 | 575 | 166 |
| Donetska | 10 | 4 | 6 | 10 | 10 | 42 | 4 | 38 | 45 | 41 | 41 | 4 | 37 | 42 | 42 | 42 | 36173 | 31526 | 31921 | 4 | 6 | 10 | 32 | 1 | 70 | 1201 | 666 |
| I-Frankivska | 9 | 5 | 4 | 9 | 9 | 36 | 6 | 30 | 36 | 36 | 36 | 6 | 30 | 36 | 36 | 36 | 7320 | 5927 | 5936 | 5 | 4 | 9 | 32 | 3 | 84 | 833 | 184 |
| Kharkivska | 6 | 2 | 4 | 6 | 6 | 26 | 4 | 22 | 26 | 24 | 26 | 4 | 22 | 26 | 26 | 26 | 9922 | 8188 | 8555 | 2 | 4 | 6 | 42 | 2 | 24 | 316 | 46 |
| Khersonska | 8 | 4 | 4 | 8 | 8 | 32 | 7 | 25 | 32 | 32 | 32 | 7 | 25 | 32 | 32 | 32 | 6679 | 5583 | 15676 | 4 | 4 | 8 | 55 | 1 | 48 | 349 | 246 |
| Khmelnytska | 8 | 5 | 3 | 8 | 8 | 32 | 8 | 24 | 32 | 32 | 32 | 6 | 26 | 32 | 32 | 32 | 12771 | 10659 | 11382 | 5 | 3 | 8 | 42 | 2 | 46 | 378 | 131 |
| Kirovohradska | 8 | 4 | 4 | 8 | 8 | 33 | 8 | 25 | 35 | 33 | 33 | 8 | 25 | 33 | 33 | 33 | 8524 | 4992 | 13402 | 4 | 4 | 8 | 53 | 3 | 67 | 768 | 128 |
| Kyivska | 6 | 3 | 3 | 6 | 6 | 24 | 6 | 18 | 24 | 24 | 24 | 6 | 18 | 24 | 24 | 24 | 11768 | 9974 | 10020 | 3 | 3 | 6 | 37 | 1 | 49 | 959 | 255 |
| Luhanska | 9 | 3 | 6 | 9 | 9 | 37 | 5 | 32 | 37 | 37 | 37 | 5 | 32 | 37 | 37 | 37 | 21289 | 15285 | 21452 | 3 | 6 | 9 | 45 | 3 | 58 | 397 | 136 |
| Lvivska | 8 | 5 | 3 | 8 | 8 | 38 | 8 | 30 | 38 | 38 | 38 | 8 | 30 | 38 | 38 | 38 | 17418 | 11298 | 11682 | 5 | 3 | 8 | 32 | 4 | 48 | 1072 | 276 |
| Mykolaivska | 9 | 4 | 5 | 9 | 9 | 36 | 5 | 31 | 39 | 36 | 39 | 2 | 37 | 39 | 39 | 39 | 11633 | 7105 | 8460 | 4 | 5 | 9 | 41 | 2 | 47 | 678 | 151 |
| Odeska | 8 | 2 | 6 | 8 | 8 | 30 | 4 | 26 | 32 | 30 | 32 | 2 | 30 | 32 | 32 | 32 | 16823 | 16552 | 21289 | 2 | 6 | 8 | 32 | 5 | 51 | 545 | 146 |
| Poltavska | 8 | 3 | 5 | 8 | 8 | 33 | 8 | 25 | 33 | 33 | 33 | 7 | 26 | 33 | 33 | 33 | 13063 | 10805 | 28080 | 3 | 5 | 8 | 57 | 4 | 60 | 1006 | 340 |
| Rivnenska | 8 | 4 | 4 | 8 | 8 | 32 | 8 | 24 | 32 | 32 | 32 | 6 | 26 | 32 | 32 | 32 | 14357 | 12166 | 18431 | 4 | 4 | 8 | 72 | 2 | 50 | 1072 | 341 |
| Sumska | 9 | 5 | 4 | 9 | 9 | 38 | 10 | 28 | 40 | 38 | 38 | 9 | 29 | 38 | 38 | 38 | 10572 | 10062 | 10062 | 4 | 4 | 8 | 64 | 3 | 40 | 843 | 248 |
| Ternopilska | 9 | 5 | 4 | 9 | 9 | 37 | 5 | 32 | 38 | 38 | 37 | 5 | 32 | 37 | 37 | 37 | 10243 | 10052 | 32934 | 5 | 4 | 9 | 39 | 2 | 51 | 605 | 259 |
| Vinnytska | 6 | 4 | 2 | 6 | 6 | 29 | 8 | 21 | 11 | 30 | 29 | 7 | 22 | 29 | 29 | 29 | 25872 | 22315 | 26840 | 4 | 2 | 6 | 19 | 1 | 37 | 420 | 254 |
| Volynska | 9 | 5 | 4 | 9 | 9 | 41 | 7 | 34 | 42 | 42 | 41 | 7 | 34 | 41 | 41 | 41 | 9892 | 9892 | 21386 | 5 | 4 | 9 | 22 | 4 | 34 | 352 | 63 |
| Zakarpatska | 9 | 5 | 4 | 9 | 9 | 37 | 8 | 29 | 37 | 37 | 37 | 8 | 29 | 37 | 37 | 37 | 35815 | 29149 | 29230 | 5 | 4 | 9 | 46 | 3 | 65 | 1268 | 353 |
| Zaporizka | 9 | 5 | 4 | 9 | 9 | 36 | 12 | 24 | 36 | 37 | 37 | 18 | 19 | 37 | 37 | 37 | 2381 | 2199 | 9560 | 5 | 4 | 9 | 39 | 2 | 169 | 1725 | 441 |
| Zhytomyrska | 6 | 3 | 3 | 6 | 6 | 24 | 2 | 22 | 24 | 24 | 24 | 3 | 21 | 24 | 24 | 24 | 10010 | 5262 | 12220 | 3 | 3 | 6 | 19 | 1 | 28 | 320 | 115 |
| Total | 200 | 100 | 100 | 200 | 200 | 832 | 160 | 672 | 831 | 833 | 837 | 154 | 683 | 838 | 838 | 838 | 357345 | 297412 | 458780 | 100 | 100 | 200 | 962 | 61 | 1358 | 18110 | 5426 |

Annex I. Details of CBA-II activities by region (regular) …. continued

| Oblast | RCRC | 2nd dialogues | CDPs | # media events | # of media coverage | # Publications on partner websites | Info bulletin |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | RCRC grafted | New RCRC | Total |  | # of CDPs | CDPs approved VC/CC | # approved by LDF |  |  |  | # issue | # hard copies | # el. Copies |
| ARC | 5 | 3 | 8 | 32 | 32 | 32 | 32 | 12 | 145 | 103 | 24 | 695 | 35 |
| Cherkaska | 3 | 6 | 9 | 39 | 39 | 39 | 39 | 10 | 130 | 99 | 5 | 300 | 230 |
| Chernihivska | 3 | 3 | 6 | 25 | 25 | 25 | 25 | 9 | 30 | 26 | 6 | 133 | 138 |
| Chernivetska | 6 | 0 | 6 | 24 | 24 | 24 | 20 | 3 | 32 | 42 | 4 | 200 | 100 |
| Dnipropetrovska | 3 | 6 | 9 | 39 | 39 | 39 | 38 | 12 | 123 | 20 | 3 | 0 | 108 |
| Donetska | 4 | 6 | 10 | 41 | 40 | 38 | 38 | 12 | 66 | 50 | 0 | 0 | 0 |
| I-Frankivska | 5 | 4 | 9 | 36 | 36 | 36 | 36 | 12 | 265 | 60 | 10 | 1315 | 237 |
| Kharkivska | 2 | 4 | 6 | 30 | 26 | 24 | 24 | 10 | 46 | 31 | 4 | 200 | 5 |
| Khersonska | 4 | 4 | 8 | 32 | 32 | 32 | 32 | 16 | 70 | 49 | 1 | 100 | 100 |
| Khmelnytska | 5 | 3 | 8 | 32 | 32 | 32 | 32 | 11 | 125 | 123 | 4 | 820 | 86 |
| Kirovohradska | 4 | 4 | 8 | 33 | 33 | 33 | 33 | 24 | 140 | 44 | 3 | 350 | 350 |
| Kyivska | 3 | 3 | 6 | 33 | 24 | 24 | 24 | 120 | 208 | 80 | 18 | 2010 | 70 |
| Luhanska | 3 | 6 | 9 | 37 | 37 | 37 | 37 | 22 | 198 | 84 | 12 | 4930 | 212 |
| Lvivska | 5 | 3 | 8 | 30 | 37 | 37 | 30 | 14 | 138 | 81 | 5 | 1200 | 33 |
| Mykolaivska | 4 | 5 | 9 | 39 | 39 | 38 | 38 | 12 | 110 | 32 | 22 | 3370 | 798 |
| Odeska | 2 | 5 | 7 | 32 | 30 | 30 | 30 | 11 | 113 | 56 | 1 | 12 | 12 |
| Poltavska | 3 | 5 | 8 | 33 | 33 | 33 | 33 | 15 | 331 | 121 | 6 | 640 | 200 |
| Rivnenska | 4 | 4 | 8 | 32 | 32 | 32 | 32 | 32 | 389 | 125 | 15 | 936 | 680 |
| Sumska | 5 | 4 | 9 | 38 | 38 | 38 | 38 | 26 | 162 | 64 | 2 | 350 | 10 |
| Ternopilska | 5 | 4 | 9 | 37 | 37 | 37 | 36 | 11 | 101 | 90 | 10 | 349 | 304 |
| Vinnytska | 4 | 2 | 6 | 24 | 28 | 28 | 26 | 5 | 61 | 31 | 7 | 435 | 200 |
| Volynska | 5 | 4 | 9 | 41 | 45 | 41 | 41 | 12 | 109 | 40 | 5 | 136 | 223 |
| Zakarpatska | 5 | 4 | 9 | 37 | 37 | 37 | 37 | 18 | 97 | 58 | 5 | 1270 | 1270 |
| Zaporizka | 5 | 4 | 9 | 37 | 37 | 37 | 37 | 15 | 326 | 68 | 21 | 1278 | 169 |
| Zhytomyrska | 3 | 3 | 6 | 24 | 24 | 24 | 24 | 9 | 100 | 69 | 14 | 980 | 196 |
| Total | 100 | 100 | 200 | 837 | 836 | 827 | 812 | 453 | 3615 | 1646 | 207 | 21812 | 5763 |

Annex II. Details of CBA replication activities by region – as of March 2013 (since inception)

| Oblast | Allocated quota | Rayons selection | PA signed by rayons | Rayon seminars | VC/CC selection | VC/CC level seminar | PA signed by VC/CC | Community selection | CO Formation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | # of rayon selected | CBA-I rayons | New rayons |  |  | # of VC/CC selected | CBA-I VC/CC | New VC/CC |  |  | Community selected | CBA-I communities | New communities | COs formed/grafted | COs enrolled at VC/CC | CO legally registered | Target HH | Participated HHs | Total Members |
| ARC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Cherkaska | 4 | 4 | 2 | 2 | 4 | 4 | 16 | 5 | 11 | 16 | 16 | 16 | 5 | 11 | 16 | 16 | 16 | 4500 | 4050 | 4050 |
| Chernihivska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Chernivetska | 2 | 2 | 2 | 0 | 2 | 2 | 4 | 0 | 4 | 4 | 4 | 8 | 0 | 8 | 4 | 4 | 4 | 3367 | 3367 | 3367 |
| Dnipropetrovska | 4 | 4 | 1 | 3 | 4 | 4 | 18 | 1 | 17 | 18 | 18 | 18 | 1 | 17 | 18 | 18 | 18 | 5839 | 4762 | 9489 |
| Donetska | 2 | 1 | 1 | 0 | 1 | 1 | 8 | 1 | 7 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 5 | 1983 | 1692 | 1692 |
| I-Frankivska | 4 | 4 | 3 | 1 | 4 | 4 | 16 | 0 | 16 | 16 | 16 | 16 | 2 | 14 | 16 | 16 | 16 | 8506 | 6806 | 6806 |
| Kharkivska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Khersonska | 2 | 2 | 1 | 1 | 2 | 2 | 9 | 4 | 5 | 9 | 9 | 9 | 4 | 5 | 9 | 9 | 9 | 3844 | 2145 | 3506 |
| Khmelnytska | 2 | 2 | 0 | 2 | 2 | 2 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 4 | 4 | 4 | 0 | 0 | 0 |
| Kirovohradska | 4 | 4 | 1 | 3 | 4 | 4 | 17 | 2 | 15 | 17 | 17 | 16 | 2 | 14 | 3 | 3 | 3 | 2557 | 641 | 657 |
| Kyivska | 2 | 2 | 2 | 0 | 2 | 2 | 8 | 2 | 6 | 8 | 8 | 8 | 2 | 6 | 8 | 8 | 8 | 2290 | 2290 | 2290 |
| Luhanska | 4 | 4 | 2 | 2 | 4 | 4 | 16 | 5 | 11 | 16 | 16 | 16 | 4 | 12 | 16 | 16 | 16 | 7061 | 5681 | 8203 |
| Lvivska | 4 | 4 | 0 | 4 | 4 | 4 | 16 | 0 | 16 | 16 | 16 | 16 | 0 | 16 | 5 | 5 | 5 | 2088 | 1710 | 1710 |
| Mykolaivska | 3 | 3 | 0 | 3 | 3 | 4 | 12 | 0 | 12 | 12 | 12 | 12 | 0 | 12 | 12 | 12 | 12 | 4593 | 3782 | 3856 |
| Odeska | 3 | 3 | 2 | 1 | 1 | 3 | 12 | 6 | 6 | 12 | 11 | 12 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |
| Poltavska | 3 | 3 | 1 | 2 | 3 | 4 | 12 | 3 | 9 | 12 | 12 | 12 | 3 | 9 | 11 | 11 | 11 | 1950 | 1638 | 5150 |
| Rivnenska | 3 | 2 | 1 | 1 | 2 | 2 | 8 | 4 | 4 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 903 | 838 | 838 |
| Sumska | 3 | 2 | 2 | 0 | 2 | 2 | 8 | 6 | 2 | 9 | 8 | 8 | 6 | 2 | 8 | 8 | 8 | 1290 | 1247 | 1247 |
| Ternopilska | 4 | 4 | 2 | 2 | 4 | 3 | 16 | 2 | 14 | 17 | 17 | 17 | 2 | 15 | 18 | 18 | 18 | 4368 | 4112 | 5092 |
| Vinnytska | 0 | 2 | 0 | 2 | 1 | 1 | 8 | 0 | 8 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |
| Volynska | 4 | 4 | 2 | 2 | 4 | 4 | 16 | 4 | 12 | 16 | 16 | 16 | 4 | 12 | 16 | 12 | 12 | 1300 | 1257 | 1369 |
| Zakarpatska | 2 | 2 | 1 | 1 | 2 | 2 | 8 | 0 | 8 | 8 | 1 | 8 | 1 | 7 | 5 | 5 | 5 | 2220 | 1780 | 5688 |
| Zaporizka | 3 | 3 | 0 | 3 | 3 | 3 | 12 | 0 | 12 | 12 | 12 | 12 | 0 | 12 | 12 | 12 | 12 | 1350 | 970 | 1840 |
| Zhytomyrska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total | 62 | 61 | 26 | 35 | 58 | 61 | 248 | 45 | 203 | 242 | 233 | 248 | 44 | 204 | 193 | 189 | 186 | 60009 | 48768 | 66850 |

Annex II. Details of CBA replication activities by region ……. continued

| Oblast | LDF | Training | RCRC | CDPs |
| --- | --- | --- | --- | --- |
|  | LDF grafted from CBA-I | New LDF formed | Total LDF | LDF sittings | Number of Training | CO-members (with repetition) | Authorities (with repetition) | RCRC grafted | New RCRC | Total | # of CDPs | CDPs approved at VC/CC | CDPs approved at LDFs |
| ARC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Cherkaska | 2 | 2 | 4 | 24 | 28 | 71 | 29 | 2 | 2 | 4 | 16 | 16 | 16 |
| Chernihivska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Chernivetska | 0 | 2 | 2 | 2 | 4 | 10 | 13 | 0 | 0 | 0 | 8 | 8 | 8 |
| Dnipropetrovska | 1 | 3 | 4 | 8 | 12 | 68 | 26 | 1 | 3 | 4 | 18 | 18 | 18 |
| Donetska | 1 | 0 | 1 | 4 | 7 | 112 | 33 | 1 | 0 | 1 | 5 | 5 | 5 |
| I-Frankivska | 3 | 1 | 4 | 8 | 12 | 96 | 4 | 3 | 1 | 4 | 9 | 9 | 9 |
| Kharkivska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Khersonska | 0 | 1 | 1 | 4 | 12 | 93 | 77 | 1 | 1 | 2 | 9 | 9 | 9 |
| Khmelnytska | 0 | 1 | 1 | 1 | 5 | 40 | 27 | 0 | 1 | 1 | 4 | 4 | 0 |
| Kirovohradska | 1 | 3 | 4 | 12 | 19 | 235 | 49 | 1 | 3 | 4 | 16 | 16 | 16 |
| Kyivska | 2 | 0 | 2 | 10 | 11 | 161 | 28 | 2 | 0 | 2 | 8 | 8 | 8 |
| Luhanska | 2 | 2 | 4 | 16 | 24 | 109 | 28 | 2 | 2 | 4 | 16 | 16 | 16 |
| Lvivska | 0 | 4 | 4 | 6 | 11 | 96 | 82 | 0 | 4 | 4 | 2 | 2 | 2 |
| Mykolaivska | 0 | 3 | 3 | 8 | 9 | 193 | 24 | 0 | 3 | 3 | 12 | 12 | 12 |
| Odeska | 2 | 0 | 2 | 2 | 12 | 65 | 19 | 2 | 0 | 2 | 1 | 1 | 1 |
| Poltavska | 1 | 2 | 3 | 6 | 15 | 259 | 81 | 3 | 1 | 4 | 6 | 5 | 1 |
| Rivnenska | 2 | 1 | 3 | 10 | 12 | 182 | 42 | 2 | 1 | 3 | 3 | 0 | 0 |
| Sumska | 3 | 0 | 3 | 12 | 3 | 64 | 11 | 3 | 0 | 3 | 8 | 8 | 8 |
| Ternopilska | 2 | 1 | 3 | 14 | 14 | 147 | 66 | 1 | 1 | 2 | 13 | 12 | 10 |
| Vinnytska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Volynska | 0 | 0 | 0 | 0 | 11 | 91 | 36 | 2 | 2 | 4 | 20 | 20 | 0 |
| Zakarpatska | 1 | 1 | 2 | 6 | 6 | 108 | 18 | 1 | 1 | 2 | 9 | 7 | 3 |
| Zaporizka | 0 | 3 | 3 | 13 | 36 | 735 | 333 | 0 | 3 | 3 | 12 | 12 | 12 |
| Zhytomyrska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total | 23 | 30 | 53 | 166 | 263 | 2935 | 1026 | 27 | 29 | 56 | 195 | 188 | 154 |

Annex – III

List of Winners of RCRC Competition

| SN | Oblast/Rayon | SN | Oblast/Rayon | SN | Oblast/Rayon |
| --- | --- | --- | --- | --- | --- |
|  | 1. Volynska |  | 10. Chernivetska |  | 19. Kirovogradska |
| 1 | Ratnivskyi | 27 | Sokyrianskyi | 52 | Novomyrgorodskyi |
| 2 | Kivertsivskyi | 28 | Zastavnivskyi | 53 | Hayvoronskyi |
| 3 | Liubomylskyi | 29 | Hertsaivskyi | 54 | Novoukrayinskyi |
| 4 | Ivanychivskyi |  | 11. Rivnenska |  | 20. Kyivska |
|  | 2. Lvivska | 30 | Dubenskyi | 55 | Skvyrskyi |
| 5 | Sambirskyi | 31 | Kostopilskyi | 56 | Baryshevskyi |
| 6 | Starosambirskyi | 32 | Radyvylivskyi | 57 | Tarashanskyi |
|  | 3. Khmelnytska |  | 12. Zhytomyrska |  | 21. Luganska |
| 7 | Iziaslavskyi | 33 | Korostyshivskyi | 58 | Popasnyanskyi |
| 8 | Novoushytskyi | 34 | Olevskyi | 59 | Novopskovskyi |
|  | 4. Chernihivska |  | 13. ARC | 60 | Novoaydarskyi (replication) |
| 9 | Shchorskyi | 35 | Pervomayskyi | 61 | Svativskyi |
| 10 | Chernihivskyi | 36 | Sakskyi | 62 | Perevalskyi (replication) |
|  | 5. Vinnytska |  |  |  | 22. Mykolayivska |
| 11 | Teplytskyi |  | 14. Cherkaska | 63 | Berezneguvatskyi |
| 12 | Kmilnytskyi | 37 | Smilyanskyi | 64 | Voznesenskyi |
|  | 6. Ivano-Frankivska | 38 | Mankivskyi | 65 | Bashtanskyi |
| 13 | Tlumatskyi | 39 | Drabivskyi |  | 23. Poltavska |
| 14 | Kolomyiskyi | 40 | Umanskyi | 66 | Lohvytskyi |
| 15 | Kosivskyi |  | 15. Dnipropetrovska | 67 | Gadyachskyi |
| 16 | Tysmenytskyi | 41 | Tomakivskyi | 68 | Chutivskyi |
|  | 7. Sumska | 42 | Apostolovskyi |  | 24. Zaporizka |
| 17 | Velykopysarivskyi | 43 | Verhnyodniprovskyi | 69 | Hulaypilskyi |
| 18 | Trostianetskyi | 44 | Petrykivskyi (replication) | 70 | Veselivskyi |
| 19 | Hlukhivskyi | 45 | Kryvorizhskyi (replication) | 71 | Orihivskyi |
|  | 8. Ternopilska |  | 16. Donetska |  | 25. Odeska |
| 20 | Kozivskyi | 46 | Artemivskyi | 72 | Ivanivskyi |
| 21 | Shumskyi | 47 | Kostyantynivskyi | 73 | Bolgradskyi |
| 22 | Zborivskyi |  | 17. Kharkivska |  |  |
| 23 | Kremenetskyi | 48 | Borivskyi |  |  |
|  | 9. Zakarpatska | 49 | Velykoburlutskyi |  |  |
| 24 | Svaliavskyi |  | 18. Khersonska |  |  |
| 25 | Mukachivskyi | 50 | Novotroitskyi |  |  |
| 26 | Uzhgorodskyi | 51 | Velykooleksandrivskyi |  |  |

Annex – IV (A). Micro-projects (standard): Regular rayons - status as of March 2013 (since inception)

|  | MPPs Approved by CBA | Cost Sharing of Approved MPs ( thousands, UAH) | Beneficiary Population (thousands) | Beneficiary Institution |
| --- | --- | --- | --- | --- |
|  |  | COs | VC/CC | Rayon Authority | Regional Authority | Private sector | CBA | Total | Total | Male | Female | Hospitals | Schools/kindergartens | Community |
| ARC | 28 | 354901 | 1137321 | 1097651 | 161229 | 30764 | 2123936 | 4905802 | 37.974 | 17.805 | 20.169 | 3 | 22 | 3 |
| Cherkaska | 28 | 228204 | 716190 | 326185 | 125232 | 166058 | 1908858 | 3470727 | 27.285 | 12.633 | 14.652 | 11 | 15 | 2 |
| Chernihivska | 19 | 360755 | 54424 | 1665475 | 0 | 0 | 1424845 | 3505499 | 5.591 | 2.503 | 3.088 | 3 | 13 | 3 |
| Chernivetska | 19 | 179132 | 47976 | 1024244 | 0 | 0 | 1077480 | 2328832 | 44.221 | 20.585 | 23.636 | 13 | 5 | 1 |
| Dnipropetrovska | 27 | 276542 | 866035 | 863705 | 944796 | 103005 | 2224439 | 5278522 | 39.416 | 18.122 | 21.294 | 2 | 24 | 1 |
| Donetska | 40 | 340116 | 1401496 | 1739652 | 0 | 50000 | 3102445 | 6633709 | 77.782 | 35.704 | 42.078 | 6 | 29 | 5 |
| I-Frankivska | 31 | 352246 | 165684 | 2466331 | 0 | 0 | 2377002 | 5361263 | 45.344 | 19.254 | 26.09 | 5 | 24 | 2 |
| Kharkivska | 22 | 232827 | 368668 | 1140812 | 0 | 34157 | 1490008 | 3266472 | 20.534 | 10.204 | 10.33 | 4 | 15 | 3 |
| Khersonska | 28 | 250833 | 1313679 | 742178 | 0 | 0 | 2161039 | 4467729 | 22.67 | 10.207 | 12.463 | 2 | 17 | 9 |
| Khmelnytska | 26 | 506346 | 352324 | 2628050 | 0 | 251670 | 2013634 | 5752024 | 18.145 | 8.168 | 9.977 | 2 | 22 | 2 |
| Kirovohradska | 34 | 355910 | 765858 | 1619400 | 0 | 262179 | 2542997 | 5546344 | 45.922 | 20.308 | 25.614 | 2 | 30 | 2 |
| Kyivska | 21 | 190710 | 262967 | 1392859 | 0 | 206875 | 1684877 | 3738288 | 18.716 | 8.446 | 10.27 | 5 | 16 | 0 |
| Luhanska | 33 | 447236 | 289459 | 3992193 | 0 | 134187 | 2486236 | 7349311 | 40.555 | 18.906 | 21.649 | 8 | 23 | 2 |
| Lvivska | 35 | 341140 | 724576 | 2284705 | 34000 | 43000 | 2284837 | 5712258 | 38.246 | 17.218 | 21.028 | 2 | 31 | 2 |
| Mykolaivska | 36 | 668977 | 814770 | 1988767 | 0 | 41688 | 2904136 | 6418338 | 38.92 | 17.524 | 21.396 | 1 | 24 | 11 |
| Odeska | 26 | 333490 | 580816 | 1370273 | 0 | 0 | 2042723 | 4327302 | 38.171 | 16.934 | 21.237 | 4 | 17 | 5 |
| Poltavska | 26 | 292871 | 197623 | 1317625 | 1178163 | 26170 | 2024271 | 5036723 | 19.62 | 9.024 | 10.596 | 1 | 17 | 8 |
| Rivnenska | 30 | 339288 | 314488 | 2521108 | 0 | 0 | 2194834 | 5369718 | 34.655 | 16.359 | 18.296 | 5 | 21 | 4 |
| Sumska | 32 | 1487602 | 1666448 | 1011756 | 326386 | 28464 | 2321000 | 6784738 | 14.344 | 6.342 | 8.002 | 2 | 11 | 19 |
| Ternopilska | 30 | 591298 | 58212 | 2223177 | 0 | 103841 | 2371385 | 5347913 | 22.8 | 10.969 | 11.831 | 2 | 26 | 2 |
| Vinnytska | 7 | 53322 | 130180 | 327048 | 0 | 90876 | 401360 | 1002786 | 4.393 | 1.85 | 2.543 | 0 | 5 | 2 |
| Volynska | 36 | 342265 | 306100 | 1829158 | 726800 | 0 | 2493740 | 5698063 | 19.945 | 8.889 | 11.056 | 9 | 26 | 1 |
| Zakarpatska | 31 | 381721 | 1168725 | 2105852 | 0 | 68617 | 2339790 | 6064705 | 53.724 | 25.38 | 28.344 | 5 | 22 | 4 |
| Zaporizka | 19 | 248789 | 498239 | 1055061 | 0 | 306738 | 1514564 | 3623391 | 29.952 | 13.673 | 16.279 | 2 | 11 | 6 |
| Zhytomyrska | 10 | 99258 | 20819 | 1004626 | 0 | 0 | 791870 | 1874935 | 6.764 | 3.098 | 3.666 | 2 | 5 | 3 |
| Total | 674 | 9255779 | 14223077 | 39737891 | 3496606 | 1948289 | 50302306 | 118865392 | 748.847 | 343.526 | 405.321 | 101 | 471 | 102 |

Annex – IV (B). Micro-projects (standard): Replication rayons - status as of March 2013 (since inception)

| Region | Approved MPPs | Total Budget | CO | VC/CC | Rayon | Oblast | Private | CBA | Beneficiary Population | Male | Female | School/Kindergarten | Community | Healthpost | Beneficiary Institutions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ARC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Cherkaska | 8 | 811882 | 51286 | 378437 | 149110 | 58407 | 17000 | 157642 | 11212 | 5086 | 6126 | 5 | 0 | 3 | 8 |
| Cherniviska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Chernivetska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Dnipropetrovska | 14 | 1772183 | 114102 | 487700 | 168339 | 726257 | 0 | 275785 | 18006 | 8297 | 9709 | 12 | 1 | 1 | 14 |
| Donetska | 6 | 378430 | 18921 | 208376 | 75448 | 0 | 0 | 75685 | 5735 | 2608 | 3127 | 5 | 1 | 0 | 6 |
| Ivano-Frankivska | 6 | 751348 | 87250 | 0 | 493652 | 60000 | 0 | 110446 | 7879 | 3693 | 4186 | 4 | 2 | 0 | 6 |
| Kharkivska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Khersonska | 5 | 428200 | 33000 | 0 | 312000 | 0 | 0 | 83200 | 8044 | 3746 | 4298 | 5 | 0 | 0 | 5 |
| Khmelnitska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Kirovogradska | 1 | 127670 | 6475 | 60000 | 40000 | 0 | 0 | 21195 | 792 | 317 | 475 | 1 | 0 | 0 | 1 |
| Kyivska | 4 | 300717 | 15434 | 0 | 225412 | 0 | 0 | 59871 | 2872 | 1234 | 1638 | 3 | 1 | 0 | 4 |
| Luhanska | 12 | 1838496 | 127119 | 260985 | 1209662 | 0 | 0 | 240730 | 10960 | 5121 | 5839 | 6 | 3 | 3 | 12 |
| Lvivska | 1 | 82174 | 4647 | 0 | 27130 | 34000 | 0 | 16397 | 463 | 209 | 254 | 0 | 0 | 1 | 1 |
| Mykolaivska | 3 | 516822 | 26567 | 12026 | 415240 | 0 | 0 | 62989 | 4299 | 1999 | 2300 | 0 | 2 | 1 | 3 |
| Odeska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Poltavska | 2 | 259664 | 12976 | 35000 | 99066 | 71722 | 0 | 40900 | 2618 | 1177 | 1441 | 1 | 0 | 1 | 2 |
| Rivnenska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Sumska | 3 | 402872 | 20340 | 128961 | 159090 | 32004 | 0 | 62477 | 1767 | 824 | 943 | 2 | 1 | 0 | 3 |
| Ternopilska | 11 | 1265310 | 157300 | 11830 | 697034 | 0 | 109384 | 289762 | 10460 | 5096 | 5364 | 9 | 0 | 2 | 11 |
| Vinnytska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Volynska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Zakarpatska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Zaporizka | 6 | 567738 | 40884 | 156147 | 264732 | 0 | 0 | 105975 | 6448 | 2729 | 3719 | 3 | 2 | 1 | 6 |
| Zhytomyrska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Sub-Total | 82 | 9503506 | 716301 | 1739462 | 4335915 | 982390 | 126384 | 1603054 | 91555 | 42136 | 49419 | 56 | 13 | 13 | 82 |

Annex - V. Micro-projects (energy efficiency) - status as of March 2013 (since inception)

- Regular rayons

| Region | Approved MPPs | CO | VC/CC | Rayon | Oblast | Private | CBA | Total Budget | Beneficiary Population | Male | Female | Healthpost | School/Kindergarten | Community |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ARC | 4 | 33160 | 155236 | 136739 | 0 | 0 | 276368 | 601503 | 5.74 | 2.63 | 3.11 | 0 | 0 | 4 |
| Cherkaska | 11 | 145612 | 854616 | 267254 | 123146 | 229505 | 925139 | 2545272 | 14.92 | 6.94 | 7.99 | 0 | 3 | 8 |
| Cherniviska | 5 | 43018 | 50476 | 358442 | 0 | 0 | 402846 | 854782 | 13.81 | 6.70 | 7.11 | 1 | 1 | 3 |
| Chernivetska | 3 | 23358 | 2500 | 193548 | 0 | 0 | 199881 | 419287 | 1.48 | 0.72 | 0.76 | 1 | 0 | 2 |
| Dnipropetrovska | 12 | 61122 | 169570 | 191505 | 246767 | 12736 | 535082 | 1216782 | 7.24 | 3.37 | 3.88 | 0 | 0 | 12 |
| Donetska | 3 | 36292 | 211622 | 0 | 0 | 88000 | 234727 | 570641 | 9.27 | 4.32 | 4.96 | 0 | 2 | 1 |
| Ivano-Frankivska | 6 | 54693 | 26000 | 506965 | 0 | 0 | 475402 | 1063060 | 6.06 | 2.95 | 3.11 | 1 | 3 | 2 |
| Kharkivska | 4 | 34680 | 301421 | 0 | 0 | 0 | 311055 | 647156 | 3.73 | 1.76 | 1.97 | 0 | 1 | 3 |
| Khersonska | 4 | 41835 | 304385 | 85000 | 0 | 0 | 319200 | 750420 | 2.88 | 1.32 | 1.56 | 0 | 4 | 0 |
| Khmelnitska | 5 | 57810 | 0 | 369905 | 0 | 21965 | 394403 | 844083 | 3.97 | 1.74 | 2.23 | 0 | 2 | 3 |
| Kirovogradska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 0 | 0 | 0 |
| Kyivska | 3 | 27287 | 65000 | 212487 | 0 | 0 | 240900 | 545674 | 1.95 | 0.89 | 1.06 | 1 | 1 | 1 |
| Luhanska | 4 | 33267 | 70181 | 229457 | 0 | 0 | 314589 | 647494 | 5.39 | 2.30 | 3.10 | 0 | 0 | 4 |
| Lvivska | 3 | 19618 | 1500 | 170758 | 0 | 0 | 187036 | 378912 | 2.58 | 1.34 | 1.24 | 0 | 0 | 3 |
| Mykolaivska | 1 | 8572 | 42000 | 30000 | 0 | 0 | 80000 | 160572 | 1.14 | 0.61 | 0.53 | 0 | 0 | 1 |
| Odeska | 4 | 53391 | 282411 | 125600 | 0 | 0 | 320181 | 781583 | 11.10 | 5.19 | 5.92 | 0 | 0 | 4 |
| Poltavska | 7 | 80975 | 132983 | 331764 | 290169 | 0 | 488244 | 1324135 | 8.46 | 3.75 | 4.71 | 0 | 1 | 6 |
| Rivnenska | 4 | 41402 | 5000 | 286939 | 0 | 0 | 319254 | 652595 | 3.73 | 1.81 | 1.92 | 0 | 3 | 1 |
| Sumska | 5 | 36678 | 231153 | 74943 | 5555 | 28454 | 313397 | 690180 | 2.33 | 1.08 | 1.25 | 1 | 0 | 4 |
| Ternopilska | 5 | 42403 | 48597 | 295849 | 0 | 0 | 374099 | 760948 | 3.87 | 1.72 | 2.15 | 1 | 4 | 0 |
| Vinnytska | 11 | 94664 | 217059 | 736395 | 0 | 49160 | 712715 | 1809993 | 4.83 | 2.28 | 2.55 | 1 | 5 | 5 |
| Volynska | 4 | 33870 | 48075 | 138200 | 104650 | 0 | 307340 | 632135 | 1.81 | 0.69 | 1.12 | 0 | 3 | 1 |
| Zakarpatska | 5 | 47966 | 276079 | 243918 | 0 | 0 | 371114 | 939077 | 4.17 | 1.97 | 2.20 | 0 | 3 | 2 |
| Zaporizka | 14 | 166814 | 308855 | 541524 | 35500 | 114052 | 1051596 | 2218341 | 18.05 | 8.13 | 9.93 | 0 | 0 | 14 |
| Zhytomyrska | 3 | 27552 | 279952 | 0 | 0 | 0 | 238868 | 546372 | 1.07 | 0.48 | 0.59 | 2 | 1 | 0 |
| Total | 130 | 1246039 | 4084671 | 5527192 | 805787 | 543872 | 9393436 | 21600997 | 139.585 | 64.66 | 74.926 | 9 | 37 | 84 |

- Replication rayons

| Region | Approved MPPs | Total Budget | CO | VC/CC | Rayon | Oblast | Private | CBA | Beneficiary Population | Male | Female | School/Kindergarten | Community | Healthpost | Beneficiary Institutions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cherkaska | 8 | 909366 | 50518 | 494012 | 87000 | 61873 | 50650 | 165313 | 4958 | 2373 | 2585 | 3 | 5 |  | 8 |
| Dnipropetrovska | 2 | 235684 | 14413 | 68356 | 61500 | 50000 |  | 41415 | 1953 | 905 | 1048 |  | 2 |  | 2 |
| Luhanska | 1 | 98703.00 | 5000.00 | 30017.00 | 43949.00 |  |  | 19737 | 862 | 387 | 475 |  | 1 |  | 1 |
| Poltavska | 4 | 594480 | 29777 | 142851 | 233501 | 109500 |  | 78851 | 2532 | 1190 | 1342 |  | 4 |  | 4 |
| Sub-Total | 15 | 1838233 | 99708 | 735236 | 425950 | 221373 | 50650 | 305316 | 10305 | 4855 | 5450 | 3 | 12 |  | 15 |

Annex –  VI

List of Partner Universities

| # | Oblast | University |
| --- | --- | --- |
| 1 | Cherkaska | Cherkasy State Technological University |
| 2 | Chernihivska | Chernihiv State Technological Univeristy |
| 3 | Dnipropetrovska | Dnipropetrovsk National University of Railway Transport Named After Academician V. Lazayan |
| 4 | Donetska | Donetsk State University of Management |
| 5 | Kharkivska | Kharkiv National Academy of Municipal Economy |
| 6 | Kharkivska | Kharkiv National Economic University |
| 7 | Khersonska | Kherson State Agricultural University |
| 8 | Khmelnytska | Khmelnytskyi University of Management and Law |
| 9 | Kirovohradska | Kirovohrad National Technical University |
| 10 | Kirovohradska | Kirovohrad Institute of Human Development of the Open International University of Human Development “Ukraine” |
| 11 | Kyivska | State Higher Educational Establishment ‘Vadym Hetman Kyiv National Economic University’ |
| 12 | Luhanska | Volodymyr Dahl East Ukrainian National University |
| 13 | Lvivska | Lviv Polytechnic National University Institute of Humanities and Social Sciences |
| 14 | Mykolaivska | Mykolaiv State Agrarian University |
| 15 | Poltavska | Poltava State Agrarian Academy |
| 16 | Rinvenska | University of International RelationsInternational University of Economics and Humanities named after Academicial Stepan Demyanchuk |
| 17 | Rivnenska | National University of Ostog Academy |
| 18 | Sumska | Sumy State Univeristy |
| 19 | Zakarpatska | Uzhgorod National University |
| 20 | Zaporizka | Tavria State Agrotechnological Univeristy |

Annex –  VII

Summary of the Report on Impact of CBA-I

Background

The world level experience on the activation of the rural communities for rural development is incorporated in the organizational and financial mechanism of CBA Project. The Project can be considered as an initial incitement for certain positive changes in the social and economic indicators and social capital characteristics in Ukrainian rural communities. The communities were selected based on social and economic indicators and reflect rayon, village councils and villages.  First phase of CBA Project lasted in Ukraine over December 2007 – June 2011. During this period, the Project supported over 1000 Ukrainian communities, across the country, in improving their living conditions through such tools as social mobilisation, training and small grants. Social mobilisation was expected to promote social capital characteristics. Training intended to enhance knowledge and skill among the target population. Small grant aimed to promote joint implementation of micro-project leading to increase in cooperation between communities and local authorities; increase in local economic growth; and improvement in living condition.  Small grant is based on cost sharing from communities, local authorities and CBA project in a mechanism that reflects commitment, transparency and accountability. First phase of CBA had budget of €13.5 million (0.002% Ukraine’s GDP in 2007). Second phase of CBA started in June 2011 with €17 million (0.086% of Ukraine’s GDP in 2011). The project is one of the most large-scale project of economic cooperation and social mobilisation of rural community members in the history of Ukrainian independence.

The project observed a set of socio-economic criteria for selection of district, village councils and villages (communities) for support e.g. poverty, level of services in such basic sectors as water supply, health, energy, environment (waste disposal, sanitation etc.), school transportation and level of commitment etc.  The districts/village councils/communities that reflected dire situation were eligible for participation in the programme.

In Sumska oblast has 18 districts with 183 villages. In first phase, CBA covered 8 districts, 42 village councils and 46 villages. Rest of them either did not apply or were not selected. During 2nd phase, 10 districts and 46 village councils were selected for participation in the programme. Among them, 15 belonged to CBA-I and 31 were new.  Historically and culturally, Sumska oblast can be divided into two regions– districts in northern region have are rich in collectivism and districts in southern regions have more of individualistic nature.

Objective

It was hypothesized that the communities which have benefited from the participation in the first phase of CBA reveal better socio-economic indicators of development than the ones which have not yet benefited from such participation. It was also hypothesized that the positive changes in the level of social capital of those communities which have benefited from the participation in CBA are expected to be one of the reasons underlying the stated difference in socio-economic indicators. Positive changes in the level of social capital should occur due to organisational and financial mechanism of CBA. Objective of this study is to test these hypotheses.

Methodology

All the 46 villages that participated in CBA-I were considered as intervention group whereas the villages which were similar to intervention villages in terms of observables but did not participate in CBA-I are considered as comparison group. Information collected from the comparison group will allow to estimate counterfactual information i.e. “what would happen to the beneficiaries had they not been included in CBA project?”

For analysis of the impact on social capital characteristics, 33 villages participated in CBA-I for which data were collected from intervention group. Pipeline matching methodology was used to analyse CBA’s impact on social capital characteristics. Accordingly, 31 communities which were assigned to participate in CBA-II but were not a part of CBA-I, form the comparison group.

Data on social-economic indicators pertaining to intervention and comparison groups were availed from ‘conditioning of Sumy region villages 2011’ relevant to 2005-10 period. The indicators included (a) village population size; (b) No. of households; (c) bus connection (No. of trips/day); (d) No. of streets in the village; (e) No. of people who left village/capita; (f) No. of people occupied at all sectors/capita; (g) No. of people occupied out of village/capita; (h) No. people died per year per capita; (i) No. of people occupied at entrepreneurial sector/capita; (j) No. of seats at school and kindergartens; (k) No. of health post visits.

Data on social capital characteristics were obtained through survey at the end of 2011 and beginning of 2012 for both intervention and comparison communities. Questionnaire to measure level of social capital characteristics was designed based on the ones used by the World Bank, European Social Survey and social capital question bank. 9 characteristics were used in the questionnaire namely, (a)  traditions of the community, (b) information and communication, (c) empowerment and political action, (d) (anti-)paternalism, (e) level of trust, (f) solidarity and inclusion, (f) general norms, (g) collective action and cooperation, and (h) general characteristics of the community (e.g. propensity to migrate, employment conditions, safety and others).

For social capital survey, 960 households (10% of the total) were interviewed using systematic sampling technique.

Percentage and regression analysis tools were used to analyze the information and derive inferences.

Findings

Followings were the key findings as revealed by the analysis of the survey information and secondary data. The findings confirm the hypotheses of the study. Result of percentage analysis and regression analysis were found to be consistent.

On socio-economic characteristics

- Village population in intervention group declined at a lower rate than in comparison group (10% significance level);

- No. of people occupied at all sector/capita in intervention group increased in comparison to comparison group (5% level of significance);

- Lower number of people in intervention community started to work out of the village compared to comparison community (5% level of significance);

- Growth rate of number of people occupying entrepreneurial sector was higher in intervention community than in comparison community (10% level of significance);

- Growth rate of bus connection was higher in intervention community than in comparison community (5% level of significance);

- Growth rate of number of seats in schools and kindergartens was higher in intervention community than in comparison community (1% level of significance);

On social capital characteristics

It was expected that participation of the communities in CBA programme will lead to transition of social capital and the willingness of the people to help themselves – from passive to active state. Followings changes were observed in the level of social capital characteristics:

- Traditions of community in the intervention group was higher than in comparison group (0.1% level of significance);

- Average value of information and communication in the intervention group was higher than in comparison group (5% level of significance);

- Average value of empowerment and political action was higher in intervention group than in comparison group (0.1% level of significance);

- Average value of (anti-)paternalism was higher in intervention group than in comparison group (1% level of significance);

- Average value of level of trust was higher in intervention group than in comparison group (1% level of significance);

- Average value of solidarity and inclusion was higher in intervention group than in comparison group (10% level of significance);

- Average value of collective action and cooperation was higher in intervention group than in comparison group (0.1% level of significance);

- Average value of general characteristics was higher in intervention group than in comparison group (1% level of significance);

It was noted that the change in the level of trust between intervention group and comparison group was positive but small. Regression analysis showed positive change in 8 of 9 characteristics. Level of trust over 5 year period deceased (in CBA-I community) to a bigger extent compared to new communities in CBA-II which had not received benefit yet. This situation was explained with the fact that the participation in economic cooperation and social mobilisation programmes not only improves community members’ awareness about the community and local authority activities, but also broadens the community members’ thinking. Community members’ argumentation during decision-making process changes qualitatively. As a result, the members of CBA-I communities took more factors into account while answering the survey questions. They assessed the reality objectively that could lower the trust level as a social capital characteristic.

On spatial characteristics

CBA-I districts in the northern region of Sumska oblast showed significantly higher socio-economic impact in compared to CBA-I districts in the southern region. They appeared to be more receptive and were easily trained to adopt new organisational and financial mechanism of CBA. They did it effectively and faster. They bear high propensity to economic cooperation and social mobilisation. This difference was explained by the cultural and historical features namely collectivism versus individualism.

Annex –  VIII

Participants of Steering Committee Meeting

- Member Institutions

| SN | Institution | Representative | Designation |
| --- | --- | --- | --- |
|  | Delegation of the European Union to Ukraine | Mr Andrew RASBASH | Head of Operations / Coordinator for Cooperation |
|  | United Nations Development Programme | Ms Ricarda RIEGER | Country Director |
|  | Secretariat of the Cabinet of Ministers of Ukraine | Mr Vyacheslav NEHODA | First Deputy Head of Department of Cooperation with Verkhovna Rada and the Regions, CBA Coordinator from SCMU |
|  | Ministry of Education and Science, Youth and Sport of Ukraine | Mr Andriy BOZHKOV | Head of the Department of International Cooperation |
|  | Ministry of Regional Development, Construction and Housing of Ukraine | Mr Samvel ARUSTAMIAN | Main Specialist of the Department of Inter-Regional and International Cooperation |
|  | Ministry of Energy and Coal of Ukraine | Ms Svitlana HRYTSAI | Main Specialist of the Department of European Integration and International Cooperation |
|  | Ministry of Agricultural Policy of Ukraine | Ms Liudmyla STAVNYCHA | Deputy Head of Department of Scientific Support to Agricultural Development and Rural Development |
|  | Ministry of Healthcare Protection of Ukraine | Mr Vyacheslav YEVTUSHENKO | Head of Department of Healthcare Reform |
|  | State Agency on Energy Efficiency and Energy Conservation of Ukraine | Ms Tetyana PUGACHOVA | Head of Department of Communications |
|  | Foundation for Local Self-government under President of Ukraine | Mr Dmytro LOSYEV | Deputy Head |
|  | Foundation for Local Self-government under President of Ukraine | Mr Andriy HUK | Deputy Head of Department of International Cooperation and Communication |
|  | Ukrainian Association of Rayon and Oblast Councils | Mr Yuriy ANDRIYCHUK | Head of Secretariat |
|  | All-Ukrainian Association of Village Councils | Mr Vadym IVCHENKO | Head of Executive Board |
|  | All-Ukrainian Association of Village Councils | Ms Olena TOMNIUK | Deputy Head of Center of Development and International Cooperation |

- Participants from other partner institutions

|  | Zaporizka Oblast State Administration | Mr Petro HONCHARUK | Deputy Head |
| --- | --- | --- | --- |
|  | Sumy Oblast Council | Ms Vira PAVLOVA | Head of the Department of Oblast Programs and Budget Analysis |
|  | Sumy State University | Mr Yuriy PETRUSHENKO | Assistant Professor, Department of Economic Theory, CBA Project focal person |
|  | Resource Center On Sustainable Local Development (Knowledge Hub) under UADRC | Mr Yaroslav MATIYCHYK | Head of Resource Center on Sustainable Local Development |
|  | UADRC | Ms Iryna KORDUBA | Deputy Head of Secretariat |
|  | Union of Agriculture Service Cooperatives of Ukraine | Mr Ivan TOMYCH | Head of the Union |
|  | Union of Agriculture Service Cooperatives of Ukraine | Mr Vitaliy LVOV | Vice-president of the Union |

C) Participants from EU/UNDP/CBA Project

|  | Delegation of the European Union to Ukraine | Ms Miroslava DIDUKH | Project Manager |
| --- | --- | --- | --- |
|  | UNDP Ukraine | Ms Oksana REMIGA | Senior Programme Manager |
|  | CBA Project | Mr Jaysingh SAH | International Project Manager |

# Footnotes

Includes 12 MoUs signed and 11 partnership terminated

In the case of the ARC, the Republican Coordination Council is headed by the speaker of Verkhovna Rada of the ARC.

Excerpt from ‘How the Participation in Economic Cooperation Programme Affect the Changes in Social and Economic Indicators of Treated Communities: Analysis of First Phase of CBA Project” by Yuriy Petrushenko and  Nadiya Kostyuchenko; Sumy State University, Ukraine

# Text boxes

Map-I: CBA-II project area